## Failure Map Data
Country | Project name_WB | Project name_common | Sector | SubSector | Segment | Crossborder | Category of reason | Covid-19 specific | failure 증거 (기사 속 키워드) | Investment Size | Project Banks | Delayed Extent | FC Year |  | FC Year 증거 | Failure History | Affected Stage | Type of PPP | URLs | Resumed | Resume URL | 위치 기준 | Latitude | Longitude
Indonesia | Jakarta Bandung High-Speed Railway | N/A | Transport | Railways | Regional Passenger | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2017 | Updated Date | https://www.thejakartapost.com/news/2017/01/20/wika-to-sign-contract-for-highspeed-railway-next-week.html | Delayed | Delay in Construction | Greenfield | https://www.railway-technology.com/news/indonesia-high-speed-railway-project-delayed/ | Resumed | https://constructionreviewonline.com/2020/04/construction-of-jakarta-bandung-high-speed-railway-resumes/ | City | -6.2088 | 106.8456
Zimbabwe | Hwange Thermal Power Station Expansion | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2018 | April | https://www.esi-africa.com/industry-sectors/renewable-energy/zimbabwe-hwange-thermal-power-station-to-reach-financial-close/ | Delayed | Delay in Construction | Brownfield | https://www.esi-africa.com/industry-sectors/generation/coronavirus-outbreak-affects-renovations-at-hwange-power-station/ | Resumed | https://www.afrik21.africa/en/zimbabwe-solgas-energy-to-commission-its-solar-power-plant-in-hwange-in-august/ | Exact Location | -18.3824 | 26.4708
Zimbabwe | Robert Mugabe International Airport expansion | N/A | Transport | Airports | Runway and terminal | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | N/A | April | N/A | Delayed | Delay in Construction | Brownfield | https://www.sundaymail.co.zw/chinese-contractors-buy-zim-hire-locals | Resumed | https://www.herald.co.zw/us153m-airport-expansion-on-course/ | Exact Location | -17.9186 | 31.0973
Zimbabwe | NetOne expansion | N/A | ICT | ICT backbone | Land-based cables | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | N/A | April | N/A | Delayed | Delay in Construction | Brownfield | https://bulawayo24.com/index-id-news-sc-national-byo-183043.html | Resumed | https://www.herald.co.zw/netone-expansion-project-to-start-soon/ | City | -19.0154 | 29.1549
Pakistan | Thar Block 2 power plant | Thar Engro Coal Power Project | Energy | Electricity | Electricity generation | Yes | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2019 | April | https://mettisglobal.news/ppib-allows-extensions-in-financial-close-dates-of-2-thar-coal-power-projects | Delayed | Delay before Construction | Greenfield | https://www.eco-business.com/news/the-shadow-of-the-coronavirus-on-pakistan/ | N/A | N/A | Exact Location | 24.7753 | 70.3976
Kenya | Kisii-Ahero-Isebania road project | N/A | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | April | N/A | Delayed | Delay in Construction | Brownfield | https://www.the-star.co.ke/business/kenya/2020-04-16-multi--billion-road-projects-take-a-hit-as-workers-stay-home/ | N/A | N/A | City | -0.1744 | 34.9203
Kenya | Sh62 billion JKIA-Westlands Expressway | JKIA-Westlands Highway | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | April | N/A | Delayed | Delay in Construction | Brownfield | https://www.msn.com/en-xl/news/other/multi-billion-road-projects-take-a-hit-as-workers-stay-home/ar-BB12HJaK | N/A | N/A | Exact Location | -1.3228 | 36.926
Indonesia | Bangko Tengah PLTU (SS-8) | Bangko Tengah (SS-8) Power Station / South Sumatra 8 | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2014 | April | https://www.gem.wiki/Bangko_Tengah_(SS-8)_power_station | delayed | Delay in Construction | Greenfield | https://industri.kontan.co.id/news/jadwal-operasional-pembangkit-terganggu-wabah-corona-ini-tanggapan-pln?page=all | N/A | N/A | Exact Location | -3.7581 | 103.7924
Indonesia | Kalbar-1 PLTU | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2017 | April | https://pontianak.tribunnews.com/2018/08/01/proyek-pltu-kalbar-1-baru-35-persen | delayed | Delay in Construction | Greenfield | https://ekonomi.bisnis.com/read/20200803/44/1274372/vid-covid-tujuh-proyek-pembangkit-listrik-berkapasitas-6.510-mw-bakal-molor-nih | N/A | N/A | Exact Location | 0.81659 | 108.846
Indonesia | Nagan Raya PLTU | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | N/A | April | N/A | delayed | Delay in Construction | Greenfield | https://www.cnnindonesia.com/ekonomi/20200326073609-85-486915/investasi-pltu-berpotensi-rugi-rp209-t-gara-gara-corona | N/A | N/A | Exact Location | 4.1078 | 96.1978
Myanmar | 350MW LNG power plant in Thanlyin in Yangon | Myanmar Thanlyin LNG-to-Power project | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | N/A | April | N/A | delayed | Delay before Construction | Greenfield | https://frontiermyanmar.net/en/chinese-consortium-may-avoid-fines-despite-missing-emergency-power-deadline | Resumed | https://www.gastopowerjournal.com/markets/item/11078-lng-supply-to-chinese-built-power-plant-in-myanmar-now-in-full-swing | Exact Location | 16.7024 | 96.3314
Myanmar | 400-MW LNG power plant in Thaketa in Yangon | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | N/A | April | N/A | delayed | Delay before Construction | Greenfield | https://frontiermyanmar.net/en/chinese-consortium-may-avoid-fines-despite-missing-emergency-power-deadline | Resumed | https://www.frontiermyanmar.net/en/delayed-lng-projects-set-to-deliver-first-power-as-govt-approves-contract/ | Exact Location | 16.8163 | 96.2248
Myanmar | 150-MW LNG power plant in Kyaukphyu in Rakhine State | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | N/A | April | N/A | delayed | Delay before Construction | Greenfield | https://frontiermyanmar.net/en/chinese-consortium-may-avoid-fines-despite-missing-emergency-power-deadline | Resumed | https://oglinks.news/myanmar/news/power-plants-delayed-covid-19-start-operating-coming-months | Exact Location | 19.4026 | 93.5004
Lao PDR | Laos-China Railway | N/A | Transport | Railways | Regional Passenger | Yes | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2019 | \ | World Bank DB | delayed | Delay in Construction | Greenfield | https://www.rfa.org/english/news/laos/lao-china-railway-04072020150320.html | Resumed | https://www.globaltimes.cn/content/1186717.shtml | City | 19.8563 | 102.4955
Indonesia | Cirebon 2 | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2017 | April | World Bank DB | delayed | Delay in Construction | Brownfield | https://www.thejakartapost.com/news/2020/03/27/coal-plant-project-delays-might-cost-developers-13-1-billion-report.html | N/A | N/A | Exact Location | -6.7746 | 108.6318
Mozambique | China's CNPC LNG project | Rovuma LNG Project | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Transmission line delayed |  |  |  | N/A | April | N/A | delayed | Delay before Construction | Greenfield | https://www.clbrief.com/chinas-cnpc-natural-gas-project-in-mozambique-delayed/ | N/A | N/A | Exact Location | -10.7533 | 40.7983
Bangladesh | 1,250MW Payra coal-fired plant project in Patuakhali | Payra Power Station | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2020 | April | https://tbsnews.net/bangladesh/964m-financial-closure-payra-ports-capital-dredging-feb-39383 | delayed | Delay in Operation | Greenfield | https://tbsnews.net/bangladesh/infrastructure/coronavirus-stalls-payra-plant-commissioning-42067 | N/A | N/A | Exact Location | 21.9941 | 90.3049
Nepal | Pokhara Regional International Airport | N/A | Transport | Airports | Runway and terminal | No | covid-19 | labor shortage | Transmission line delayed |  |  |  | N/A | February | N/A | delayed | Delay in Construction | Greenfield | https://www.airport-technology.com/news/airport-construction-nepal-delay/ | N/A | N/A | Exact Location | 28.1852 | 84.0147
Bangladesh | Padma Multipurpose Bridge | N/A | Transport | Roads | Bridge | No | covid-19 | labor shortage | Transmission line delayed |  |  |  | 2012 | February | https://projects.worldbank.org/en/projects-operations/project-detail/P111017?lang=en&tab=procurement | delayed | Delay in Construction | Greenfield | https://thefinancialexpress.com.bd/trade/coronavirus-outbreak-construction-of-padma-bridge-impeded-1583122117 | Resumed | https://www.globaltimes.cn/content/1190037.shtml | Exact Location | 23.4368 | 90.2629
Costa Rica | San Carlos road | National Primary Route 35 of Costa Rica | Transport | Roads | Highway | No | covid-19, monetary, environmental | labor shortage | travel limit and shipping disruption |  |  |  | N/A | February | N/A | delayed | Delay in Construction | Greenfield | https://www.worldhighways.com/wh8/news/costa-rica-construction-contracts | N/A | N/A | City | 10.0159 | -84.2142
Indonesia | Java 7 PLTU | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage, supply chain | travel limit and shipping disruption |  |  |  | 2016 | May | https://www.gem.wiki/Jawa-7_power_station | delayed | Delay in Construction | Greenfield | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | N/A | N/A | Exact Location | -5.9917 | 106.1008
Indonesia | Kalselteng-1 | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage, supply chain | travel limit and shipping disruption |  |  |  | 2016 | April | https://www.gem.wiki/Kalselteng-1_power_station | delayed | Delay in Construction | Greenfield | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | N/A | N/A | Exact Location | -1.3715 | 113.5614
Montenegro | Bar-Boljare(Belgrade) motorway (A-1 motorway) | Belgrade-Bar railway | Transport | Roads | Highway | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2017 | April | N/A | delayed | Delay in Construction | Greenfield | https://balkaninsight.com/2020/09/30/montenegro-forced-to-extend-deadline-for-chinese-to-finish-highway/ | Resumed | https://seenews.com/news/chinas-crbc-to-complete-bridge-construction-project-in-montenegro-by-end-2020-722393 | Exact Location | 42.9719 | 19.602
Afghanistan | 178 km road of Yakawlang road | Dar-i-Suf to Yakawlang (178 Km) Road | Transport | Roads | Highway | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2017 | May | https://tolonews.com/business/200m-road-construction-agreement-signed | delayed | Delay in Construction | Greenfield | http://www.afghanistantimes.af/construction-projects-stagnate-in-bamyan-amid-covid-19/ | N/A | N/A | City | 34.7378 | 66.8586
Ghana | Pokuase Interchange | N/A | Transport | Roads | Highway | No | covid-19 | supply chain, others | travel limit and shipping disruption |  |  |  | 2016 | June | https://www.modernghana.com/news/736584/govt-secures-funds-for-pokuase-interchange.html | delayed | Delay in Construction | Greenfield | https://www.modernghana.com/news/1015290/covid-19-delays-completion-of-pokuase-interchange.html | Resumed | https://www.ghanabusinessnews.com/2020/11/20/obetsebi-lamptey-pokuase-interchanges-will-open-from-november-25-minister/ | Exact Location | 5.6887 | -0.27506
Sri Lanka | Sri Lanka waste-to-energy power plant in Colombo | KCHT Power Station Colombo South Waste Processing Facility Karadiyana W2E Project Karadiyana Power Station | Municipal Solid Waste | Treatment / Disposal | Incineration / Waste to Energy | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2018 | July | https://economynext.com/sri-lankas-hnb-syndicates-r9bn-loan-for-waste-to-energy-plant-10429/ | delayed | Delay in Construction | Greenfield | https://economynext.com/sri-lanka-waste-to-energy-power-plant-delayed-by-covid-19-travel-curbs-70837/ | N/A | N/A | City | 6.9334 | 79.8473
India | Bangalore Metro Rail | Bangalore Metro Rail Phase II - Namma Metro to Anjanapura | Transport | Railways | Regional Passenger | No | covid-19, legal issue | others | travel limit and shipping disruption |  |  |  | N/A | June | N/A | delayed | Delay in Construction | Greenfield | https://www.thehindu.com/news/cities/bangalore/bmrcl-misses-deadline/article32975347.ece | Resumed | https://www.thenewsminute.com/article/bengaluru-metro-yelachenahalli-anjanapura-route-likely-open-jan-15-141003 | City | 12.954 | 77.592
Indonesia | Kuningan East Ring Road in West Java | N/A | Transport | Roads | Highway | No | covid-19, monetary issue | others | Gov't Budget Reallocation / Regulatory Changes |  |  |  | N/A | March | N/A | delayed | Delay before Construction | Greenfield | https://www.thejakartapost.com/news/2020/04/23/covid-19-crisis-delays-several-infrastructure-projects.html | N/A | N/A | City | -6.9801 | 108.4869
Indonesia | Brebes Ring Road in Central Java | N/A | Transport | Roads | Highway | No | covid-19, monetary issue | others | Gov't Budget Reallocation / Regulatory Changes |  |  |  | N/A | April | N/A | delayed | Delay before Construction | Greenfield | https://www.thejakartapost.com/news/2020/04/23/covid-19-crisis-delays-several-infrastructure-projects.html | N/A | N/A | City | -6.8964 | 108.904
Zambia | Batoka Gorge hydroelectric project | Batoka Gorge Hydroelectric Power Station | Energy | Electricity | Electricity generation | Yes | covid-19 | preemptive action | N/A |  |  |  | 2018 | April | N/A | delayed | Delay before Construction | Greenfield | https://southerntimesafrica.com/site/news/batoka-project-to-start-in-2021 | Resumed | https://southerntimesafrica.com/site/news/batoka-project-to-start-in-2021 | Exact Location | -17.9195 | 26.1309
Zimbabwe | Centrale thermique de Lome | ContourGlobal Togo 100 MW power plant | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2008 | May | http://www.afrol.com/articles/32068 | delayed | Delay in Construction | Greenfield | https://www.agenceecofin.com/centrale/0603-74551-zimbabwe-le-coronavirus-ralentira-les-travaux-de-rehabilitation-de-la-centrale-de-hwange | N/A | N/A | City | -19.3971 | 29.9944
Nigeria | Lagos - Ibadan 150km railroad project | N/A | Transport | Railways | Regional Passenger | No | covid-19 | labor shortage | travel limit and shipping disruption |  |  |  | 2018 | March | N/A | delayed | Delay in Construction | Greenfield | https://www.railway-technology.com/news/completion-of-1-5bn-nigeria-project-delays-due-to-covid-19-outbreak/ | Resumed | https://www.bbc.com/pidgin/tori-53866767 | Exact Location | 6.9238 | 3.6363
Bangladesh | Rahanpur to Monakasha Border 400kV Transmission Line | N/A | Energy | Electricity | Electricity transmission | Yes | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | N/A | March | N/A | delayed | Delay in Construction | Greenfield | https://www.dhakatribune.com/bangladesh/power-energy/2020/05/12/ongoing-power-transmission-projects-hit-snag-for-corona-shutdown | N/A | N/A | City | 25.7541 | 89.2597
Bangladesh | Southwest Transmission Grid Expansion Project | N/A | Energy | Electricity | Electricity generation and transmission | No | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | 2018 | May | https://www.nsenergybusiness.com/news/adb-loan-power-transmission-bangladesh/ | delayed | Delay in Construction | Greenfield | https://www.dhakatribune.com/bangladesh/power-energy/2020/05/12/ongoing-power-transmission-projects-hit-snag-for-corona-shutdown | N/A | N/A | City | 23.0041 | 89.8306
Bangladesh | 500 MW HVDC Back-to-Back Station at Comilla North | 500 MW HVDC Back-to-Back Station at Cumilla North (Bangladesh) for Transfer of Power through Surjamaninagar (Tripura, India) - Comilla North (Bangladesh) | Energy | Electricity | Electricity transmission | No | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | 2017 | May | N/A | delayed | Delay in Construction | Greenfield | https://www.dhakatribune.com/bangladesh/power-energy/2020/05/12/ongoing-power-transmission-projects-hit-snag-for-corona-shutdown | N/A | N/A | City | 23.4738 | 91.1763
Bangladesh | Bheramara (Bangladesh)-Baharampur (India) 2nd 400kV Transmission Line | N/A | Energy | Electricity | Electricity transmission | Yes | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | 2017 | May | https://web.pgcb.gov.bd/project_details/148 | delayed | Delay in Construction | Greenfield | https://www.dhakatribune.com/bangladesh/power-energy/2020/05/12/ongoing-power-transmission-projects-hit-snag-for-corona-shutdown | N/A | N/A | City | 24.0625 | 89.0055
Bangladesh | Bakerganj-Barguna 132kV Transmission Line & Barguna 132/33kV Substation | N/A | Energy | Electricity | Electricity transmission | Yes | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | 2017 | May | https://web.pgcb.gov.bd/project_details/147 | delayed | Delay in Construction | Greenfield | https://www.dhakatribune.com/bangladesh/power-energy/2020/05/12/ongoing-power-transmission-projects-hit-snag-for-corona-shutdown | N/A | N/A | City | 22.1599 | 90.1169
Indonesia | Abadi Onshore LNG Complex | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19 | labor shortage | Gov't Budget Reallocation / Regulatory Changes |  |  |  | N/A | May | N/A | delayed | Delay before Construction | Greenfield | https://www.mentorimcgroup.com/2020/05/12/abadi-schedule-faces-delays-due-to-covid-concerns/ | N/A | N/A | Exact Location | -9.0823 | 131.3197
Egypt, Arab Rep. | Benban Solar Energy Complex | BenBan solar park | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | Although the opening of the new control and monitoring centre has been postponed until Q3 2020 due to the COVID-19 outbreak |  |  |  | 2018 | April | https://www.pv-magazine.com/2017/10/27/400-mw-pv-project-in-egypt-reaches-financial-close/ | delayed | Delay in Construction | Greenfield | https://www.worldcement.com/africa-middle-east/21042020/globaldata-egypts-construction-energy-market-outlook-remains-positive-despite-covid-19-delays/ | N/A | N/A | Exact Location | 24.4405 | 32.7416
India | Malhar Road project | N/A | Transport | Roads | Highway | No | covid-19 | preemptive action | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | April | N/A | delayed | Delay in Construction | Greenfield | https://economictimes.indiatimes.com/small-biz/productline/building-materials/ludhiana-smart-city-projects-hit-roadblock-thanks-to-covid-19/articleshow/75118864.cms | N/A | N/A | City | 30.913 | 75.8508
Colombia | La Linea Tunnel project | Centenario II Tunnel | Transport | Roads | Highway and tunnel | No | covid-19 | preemptive action | Non-availability of labourers due to Lockdown measure |  |  |  | 2019 | April | https://www.caf.com/en/currently/news/2009/03/us-270-million-for-la-linea-tunnel-in-colombia/ | delayed | Delay in Construction | Greenfield | https://www.roadtraffic-technology.com/projects/la-linea-tunnel-project/ | Resumed | https://www.bnamericas.com/en/news/colombia-looks-to-resume-infra-works-despite-covid-19 | City | 4.8511 | -75.8002
Indonesia | Sokoria Geothermal Power Plant (PLTP) | N/A | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | The construction for several renewable energy projects (PLT EBT) have been hampered along with the increasingly massive spread of the corona virus or Covid-19 in Indonesia, so CNBC in Indonesia. |  |  |  | 2016 | April | https://www.pwc.com/id/en/publications/assets/eumpublications/utilities/power-guide-2018.pdf | delayed | Delay in Construction | Greenfield | https://www.thinkgeoenergy.com/covid-19-situation-delaying-renewable-energy-development-in-indonesia/ | N/A | N/A | Exact Location | -8.7937 | 121.7662
India | Chardham all-weather road project | N/A | Transport | Roads | Highway | Yes | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  | 6month | N/A | April | N/A | delayed | Delay in Construction | Greenfield | https://economictimes.indiatimes.com/news/economy/infrastructure/covid-19-chardham-all-weather-road-project-to-be-delayed-due-to-lockdown/articleshow/75176701.cms | N/A | N/A | City | 30.9957 | 78.4611
Indonesia | Tanjung Jati B | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | 2017 | April | https://www.power-technology.com/projects/tanjung-jati-b-power-plant-expansion/ | delayed | Delay in Construction | Greenfield | https://www.cnnindonesia.com/ekonomi/20200326073609-85-486915/investasi-pltu-berpotensi-rugi-rp209-t-gara-gara-corona | N/A | N/A | Exact Location | -6.4454 | 110.7391
Indonesia | Sumsel-1 PLTU | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | 2017 | April | https://www.gem.wiki/Sumsel-1_power_station | delayed | Delay in Construction | Greenfield | https://www.cnnindonesia.com/ekonomi/20200326073609-85-486915/investasi-pltu-berpotensi-rugi-rp209-t-gara-gara-corona | N/A | N/A | Exact Location | -3.477 | 103.9958
Myanmar | 21MW Kyun Chaung gas power plant | N/A | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | 2019 | April | https://www.mmtimes.com/news/magwe-gas-plant-starts-running-vpower-says.html | Delayed | Delay in Operation | Greenfield | https://www.mmtimes.com/news/magwe-gas-plant-starts-running-vpower-says.html | Resumed | https://www.irrawaddy.com/news/burma/myanmar-power-plants-delayed-covid-19-start-operating-coming-months.html | City | 21.0326 | 94.4179
Indonesia | Bengkulu PLTU | N/A | Energy | Electricity | Electricity distribution | No | covid-19, monetary issue, capital issue | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | 2017 | April | https://www.gem.wiki/Bengkulu_power_station | Delayed | Delay in Construction | Greenfield | https://www.cnnindonesia.com/ekonomi/20200326073609-85-486915/investasi-pltu-berpotensi-rugi-rp209-t-gara-gara-corona | N/A | N/A | Exact Location | -3.912 | 102.2707
Mauritania | Greater Tortue/Ahmeyim FLNG Project | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19 | others | Travel limit and shipping disruption https://www.enerdata.net/publications/daily-energy-news/bp-delays-flng-delivery-greater-tortue-ahmeyim-senegal-mauritania.html" |  |  | 12month | 2018 | April | https://www.gem.wiki/Greater_Tortue_Ahmeyim_FLNG_Terminal | Delayed | Delay before Construction | Greenfield | https://www.fitchsolutions.com/corporates/oil-gas/covid-19-impact-mauritanias-greater-tortueahmeyim-flng-project-delayed-one-year-20-04-2020 | N/A | N/A | City | 19.5372 | -16.2601
Colombia | Toyo Tunnel | N/A | Transport | Roads | Highway and tunnel | No | monetary issue |  | Insufficient funding |  |  |  | 2015 | April | https://www.fcc.es/en/-/fcc-construira-el-proyecto-del-tunel-del-toyo-en-colombia-por-392-millones-de-euros | Delayed | Delay in Construction | Greenfield | https://www.worldhighways.com/wh8/news/key-colombia-tunnel-projects-delayed | Resumed | https://www.worldhighways.com/wh10/news/colombias-toyo-tunnel-project-underway | City | 6.7295 | -76.0006
India | Kochi Metro's Thykoodam-Pettah corridor | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2012 | April | https://www.railway-technology.com/projects/kochi-metro/ | Delayed | Delay in Construction | Greenfield | https://www.thehindu.com/news/cities/Kochi/metro-work-resumes/article31417634.ece | Resumed | https://www.thehindu.com/news/cities/Kochi/metro-work-resumes/article31417634.ece | City | 9.9577 | 76.3217
Myanmar | 380MW Manipur hydro project | N/A | Energy | Electricity | Electricity generation | No | etc. |  | High risks |  |  |  | 2004 | March | https://www.mmtimes.com/news/myanmar-suspends-manipur-hydro-project-chin-state.html | Delayed | Delay before Construction | Greenfield | https://www.mmtimes.com/news/myanmar-suspends-manipur-hydro-project-chin-state.html | N/A | N/A | City | 24.8346 | 93.8784
Vietnam | HCMC Saigon Metro line 1 (Ben Thanh – Suoi Tien) | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Travel limit and shipping disruption |  |  |  | N/A | August | N/A | Delayed | Delay in Construction | Greenfield | https://e.vnexpress.net/news/business/economy/saigon-metro-faces-delay-as-experts-unable-to-enter-vietnam-4125365.html | Resumed | https://tuoitrenews.vn/news/society/20190212/new-hope-as-construction-of-ho-chi-minh-city-metro-resumes-after-tet/48896.html | City | 10.776 | 106.6955
Bulgaria | Bulgaria's Belene nuclear power plant | The Belene Nuclear Power Plant | Energy | Electricity | Electricity generation | No | covid-19 | others | Tender Delayed |  |  |  | 2008 | July | https://www.power-technology.com/projects/belene-nuclear/ | Delayed | Delay before Construction | Greenfield | https://www.intellinews.com/coronavirus-outbreak-to-delay-launch-of-bulgaria-s-belene-project-181811/ | Resumed | https://www.reuters.com/article/bulgaria-nuclear-rosatom/update-1-rosatom-framatome-ge-team-up-for-bulgarian-nuclear-tender-idUSL8N2DV1KJ | City | 42.5212 | 25.2053
Mexico | 108MW Energía Sierra Juárez II wind farm | N/A | Energy | Electricity | Electricity generation | No | covid-19, political issue | supply chain | Tender Delayed |  |  | 2month | N/A | April | N/A | Delayed | Delay before Construction | Greenfield | https://expansion.mx/empresas/2020/07/23/ienova-ve-retrasos-por-el-coronavirus-y-el-gobierno-y-preve-reducir-inversiones | N/A | N/A | City | 32.5644 | -116.626
Philippines | Dito Telecommunity broadband cell tower project | N/A | ICT | ICT backbone | Land-based cables | No | covid-19 | labor shortage | Non-availability of labourers due to lockdown measure |  |  |  | N/A | April | N/A | Delayed | Delay in Operation | Greenfield | https://www.philstar.com/business/2020/07/01/2024914/coronavirus-delays-dennis-uys-dito-launch | Resumed | https://business.inquirer.net/309069/aboitiz-deploys-small-cells-to-help-telcos-improve-signal-internet | City | 12.3802 | 122.7673
China | Jiangyin LNG terminal | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19, monetary issue | others | Financial strain |  |  |  | N/A | July | N/A | Delayed | Delay in Operation | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/070720-analysis-chinas-new-lng-regas-projects-delayed-amid-covid-19-impact-financial-strain | N/A | N/A | Exact Location | 31.9321 | 120.1087
India | Mumbai Pune Expressway Project | Mumbai Pune Expressway Missing Link Project | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers |  |  |  | 2020 | July | https://www.deccanherald.com/business/irb-infra-achieves-rs-6610-cr-financial-closure-for-mumbai-pune-expressway-project-851117.html | Delayed | Delay in Construction | Brownfield | https://www.freepressjournal.in/mumbai/mumbai-pune-expressway-missing-link-project-deadline-extended#:~:text=The%20revised%20project%20completion%20deadline,as%20against%20February%202022%20earlier&text=Afcons%20Infrastructure%20and%20the%20Hyderabad,contractors%20carrying%20out%20this%20project. | Resumed | https://www.deccanherald.com/business/irb-infra-achieves-rs-6610-cr-financial-closure-for-mumbai-pune-expressway-project-851117.html | Exact Location | 18.7697 | 73.4043
Sri Lanka | Uma Oya hydroelectric power plant | Uma Oya Multipurpose Development Project | Energy | Electricity | Electricity generation | No | environmental issue |  | The project is reportedly being delayed due to continuing leaks which sprung during excavation on the Karadagolla tunnel |  |  |  | 2008 | April | https://www.newsfirst.lk/2019/04/19/uma-oya-project-in-its-final-phase-80-funded-by-sri-lanka/ | Delayed | Delay in Construction | Greenfield | http://www.china.org.cn/world/Off_the_Wire/2020-04/29/content_75991315.htm | Resumed | http://www.xinhuanet.com/english/2020-04/29/c_139018219.htm | City | 6.8014 | 81.0851
China | Chaozhou LNG terminal | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19, monetary issue | supply chain | Financial strain |  |  |  | N/A | April | N/A | Delayed | Delay in Construction | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/070720-analysis-chinas-new-lng-regas-projects-delayed-amid-covid-19-impact-financial-strain | N/A | N/A | Exact Location | 23.5766 | 117.1224
India | Navi Mumbai International Airport | Mumbai International Airport | Transport | Airports | Runway and terminal | No | covid-19 | others | Covid-19 |  |  |  | 2020 | July | https://economictimes.indiatimes.com/industry/transportation/airlines-/-aviation/sbi-takes-over-as-lead-financier-of-navi-mumbai-airport-project/articleshow/73720912.cms?from=mdr | Delayed | Delay in Construction | Greenfield | https://www.businessinsider.in/business/news/navi-mumbai-airport-construction-to-be-little-delayed-amid-coronavirus-pandemic/articleshow/75477515.cms | Resumed | https://www.freepressjournal.in/mumbai/navi-mumbai-international-airportwhen-it-will-see-the-flight-of-the-day-is-unclear | Exact Location | 18.993 | 73.0575
Mexico | 42MW Baja California Sur VI Combined Cycle Gas-Fired Plant | N/A | Energy | Electricity | Electricity generation | No | covid-19, monetary issue(global economy, productivity) | others | Gov't Budget Reallocation / Regulatory Changes |  |  |  | N/A | April | N/A | Cancelled | Cancel before Construction | Greenfield | https://realestatemarket.com.mx/noticias/infraestructura-y-construccion/29268-cfe-cancela-construccion-de-plantas-electricas-en-diferentes-estados | N/A | N/A | City | 25.1029 | -111.7077
Mexico | 804.8MW San Luis Potosí Combined Cycle Gas-Fired Plant | N/A | Energy | Electricity | Electricity generation | No | covid-19, monetary issue | supply chain | Gov't Budget Reallocation / Regulatory Changes |  |  |  | N/A | July | N/A | Cancelled | Cancel before Construction | Greenfield | https://www.proyectosmexico.gob.mx/proyecto_inversion/0889-cfe-central-323-ciclo-combinado-san-luis-potosi/ | N/A | N/A | City | 21.8042 | -100.9326
Nepal | Melamchi Water Supply Project | N/A | Water and sewerage | Treatment plant | Sewerage treatment plant | No | covid-19, legal issue | supply chain | Travel limit and shipping disruption |  |  |  | 2000 | July | https://www.spotlightnepal.com/2020/07/12/melamchi-dream-come-true/ | Delayed | Delay in Construction | Greenfield | https://kathmandupost.com/valley/2020/04/06/melamchi-likely-to-face-more-delays-as-workers-leave-the-site | Resumed | https://myrepublica.nagariknetwork.com/news/japan-pleased-to-see-successful-completion-of-melamchi-water-supply-project/ | Exact Location | 27.8258 | 85.5794
Tunisia | Nawara gas field development project | South Tunisia Gas Project (STGP) | Energy | Natural Gas | Natural gas transmission | No | covid-19 | others | Covid-19 |  |  |  | 2015 | April | https://projectsportal.afdb.org/dataportal/VProject/show/P-TN-FD0-006 | Delayed | Delay in Construction | Greenfield | https://www.meed.com/covid-19-delays-work-on-tunisian-gas-project | N/A | N/A | Exact Location | 33.9341 | 10.0099
Bangladesh | Dhaka Metrorail project | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19, legal issue | supply chain | Travel and shipment disruption due to Covid-19 |  |  |  | 2013 | April | https://tbsnews.net/bangladesh/infrastructure/launch-metro-rail-likely-be-delayed-101605 | Delayed | Delay in Construction | Greenfield | https://bdnews24.com/economy/2020/06/14/coronavirus-crisis-derails-bangladesh-metrorail-project | Resumed | https://www.dhakatribune.com/bangladesh/dhaka/2020/09/04/metro-rail-s-construction-progressing-fast-with-49-15-completion | City | 23.8034 | 90.407
Colombia | Cambao-Manizales Highway (256KM) | Vía cambao-Manizales | Transport | Roads | Highway | No | environmental issue |  | Dispute between concessionare and ANI(National Infrastructure Agency) |  |  |  | 2015 | June | https://www.infrapppworld.com/news/colombia-awards-fifth-private-initiative-in-road-sector | Cancelled | Cancel before Construction | Brownfield | https://www.elolfato.com/via-cambao-manizales-otra-promesa-sin-cumplir-para-los-tolimenses | Resumed | https://www.carreteras-pa.com/noticias/colombia-reactiva-obras-de-la-via-4g-cambao-manizales/ | City | 5.0223 | -74.0288
India | ACME Jaipur 250MW Solar Power Plant | N/A | Energy | Electricity | Electricity generation | No | covid-19, capital issue | supply chain | Land aquisition delays plus further delays casued by Covid-19 |  |  |  | 2018 | April | https://www.business-standard.com/article/companies/acme-to-cancel-india-s-cheapest-solar-project-citing-covid-19-impact-120052000977_1.html | Cancelled | Cancel before Construction | Greenfield | https://www.reuters.com/article/india-solar/citing-covid-uncertainty-indias-acme-solar-cancels-deal-to-supply-power-at-record-low-tariff-idUSL4N2D22TL | N/A | N/A | City | 24.5367 | 81.3033
China | Jiaxing LNG | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19, monetary issue | supply chain | Financial strain |  |  |  | 2019 | April | https://www.seatrade-maritime.com/ports-logistics/jiaxing-lng-terminal-starts-construction | Delayed | Delay in Operation | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/070720-analysis-chinas-new-lng-regas-projects-delayed-amid-covid-19-impact-financial-strain | N/A | N/A | City | 30.6784 | 121.2277
India | Kajauli waterworks phases V and VI | N/A | Water and sewerage | Treatment plant | Portable water and sewerage treatment | No | covid-19, legal issue | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | July | N/A | Delayed | Delay in Construction | Greenfield | https://timesofindia.indiatimes.com/city/chandigarh/covid-19-impact-labour-crunch-delays-mohali-water-project/articleshow/76345299.cms | N/A | N/A | City | 30.7478 | 76.6382
Colombia | 2.4 GW Hidro Ituango project | N/A | Energy | Electricity | Electricity generation | No | environmental issue | N/A | the collapse of a water diversion tunnel forced the evacuation of 113,000 people and prompted the regional Antioquia government to declare a state of emergency amid fears of catastrophic flooding. |  |  |  | N/A | June | N/A | Delayed | Delay in Construction | Greenfield | https://www.bnamericas.com/en/news/covid-19-delays-colombias-hidroituango-mega-dam-project | N/A | N/A | City | 7.1715 | -75.7647
Colombia | 2.4 GW Hidro Ituango project | N/A | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | June | N/A | Delayed | Delay in Construction | Greenfield | https://www.bnamericas.com/en/news/covid-19-delays-colombias-hidroituango-mega-dam-project | N/A | N/A | City | 7.1715 | -75.7647
China | Damaiyu LNG | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19, monetary issue | supply chain | Financial strain |  |  |  | 2018 |  | https://www.gem.wiki/Damaiyu_LNG_Terminal | Delayed | Delay in Operation | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/070720-analysis-chinas-new-lng-regas-projects-delayed-amid-covid-19-impact-financial-strain | N/A | N/A | Exact Location | 28.1061 | 121.1348
Argentina | RenovAr renewable tenders: 1, 1.5, 2 and 3 | N/A | Energy | Electricity | Electricity generation | No | covid-19, legal issue | preemptive action | Tender Delayed |  |  |  | N/A | July | N/A | Delayed | Delay before Construction | Greenfield | https://www.bnamericas.com/en/news/argentina-extends-progress-deadlines-for-renewable-energy-projects | N/A | N/A | City | -34.6033 | -58.3816
Montenegro | Velje brdo PV plant | N/A | Energy | Electricity | Electricity generation | No | covid-19 | others | Tender Delayed |  |  |  | N/A | June | N/A | Delayed | Delay before Construction | Greenfield | https://balkangreenenergynews.com/velje-brdo-pv-plant-tender-to-start-by-year-end-could-expand-to-300-mw/ | N/A | N/A | City | 42.4846 | 19.2184
China | Jiangsu Binhai LNG | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19, monetary issue | supply chain | Financial strain |  |  |  | N/A | June | N/A | Delayed | Delay in Operation | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/070720-analysis-chinas-new-lng-regas-projects-delayed-amid-covid-19-impact-financial-strain | N/A | N/A | Exact Location | 34.2875 | 120.2713
Bangladesh | 1,600-MW Jharkhand project | Adani – Godda Coal-Fired Thermal Power Plant 1600 MW – Jharkhand | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2019 | July | https://www.gem.wiki/Adani_Godda_power_station | Delayed | Delay before Construction | Greenfield | https://www.business-standard.com/article/companies/1-600-mw-jharkhand-project-delayed-amid-covid-19-lockdown-adani-power-120060101759_1.html | N/A | N/A | Exact Location | 24.8159 | 87.1351
Nigeria | Akanu Ibiam International Airport, Enugu | Enugu Airport | Transport | Airports | Runway and terminal | No | covid-19 | labor shortage | decision to suspend work to the COVID-19 pandemic |  |  |  | N/A | June | N/A | Delayed | Delay in Construction | Brownfield | https://www.sunnewsonline.com/work-resumes-at-enugu-airport/ | Resumed | https://www.sunnewsonline.com/work-resumes-at-enugu-airport/ | Exact Location | 6.4718 | 7.5677
Nepal | NEA Tanahun HPP | 140 MW Tanahu Hydropower Project | Energy | Electricity | Electricity generation and transmission | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | 2013 | June | https://www.eib.org/en/projects/pipelines/all/20120278 | Delayed | Delay in Construction | Greenfield | https://www.hydroreview.com/2020/03/09/coronavirus-may-significantly-delay-hydro-project-construction/#gref | N/A | N/A | Exact Location | 27.9594 | 84.2746
Nepal | Gautam Buddha International Airport (GBIA) | N/A | Transport | Airports | Runway and terminal | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Brownfield | https://www.nepalisansar.com/government/nepal-resumes-gbia-airport-construction-amid-covid-19/ | Resumed | https://www.tourismmail.com/construction-of-gautam-buddha-international-airport-resumes | Exact Location | 27.5069 | 83.4197
Bangladesh | Dhaka Mass Rapid Transit Line 6 | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | 2020 | May | https://www.railwaypro.com/wp/jica-to-provide-safety-management-ta-for-dhaka-mrt-line-6/ | Delayed | Delay in Construction | Greenfield | https://thefinancialexpress.com.bd/trade/first-metro-rail-arrival-from-japan-uncertain-1587093264 | Resumed | https://www.dhakatribune.com/bangladesh/dhaka/2020/06/03/metro-rail-construction-to-resume | Exact Location | 23.8418 | 90.3635
Russian Federation | Unit 2 of the Leningrad II nuclear power plant in western Russian | Leningrad II unit 2 | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | Travel limit and shipping disruption |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Brownfield | https://www.world-nuclear-news.org/Articles/Leningrad-II-2-start-up-postponed-to-April-2021 | N/A | N/A | Exact Location | 59.8279 | 29.0535
Congo, Dem. Rep. | Kisangani Solar Photovoltaic Power plant | N/A | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | Travel limit and shipping disruption |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://globalpressjournal.com/africa/democratic-republic-of-congo/coronavirus-claims-another-victim-solar-power-plant-drc/ | N/A | N/A | City | 0.51868 | 25.2013
Nepal | Upper Tamakoshi Project | Upper Tamakoshi Hydroelectric Project | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Travel limit and shipping disruption |  |  |  | 2018 | May | https://kclastute.com/assets/uploads/files/articles/Upper_Tamakoshi_ERP_(1).pdf | Delayed | Delay in Construction | Greenfield | https://myrepublica.nagariknetwork.com/news/upper-tamakoshi-project-likely-to-be-delayed/#:~:text=KATHMANDU%2C%20May%2025%3A%20The%20completion,19%20lockdown%20in%20the%20country.&text=The%20project%20was%20expected%20to,has%20impacted%20the%20project%20deadline. | N/A | N/A | Exact Location | 27.9247 | 86.2132
China | Rudong LNG phase 3 | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19 | supply chain | Financial strain |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/070720-analysis-chinas-new-lng-regas-projects-delayed-amid-covid-19-impact-financial-strain | N/A | N/A | City | 32.3577 | 121.1711
Bangladesh | Runway capacity enhancement project at Shah Amanat International Airport | Shah Amanat International Airport Runway | Transport | Airports | Runway and terminal | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | N/A | July | N/A | Delayed | Delay in Operation | Brownfield | https://tbsnews.net/economy/aviation/covid-19-chattogram-airports-runway-strengthening-work-stalled-98896 | N/A | N/A | Exact Location | 22.2458 | 91.8145
China | Qingdao LNG phase 2 | N/A | Energy | Natural Gas | Natural gas transmission | No | covid-19 | supply chain | Financial strain |  |  |  | N/A | June | N/A | Delayed | Delay in Construction | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/070720-analysis-chinas-new-lng-regas-projects-delayed-amid-covid-19-impact-financial-strain | N/A | N/A | City | 36.094 | 120.386
Cambodia | 400MW Heavy fuel oil power plant in Kandal province | 400 MW Kandal HFO/LNG Power Plants Project | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | 2019 | July | https://www.khmertimeskh.com/50739921/completion-of-heavy-fuel-oil-power-plant-in-kandal-will-ease-power-shortages/ | Delayed | Delay in Construction | Greenfield | https://thailand-construction.com/cambodias-power-plant-in-kandal-province-delayed-by-covid-19-travel-bans/ | N/A | N/A | Exact Location | 11.539 | 105.0887
India | Kempegowda International Airport (KIA) : second terminal | N/A | Transport | Airports | Runway and terminal | No | capital issue |  | Lower Demand Projection |  |  |  | 2019 | June | https://www.livemint.com/news/india/bengaluru-airport-to-come-up-with-terminal-2-gets-rs-10-000-crore-1565090581735.html | Delayed | Delay in Construction | Brownfield | https://www.deccanherald.com/city/bengaluru-infrastructure/kia-second-terminal-to-be-delayed-by-6-to-12-months-844968.html | N/A | N/A | Exact Location | 13.1987 | 77.7065
Montenegro | 250 MW Briska Gora solar plant | Briska Gora solar power plant | Energy | Electricity | Electricity generation | No | covid-19 | others | Travel limit and shipping disruption |  |  |  | N/A | June | N/A | Delayed | Delay in Construction | Greenfield | https://www.karanovicpartners.com/news/tender-for-the-solar-power-plant-in-podgorica-at-velje-brdo-by-the-end-of-the-year/ | N/A | N/A | City | 41.9677 | 19.2943
Namibia | Upgrade of the dual carriageway on the Windhoek-Okahandja road | Upgrade of WIndhoek-Okahandja road | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | June | N/A | Delayed | Delay in Construction | Greenfield | https://www.namibiansun.com/news/massive-capital-projects-delayed2020-06-05 | N/A | N/A | City | -22.5044 | 17.078
Namibia | Upgrade to a dual carriageway of the Windhoek to Hosea Kutako International Airport road | Windhoek-Hosea Kutako Airport Road Upgrade | Transport | Roads | Highway | No | covid-19 | others | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | June | N/A | Delayed | Delay in Construction | Greenfield | https://www.namibiansun.com/news/massive-capital-projects-delayed2020-06-05 | N/A | N/A | City | -22.5044 | 17.078
Myanmar | Falam's airport in Chin State | Falam (Surbung) New Airport Project | Transport | Airports | Runway and terminal | No | covid-19, environmental | others | Travel limit and shipping disruption |  |  |  | 2015 | N/A | N/A | Delayed | Delay in Operation | Greenfield | https://consult-myanmar.com/2020/06/05/opening-of-the-first-airport-in-myanmars-chin-state-delayed-amid-covid-19/ | Resumed | https://www.mmtimes.com/news/construction-chin-state-airports-make-progress-despite-covid-19.html | Exact Location | 22.9342 | 93.6151
India | Waste-to Energy Plant at Kapuluppada | Waste-to-energy(WTE) power project | Municipal Solid Waste | Treatment / Disposal | Incineration / Waste to Energy | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2018 | June | https://solidwasteindia.com/wte-plant-at-kapuluppada-to-begin-operations-in-december-2020/ | Delayed | Delay in Construction | Greenfield | https://www.thehindu.com/news/cities/Visakhapatnam/waste-to-energy-plant-to-be-ready-by-year-end/article31760959.ece | Resumed | https://www.thehindu.com/news/cities/Visakhapatnam/waste-to-energy-plant-to-be-ready-by-year-end/article31760959.ece | City | 17.8352 | 83.3846
Mexico | Terminal 3 of Mexico City International Airport (AICM) | Mexico City new International Airport | Transport | Airports | Runway and terminal | No | covid-19 | others | Lower Demand Projection |  |  |  | N/A |  | N/A | Cancelled | Cancel in Construction | Greenfield | https://simpleflying.com/mexico-city-terminal-canceled/ | N/A | N/A | Exact Location | 19.436 | -99.0718
Bolivia | 290 MW Ivirizu hydropower plant | 290.2-MW Ivirizu hydroelectric project | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2017 | June | https://www.chinadaily.com.cn/business/2017-08/19/content_30826511.htm | Delayed | Delay in Construction | Greenfield | https://webcache.googleusercontent.com/search?q=cache:pEGTBzVfbmsJ:https://www.bnamericas.com/en/news/bolivia-pushes-back-geothermal-call+&cd=1&hl=ko&ct=clnk&gl=kr | N/A | N/A | City | -16.8262 | -65.0067
Bolivia | 100MW Laguna Colorada geothermal project(Second Stage) | Laguna Colorada geothermal project | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2017 | March | https://geothermalresourcescouncil.blogspot.com/2017/03/Bolivia-geothermal.html | Delayed | Delay before Construction | Greenfield | https://newenergyevents.com/laguna-colorada-geothermal-project-faces-covid-19-delays/ | N/A | N/A | Exact Location | -22.434 | -67.7563
Malaysia | East Coast Rail Link project | East Coast Rail Line project | Transport | Railways | Regional Passenger | No | covid-19 | labor shortage | Travel limit and shipping disruption |  |  |  | 2016 | March | https://en.wikipedia.org/wiki/MRL_East_Coast_Rail_Link | Delayed | Delay in Construction | Greenfield | https://www.straitstimes.com/asia/se-asia/malaysia-gives-green-light-for-construction-to-resume-on-east-coast-rail-link | Resumed | https://www.straitstimes.com/asia/se-asia/malaysia-gives-green-light-for-construction-to-resume-on-east-coast-rail-link | City | 2.9999 | 101.396
Philippines | 2x668-MW supercritical coal-fired power project | Dinginin power station | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Travel limit and shipping disruption |  |  |  | 2015 | March | https://www.gem.wiki/Dinginin_power_station | Delayed | Delay in Construction | Greenfield | https://www.philstar.com/business/2020/03/18/2001646/bataan-coal-plant-completion-delayed | N/A | N/A | Exact Location | 14.425 | 120.537
Indonesia | 510 MW Batang Toru hydropower plants | Batang Toru hydropower project | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Travel limit and shipping disruption |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.hydroreview.com/2020/03/02/coronavirus-delays-construction-progress-on-510-mw-batang-toru-hydropower-plant-in-indonesia/ | N/A | N/A | Exact Location | 1.3449 | 99.1008
Ecuador | Quito Metro | Metro de Quito | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.construccionlatinoamericana.com/metro-de-quito-paralizado-por-coronavirus/142852.article | Resumed | https://en.travel2latam.com/nota/60769-quitos-tourism-sector-prepared-to-receive-visitors | Exact Location | -0.29859 | -78.5555
Nepal | 54 MW Super Dordikhola Hydropower Project 'B' | Super Dordi Hydropower Project | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Resumed | https://www.eadarsha.com/eng/super-dordi-b-hydel-project-80-per-cent-complete/ | Exact Location | 28.1834 | 84.3343
Nepal | 25 MW Upper Dordi 'A' Project | Upper Dordi 'A' Hydropower Project | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | 2014 | March | https://kathmandupost.com/money/2014/09/30/building-of-upper-dordi-to-start-after-holidays | Delayed | Delay in Construction | Greenfield | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | N/A | N/A | Exact Location | 28.15 | 84.2846
Nepal | 12 MW Dordi-1 Project | Dordi-1 Hydro electric project | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | 2016 | March | http://www.ledco.com.np/Page/index.php?PageID=5 | Delayed | Delay in Construction | Greenfield | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | N/A | N/A | City | 28.3005 | 84.5797
Nepal | 27 MW Dordikola Hydropower Project | Dordikola Hydropower Project | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | 2011 | March | N/A | Delayed | Delay in Construction | Greenfield | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | N/A | N/A | Exact Location | 28.10 to 28.1332 | 84.26 to 84.2830
Nepal | 30 MW Nyadi Hydropower Project | Nyadi Hydropower Project | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | 2017 | March | https://ppi.worldbank.org/en/snapshots/project/Nyadi-Hydropower-Plant-9085 | Delayed | Delay in Construction | Greenfield | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Resumed | https://www.investopaper.com/news/nyadi-hydropower-project/ | City | 28.3276 | 84.3991
Nepal | 40.27 MW Upper Nyandi Hydropower Project | Super Nyadi Hydropower Project (40.27 MW) | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | N/A | N/A | City | 28.3016 | 84.3987
Nepal | 2.4 MW Upper Syange Khola | Upper Syange Khola Small Hydropower Project | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2018 | March | https://www.sharesansar.com/newsdetail/upper-syange-hydropower-completes-financial-closure-for-2-4-mw-upper-syange-hydropower-project | Delayed | Delay in Construction | Greenfield | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | N/A | N/A | City | 28.2969 | 84.3699
Nepal | 7.7 MW Midimkhola | Midimkhola hydropower projects | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | N/A | N/A | City | 28.3062 | 84.4207
Russian Federation | 200-megawatt (MW) wind power project in Kalmykia | 200MW Kalmykia Wind Farm | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | force majeure |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://www.kommersant.ru/doc/4348520 | N/A | N/A | City | 46.4842 | 44.4007
Argentina | Cauchari solar power plant | Cauchari Solar Park Project | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.energiaestrategica.com/coronavirus-nuevas-medidas-de-mitigacion-afectan-el-avance-en-obras-de-proyectos-de-renovables-pero-no-la-operacion-de-parques/ | N/A | N/A | City | -25 | -67
Argentina | Loma Blanca Wind Portfolio | Loma Blanca Wind Farm (Parque eólico Loma Blanca) I, II, III, VI | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of components and personnel due to Lockdown measure |  |  |  | 2019 | March | World Bank DB | Delayed | Delay in Construction | Greenfield | https://www.energiaestrategica.com/coronavirus-nuevas-medidas-de-mitigacion-afectan-el-avance-en-obras-de-proyectos-de-renovables-pero-no-la-operacion-de-parques/ | N/A | N/A | Exact Location | -43.1291 | -65.2577
Argentina | Bicentennial, Mataco and San Jorge wind project(RenovAr Program) | Parque del Bicentenario, El Mataco and San Jorge wind complex(RenovAr Program) | Energy | Electricity | Electricity generation | No | covid-19 | others | The Argentine government issued a total quarantine until the end of the month, which will begin to affect the construction of at least 10 wind farms by companies such as Goldwind, Genneia and PCR, for more than 850 MW. Generators do not consider that they will have difficulties operating their parks. |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.energiaestrategica.com/coronavirus-nuevas-medidas-de-mitigacion-afectan-el-avance-en-obras-de-proyectos-de-renovables-pero-no-la-operacion-de-parques/ | N/A | N/A | City | -48.3535 | -69.3757
Philippines | Power Source First Bulacan Solar Plant | Bulacan solar power plant | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | travel limit and shipping disruption |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.pna.gov.ph/articles/1094786 | Resumed | https://businessmirror.com.ph/2020/04/29/mgen-gets-ok-to-resume-work-on-bulacan-solar-power-project/ | Exact Location | 15.0223 | 121.0552
India | 1.2km Purana Qila road tunnel | Pragati Maidan tunnel | Transport | Roads | Highway and tunnel | No | covid-19 | preemptive action | Gov't Budget Reallocation / Regulatory Changes |  |  | 6 | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.hindustantimes.com/cities/pandemic-sets-back-delhi-s-infra-projects-by-six-months/story-0fcq2ElDkD66hYyifQIvlL.html | Resumed | https://timesofindia.indiatimes.com/city/delhi/pragati-maidan-work-on-with-45-workers/articleshow/75652190.cms | Exact Location | 28.6155 | 77.2372
India | Barapullah phase-3 elevated corridor | Barapullah Road Phase-III Route | Transport | Roads | Highway | No | covid-19 | preemptive action | Gov't Budget Reallocation / Regulatory Changes |  |  | 6 | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.hindustantimes.com/cities/pandemic-sets-back-delhi-s-infra-projects-by-six-months/story-0fcq2ElDkD66hYyifQIvlL.html | Resumed | https://www.newindianexpress.com/cities/delhi/2020/jun/15/air-pollution-covid-19-lockdown-slows-down-delhis-much-needed-makeover-2156750.html | City | 28.5919 | 77.2616
India | Ashram underpass | Ashram Underpass | Transport | Roads | Highway | No | covid-19 | preemptive action | Gov't Budget Reallocation / Regulatory Changes |  |  | 6 | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.hindustantimes.com/cities/pandemic-sets-back-delhi-s-infra-projects-by-six-months/story-0fcq2ElDkD66hYyifQIvlL.html | Resumed | https://www.hindustantimes.com/delhi-news/traffic-to-be-restricted-at-ashram-chowk-towards-bhogal-for-two-nights-till-thursday/story-sRmQoBXGjU0ZsJmBDIaanO.html | Exact Location | 28.5725 | 77.2583
India | Benito-Juarez Road underpass | Benito Juarez Marg | Transport | Roads | Highway | No | covid-19 | preemptive action | Gov't Budget Reallocation / Regulatory Changes |  |  | 6 | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.hindustantimes.com/cities/pandemic-sets-back-delhi-s-infra-projects-by-six-months/story-0fcq2ElDkD66hYyifQIvlL.html | N/A | N/A | Exact Location | 28.5824 | 77.1639
Nepal | Chilime Rasuwagadhi HPP | Rasuwagadhi Hydroelectric Power Plant Project | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | travel limit and shipping disruption |  |  |  | 2012 | March | World Bank DB | Delayed | Delay in Construction | Greenfield | https://www.hydroreview.com/2020/03/09/coronavirus-may-significantly-delay-hydro-project-construction/#gref | N/A | N/A | Exact Location | 28.2709 | 85.3769
Bosnia and Herzegovina | 160 MW hydro power plant (HPP) HE Dabar | 160 MW Dabar Hydro Power Plant | Energy | Electricity | Electricity generation | No | covid-19 | others | Has been delayed by a month due to the coronavirus outbreak in China |  |  | 1 | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://seenews.com/news/coronavirus-to-delay-dabar-hpp-project-in-bosnias-serb-republic-report-689960 | N/A | N/A | City | 42.7077 | 18.3502
Brazil | Piauí Solar PV Projects | 40 MW solar PV portfolio in Piaui | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | Tender Delayed |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://renewablesnow.com/news/brazils-piaui-resumes-plans-to-tender-40-mw-of-solar-703795/ | Resume | https://renewablesnow.com/news/brazils-piaui-resumes-plans-to-tender-40-mw-of-solar-703795/ | City | -7.6651 | -42.6519
Philippines | Ninoy Aquino International Airport (NAIA) Rehabilitation project | N/A | Transport | Airports | Runway and terminal | No | covid-19 | preemptive action | Adherence to community quarantine |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Brownfield | https://business.inquirer.net/292649/big-infra-projects-face-delays-due-to-covid-19 | N/A | N/A | Exact Location | 14.5119 | 121.0164
Philippines | Sangley International Airport project | Sangley Point International Airport (SPIA) project | Transport | Airports | Runway and terminal | No | covid-19 | preemptive action | Adherence to community quarantine |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://business.inquirer.net/299736/macroasia-cccc-seeks-more-time-to-submit-final-bid-for-sangley-airport | N/A | N/A | Exact Location | 14.4899 | 120.8944
Colombia | Carrizal Wind Farm (195MW) | N/A | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Delay in the construction of transmission line |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://ijglobal.com/articles/146502/covid-19-delays-threaten-colombian-wind-projects | N/A | N/A | City | 11.5374 | -72.425
Colombia | Irraipa Wind Farm (99MW) | N/A | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Delay in the construction of transmission line |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://ijglobal.com/articles/146502/covid-19-delays-threaten-colombian-wind-projects | N/A | N/A | City | 12.1228 | -71.9514
Colombia | 110 kV Nueva San Juan substation | 110 kV Nueva San Juan substation | Energy | Electricity | Electricity transmission | No | covid-19 | supply chain | Delay in procurement process of transmission line |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://ijglobal.com/articles/147414/third-delay-for-colombia-transmission-tender | N/A | N/A | City | 4.6115 | -77.6046
Colombia | 110 kV Nueva Río substation | 110 kV Nueva Río substation | Energy | Electricity | Electricity transmission | No | covid-19 | supply chain | Delay in procurement process of transmission line |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | https://ijglobal.com/articles/147414/third-delay-for-colombia-transmission-tender | N/A | N/A | City | 11.0055 | -74.8024
Colombia | 110 kV Nueva Toluviejo | 110 kV Nueva Toluviejo | Energy | Electricity | Electricity transmission | No | covid-19 | supply chain | Delay in procurement process of transmission line |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | https://ijglobal.com/articles/146502/covid-19-delays-threaten-colombian-wind-projects | N/A | N/A | City | 9.4529 | -75.4479
Papua New Guinea | Papua LNG | PNG LNG Project | Energy | Natural Gas | Natural gas transmission | No | political issue | N/A | Tender Delayed |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | https://www.maritime-executive.com/editorials/papua-new-guinea-lng-projects-likely-to-be-delayed | N/A | N/A | City | -9.445 | 147.1814
Philippines | Power Source Tarlac Solar Plant | 50-MW Tarlac solar power plant | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.pna.gov.ph/articles/1094786 | Resumed | https://businessmirror.com.ph/2020/04/29/mgen-gets-ok-to-resume-work-on-bulacan-solar-power-project/ | City | 15.4729 | 120.4729
Myanmar | 151-MW power plant in Ahlone Township, Yangon | 151MW Ahlone Power Plant | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Travel limit and shipping disruption |  |  |  | 2013 | March | https://ppi.worldbank.org/en/snapshots/project/ahlone-power-plant-7829 | Delayed | Delay in Construction | Greenfield | https://elevenmyanmar.com/news/govt-faces-hydropower-project-delays-due-to-covid-19 | Resumed | https://www.petroleum-economist.com/articles/midstream-downstream/power-generation/2020/myanmar-lng-projects-overcome-pandemic-and-sceptics | City | 15.4854 | 120.6133
Malaysia | Sungai Krian and Batang Saribas bridge projects | N/A | Transport | Roads | Bridge | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://sarawakvoice.com/2020/06/12/jambatan-sungai-krian-dan-batang-saribas-akan-legakan-penduduk/ | Resumed | https://www.malaymail.com/news/malaysia/2020/06/11/construction-of-bridges-in-sarawak-to-resume-after-covid-19-delays-says-cm/1874589 freemalaysiatoday.com/category/nation/2020/06/11/work-on-2-sarawak-bridges-resumes/ | City | 1.6337 | 111.1723
Indonesia | Bailey Bridges Upgrading Project | N/A | Transport | Roads | Bridge | No | covid-19 | preemptive action | Temporary delay caused by covid-19 pandemic |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Brownfield | https://dayakdaily.com/rm194-million-bridge-upgrades-to-resume-after-delays-due-to-covid-19/ | Resumed | https://dayakdaily.com/rm194-million-bridge-upgrades-to-resume-after-delays-due-to-covid-19/ | City | 1.0428 | 108.3025
Thailand | High-speed railway 250km | High-speed railway 250km between Hua Lamphong station and northeastern town of Nakhow Ratchasima | Transport | Railways | Regional Passenger | No | covid-19, political issue | labor shortage | Travel limit and shipping disruption |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://www.oboreurope.com/en/railway-construction-thailand/ | N/A | N/A | City | 13.7385 | 100.5166
Myanmar | Muse-Mandalay railway link | N/A | Transport | Railways | Regional Passenger | Yes | covid-19, political issue | labor shortage | Travel limit and shipping disruption |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | http://www.globalconstructionreview.com/news/chinas-plans-southeast-asia-suffer-coronavirus-sho// | Resumed | https://www.irrawaddy.com/news/burma/myanmar-china-conduct-feasibility-study-mandalay-kyaukphyu-rail-link.html | City | 23.9937 | 97.9095
Myanmar | Kyaukphyu special economic zone (sea port, power stations and industrial parks) | Kyaukphyu SEZ | Others | Others | Other | No | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Brownfield | http://www.globalconstructionreview.com/news/chinas-plans-southeast-asia-suffer-coronavirus-sho/ | N/A | N/A | City | 19.4214 | 93.5436
Nigeria | Lagos-Ibadan Expressway | 127.6km Lagos-Ibadan Expressway | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2017 | May | https://www.iflr1000.com/File?fileName=IFLR1000_E%26I2017_Africa%20edited.pdf | Delayed | Delay in Construction | Greenfield | https://guardian.ng/property/fg-explains-delays-in-lagos-ibadan-expressway-completion/ | N/A | N/A | Exact Location | 6.58 | 3.3805
Colombia | Chemesky Wind Farm (100MW) | 99MW Chemesky Wind Farm | Energy | Electricity | Electricity generation | No | covid-19, etc(environment) | supply chain | Transmission line delayed |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | https://www.portafolio.co/economia/sector-energia-hay-demoras-en-los-proyectos-clave-de-colombia-548545 | N/A | N/A | City | 11.38 | -72.2397
India | Four-lane Trichy-Kallagam section of NH 227 | Four-laning of NH-227 (Trichy-Kallagam), Four-laning of Trichy to Kallagam section of NH-227 | Transport | Roads | Highway | No | covid-19, monetary issue | labor shortage | The National Highways Authority of India (NHAI) has stopped all ongoing road projects worth more than Rs 17,000 crore in the state following the complete lockdown of the country to fight Covid-19 outbreak. |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://timesofindia.indiatimes.com/city/chennai/27-03-ch-covid-19-stalls-rs-17000-cr-road-projects-in-tn/articleshow/74855152.cms | N/A | N/A | City | 11.0312 | 78.9884
Brazil | 126MW Jaguatirica II thermoelectric plant | 132.3MW UTE Jaguatirica II thermal power plant | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.roraima1.com.br/2020/03/29/coronavirus-atrapalha-obra-de-termeletrica-em-roraima/ | N/A | N/A | Exact Location | 2.9635 | -60.6805
Brazil | 1,400MW Angra-3 nuclear power plant | N/A | Energy | Electricity | Electricity generation | No | monetary issue | N/A | Lower Demand Projection |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://www.devdiscourse.com/article/international/1062323-covid-19-to-delay-brazil-nuclear-plant--eletronuclear | N/A | N/A | City | -23.0063 | -44.4595
Ecuador | Villonaco II Wind Farm (55MW) | N/A | Energy | Electricity | Electricity generation | No | covid-19 | others | Tender Delayed |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | https://renewablesnow.com/news/ecuadors-tender-for-wind-solar-concessions-postponed-again-due-to-covid-19-706222/ | Resumed | https://renewablesnow.com/news/final-bidders-emerge-in-ecuadors-310-mw-solar-wind-tender-717244/ | City | -4.0079 | -79.2111
India | ACME 600 MW Solar project in Rajasthan | N/A | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Outbreak of Covid-19 and its adverse impact on manufacturing facilities of suppliers |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://economictimes.indiatimes.com/small-biz/productline/power-generation/acme-says-cant-supply-cheapest-solar-power/re_show/75886561.cms | N/A | N/A | City | 26.3638 | 64.8592
Ecuador | Villonaco III Wind Farm (55MW) | N/A | Energy | Electricity | Electricity generation | No | covid-19 | others | Tender Delayed |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://renewablesnow.com/news/ecuadors-tender-for-wind-solar-concessions-postponed-again-due-to-covid-19-706222/ | Resumed | https://renewablesnow.com/news/final-bidders-emerge-in-ecuadors-310-mw-solar-wind-tender-717244/ | City | -4.0008 | -79.2592
Albania | Vlora airport construction | Vlora airport | Transport | Airports | Runway and terminal | No | monetary issue | N/A | Tender Delayed |  |  |  | 2020 | March | https://exit.al/en/2020/02/25/ebrd-to-finance-construction-of-vlora-airport/ | Delayed | Delay before Construction | Greenfield | https://www.tiranatimes.com/?p=145028 | Resumed | https://www.intellinews.com/tender-process-for-vlora-airport-in-albania-to-resume-soon-182432/ | Exact Location | 40.479 | 19.4736
Zambia | Bweengwa thermal power plant | Bweengwa River Geothermal Project | Energy | Electricity | Electricity generation | No | covid-19 | others | Due to the disruptive COVID-19, Kalahari Geo’s operations in Bweengwa have almost ground to a halt |  |  |  | 2020 | March | https://repp.energy/project/geothermal-project-bweengwa-zambia/ | Delayed | Delay in Construction | Greenfield | https://geothermalresourcescouncil.blogspot.com/2019/07/zambia-geothermal.html | Resumed | https://www.greenbuildingafrica.co.za/zambia-exploratory-drilling-for-15mw-geothermal-plant-continues/ | City | -16.0982 | 27.1201
Albania | 140 megawatt (MW) photovoltaic park in Albania | 140 megawatt (MW) solar power park in Karavasta | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Tender Delayed |  |  |  | 2020 | May | https://www.pv-magazine.com/2020/05/28/albanias-140-mw-pv-tender-concludes-with-final-price-of-e0-02489-kwh/ | Delayed | Delay before Construction | Greenfield | https://www.reuters.com/article/solar-albania-voltalia/frances-voltalia-wins-albanian-solar-park-contract-idUSL8N2D944U | Resumed | https://www.pv-magazine.com/2020/05/28/albanias-140-mw-pv-tender-concludes-with-final-price-of-e0-02489-kwh/ | City | 40.873 | 19.4858
Vietnam | Hanoi urban railway | Nhon-Hanoi Railway Station metro line | Transport | Railways | Local Passenger/Light rail | No | covid-19, technical issue | labor shortage | Travel limit and shipping disruption |  |  |  | 2008 | May | N/A | Delayed | Delay in Construction | Greenfield | https://english.thesaigontimes.vn/76542/launch-date-for-hanoi-urban-railway-remain | Resumed | https://thailand-construction.com/chinese-experts-resume-delayed-work-on-vietnams-hanoi-metro-line/ | City | 21.025 | 105.8411
India | Kolkata Metro Railway East-West project | Kolkata East West Metro | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://www.newindianexpress.com/cities/kolkata/2020/jul/14/e-w-metro-corridor-work-affected-after-labourers-test-covid-19-positive-in-kolkata-2169608.html | Resumed | https://www.ndtv.com/india-news/coronavirus-india-kolkata-east-west-metro-corridor-work-to-recommence-soon-official-2222606 | City | 22.5502 | 88.3303
Vietnam | Thai Binh 2 Thermal Power | N/A | Energy | Electricity | Electricity generation | No | monetary issue | N/A | PetroVietnam said project difficulties include the fact that PVC has not had experience acting as an EPC contractor for thermal power plants. Inability to pay for completed works and sub-contractors is also a challenge. |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://vietnamnews.vn/economy/483334/moit-proposes-to-resolve-thai-binh-2-power-plants-difficulties.html#:~:text=2%20trillion%2C%20accounting%20for%2082,was%20delayed%20by%2055%20months. | N/A | N/A | City | 20.4449 | 106.3371
Indonesia | MRT Jakarta phase 2 | MRT Jakarta phase 2 | Transport | Railways | Local Passenger/Light rail | No | covid-19, capital issue(labor shortage) | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | 2010 | May | N/A | Delayed | Delay in Construction | Greenfield | https://www.thejakartapost.com/news/2020/05/01/mrt-jakarta-delays-phase-2-construction-amid-covid-19-outbreak.html | Resumed | https://www.thejakartapost.com/news/2020/06/22/mrt-jakarta-commences-phase-2-construction-amid-covid-19-outbreak.html | City | -6.1922 | 106.8232
Ecuador | El Aromo Solar project | 200MW El Aromo solar PV project | Energy | Electricity | Electricity generation | No | covid-19 | others | Tender Delayed |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | https://renewablesnow.com/news/ecuadors-tender-for-wind-solar-concessions-postponed-again-due-to-covid-19-706222/ | Resumed | https://www.solarpack.es/en/solarpack-wins-20-year-long-ppa-contract-in-ecuador-for-258-mw-solar-pv-project/ | City | -1.065 | -80.7767
India | Rangit Stage IV Hydroproject in Sikkim | N/A | Energy | Electricity | Electricity generation | No | covid-19, capital issue | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://m.economictimes.com/industry/energy/power/lockdown-stalled-nclt-clearance-for-rangit-stage-iv-hydroproject-in-sikkim/amp_articleshow/75532876.cms | N/A | N/A | City | 27.3415 | 88.4122
India | Rohtang tunnel(Atal tunnel) | Rohtang tunnel | Transport | Roads | Highway and tunnel | No | covid-19, environmental issue | others | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://www.thehindu.com/news/national/coronavirus-lockdown-bro-opens-rohtang-pass-3-weeks-in-advance/article31432921.ece | Resumed | https://economictimes.indiatimes.com/news/defence/bro-begins-work-in-rohtang-tunnel-after-brief-suspension-due-to-coronavirus/articleshow/75556894.cms?from=mdr | City | 32.3997 | 77.1486
Philippines | Skyway Extension Project | N/A | Transport | Roads | Local Passenger/Light rail | No | covid-19, capital issue | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://www.bworldonline.com/skyway-extension-faces-delay-on-pandemic-lockdown/ | Resumed | https://www.pna.gov.ph/articles/1102839 | City | 14.5382 | 121.0178
Russian Federation | Berezovskaya 3 plant | Berozovskaya GRES unit 3 | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | May | N/A | Delayed | Delay in Operation | Greenfield | https://www.iea-coal.org/uniper-extends-delay-to-restart-of-russian-coal-fired-plant/ | N/A | N/A | City | 55.5794 | 89.0725
South Africa | James Kleynhans Treatment | N/A | Water and sewerage | Treatment plant | Portable water and sewerage treatment | No | covid-19, monetary issue | others | Gov't Budget Reallocation / Regulatory Changes |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://www.news24.com/news24/SouthAfrica/News/coronavirus-shifting-funds-to-respond-to-pandemic-will-prolong-makhanda-water-crisis-20200430 | N/A | N/A | City | -33.3107 | 26.5256
Mexico | Costa Azul | Costa Azul natural gas export project | Energy | Natural Gas | Natural gas transmission | No | covid-19, capital issue | others | Lower Demand Projection |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | https://ieefa.org/the-financial-prospects-for-liquefied-natural-gas-lng-%E2%80%92-once-one-of-the-globes-hottest-energy-commodities-seem-to-be-imploding-before-our-eyes-in-the-most-recent-step-i/ | N/A | N/A | City | 32.001 | -116.8341
Brazil | Linhao de Tucurui Transmission Line | Tucuruí transmission line | Energy | Electricity | Electricity transmission | No | covid-19, legal issue | others | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay before Construction | Greenfield | https://folhabv.com.br/noticia/CIDADES/Capital/Construcao-do-Linhao-de-Tucurui-tem-novo-calendario/68729 | N/A | N/A | City | -3.7752 | -49.6762
Serbia | Belgrade river port | Bergrade river port | Transport | Ports | Other | No | covid-19, technical issue | supply chain | two-month delay in the planned implementation of geotechnical and bathymetric surveys, |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://seenews.com/news/serbia-delays-start-of-new-belgrade-river-port-construction-to-2022-698121 | N/A | N/A | City | 44.8143 | 20.4403
Mexico | Maya Train project | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19, political issue | others | Violation of the indigenous people's constitutional right to health protection |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://mexiconewsdaily.com/news/new-injunction-halts-maya-train-construction-in-3-chiapas-municipalities/ | N/A | N/A | City | 20.1978 | -87.5027
Indonesia | Serang-Panimbang toll road | N/A | Transport | Roads | Local Passenger/Light rail | No | covid-19, political issue | preemptive action | Non-availability of labourers due to Lockdown measure |  |  |  | 2017 | May | https://www.kdi.re.kr/common/seminar_down.jsp?fno=5sDLotstSh858iD8fVLr7w%3D%3D&fty=IKKLJlukyUcpG4EmUThiYg%3D%3D | Delayed | Delay in Construction | Greenfield | https://finance.detik.com/infrastruktur/d-4987481/proyek-konstruksi-tol-serang-panimbang-disetop | Resumed | https://www.wikabitumen.co.id/page/detailnews/serang--panimbang-toll-project-latest-update | City | -6.119 | 106.1709
India | Kanpur Metro | Kanpur Metro | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2020-08-01 | May | https://www.eib.org/en/projects/pipelines/all/20190849 | Delayed | Delay in Construction | Greenfield | https://www.livemint.com/news/india/kanpur-metro-construction-work-resumes-amid-lockdown-3-0-11589020714033.html | Resumed | https://www.livemint.com/news/india/kanpur-metro-construction-work-resumes-amid-lockdown-3-0-11589020714033.html | City | 26.4894 | 80.2819
India | Majerhat bridge | N/A | Transport | Roads | Highway | No | covid-19 | labor shortage | Gov't safety suspension |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://timesofindia.indiatimes.com/city/kolkata/after-long-break-majerhat-bridge-work-resumes/articleshow/75636979.cms | Resumed | https://timesofindia.indiatimes.com/city/kolkata/after-long-break-majerhat-bridge-work-resumes/articleshow/75636979.cms | City | 22.516 | 88.3225
Philippines | BGC-Ortigas Center Link Road | Bonifacio Global City-Ortigas Center Road | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://malaya.com.ph/index.php/news_business/key-infra-projects-resume-construction/ | Resumed | https://malaya.com.ph/index.php/news_business/key-infra-projects-resume-construction/ | City | 14.5667 | 121.0551
Nepal | Chilime Trishuli 220 KV transmission line | N/A | Energy | Electricity | Electricity transmission | No | monetary issue | N/A | Travel limit and shipping disruption |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://myrepublica.nagariknetwork.com/news/coronavirus-affects-construction-of-chilime-trishuli-transmission-line/ | N/A | N/A | City | 28.1861 | 85.3003
India | Tanakpur-Pithoragarh stretch of the Chardham all-weather road | Chardham highway project | Transport | Roads | Highway | No | covid-19, capital issue | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | March | N/A | Delayed | Delay in Construction | Greenfield | https://www.financialexpress.com/infrastructure/roadways/chardham-all-weather-road-project-tanakpur-pithoragarh-stretch-to-be-delayed-due-to-covid-19-lockdown/1931298/ | N/A | N/A | City | 30.772 | 79.496
India | 624 MW Kiru hydroelectric project | Kiru Hydro Electric Project | Energy | Electricity | Electricity generation | No | covid-19, capital issue, legal issue | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | April | N/A | Delayed | Delay in Construction | Greenfield | https://www.dailyexcelsior.com/finally-work-on-624-mw-kiru-hep-to-begin-next-month/ | Resumed | https://www.dailyexcelsior.com/finally-work-on-624-mw-kiru-hep-to-begin-next-month/ | City | 33.2595 | 76.1858
Philippines | Estrella-Pantaleon Bridge Project | Rockwell Bridge | Transport | Roads | Bridge | No | covid-19 | others | Covid-19 |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://www.philstar.com/headlines/2020/05/17/2014564/dpwh-resumes-work-ncr-flagship-projects | Resumed | https://mb.com.ph/2020/07/25/2-china-funded-bridges-in-metro-manila-set-for-completion/ | Exact Location | 14.5638 | 121.0388
India | Mumbai Metro lines 2A and 7 | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Covid-19 and its subsequent lockdown |  |  |  | N/A | May | N/A | Delayed | Delay in Operation | Greenfield | https://www.freepressjournal.in/mumbai/mumbai-metro-lines-2a-and-7-will-be-operational-in-2021 | Resumed | https://www.thehindu.com/news/cities/mumbai/work-on-all-metro-routes-resumes-after-months-break/article31392293.ece | Exact Location | 19.2504 | 72.8595
Mexico | El Llano Solar project | Neoen - El Llano solar project | Energy | Electricity | Electricity generation and transmission | No | covid-19 | others | Due to reduced electricity demand because of the pandemic |  |  |  | 2019 | June | https://www.astrisfinance.com/news//march-2019-astris-closes-two-solar-pv-deals-in-mexico-and-argentina-with-neoen | Delayed | Delay in Operation | Greenfield | http://taiyangnews.info/markets/neoen-mexico-pv-project-off-line | N/A | N/A | City | 22.0094 | -102.4043
Jamaica | Norman Manley International Airport (NMIA) | N/A | Transport | Airports | Runway and terminal | No | covid-19 | others | Covid 19 |  |  |  | 2019 | May | http://dbankjm.com/completed-transactions-2/norman-manley-international-airport-nmia/ | Delayed | Delay in Operation | Brownfield | https://jis.gov.jm/new-airport-development-projects/ | N/A | N/A | Exact Location | 17.9375 | -76.7798
Philippines | Binondo-Intramuros Bridge | N/A | Transport | Roads | Bridge | No | covid-19 | labor shortage | Enhanced community quarantine (ECQ) |  |  |  | N/A | June | N/A | Delayed | Delay in Construction | Greenfield | https://www.philstar.com/headlines/2020/05/17/2014564/dpwh-resumes-work-ncr-flagship-projects | Resumed | https://www.topgear.com.ph/news/motoring-news/dpwh-estrella-pantaleon-binondo-intramuros-bridge-project-a962-20200727 | Exact Location | 14.5984 | 120.9713
India | Elevated Railway Line on the Rohtak – Gohana stretch | Rohtak-Gohana Railway line | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://www.tribuneindia.com/news/haryana/nations-first-elevated-railway-track-project-misses-deadline-for-third-time-108929 | N/A | N/A | City | 28.91 | 76.5666
India | 200 megawatts (MW) ACME Solar | N/A | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Land acquisition delays, the coronavirus outbreak (force majeure) |  |  |  | N/A | July | N/A | Canceled | Cancel before Construction | Greenfield | https://www.reuters.com/article/india-solar/citing-covid-uncertainty-indias-acme-solar-cancels-deal-to-supply-power-at-record-low-tariff-idUSL4N2D22TL | N/A | N/A | City | 26.5183 | 73.774
Philippines | NLEX Harbor Link Project | R10 section' segment | Transport | Roads | Highway | No | covid-19 | labor shortage | halted due to government's pronouncement of lockdown |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | Resumed | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | City | 14.6603 | 120.9452
Philippines | Cebu Cordova Link Expressway. | CCLEX project | Transport | Roads | Bridge | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2019 | May | https://cebudailynews.inquirer.net/216052/cclec-6-banks-ink-p19b-loan-for-third-bridge | Delayed | Delay in Construction | Greenfield | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | Resumed | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | City | 10.2999 | 123.9108
Philippines | Cavite-Laguna Expressway | CALAX project | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2019 | May | https://pia.gov.ph/news/articles/1016837 | Delayed | Delay in Construction | Greenfield | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | Resumed | https://manilastandard.net/business/corporate/325095/mptc-resumes-construction-of-cavite-laguna-expressway.html | City | 14.3344 | 121.0707
Philippines | North Luzon Expressway (NLEX) Connector | NLEX–SLEX Connector Road Project | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | Resumed | https://www.gmanetwork.com/news/money/companies/739052/nlex-corp-resumes-works-on-major-infra-projects/story/ | City | 14.7555 | 121.0458
Philippines | Subic Freeport Expressway (SFEX) | Subic–Tipo Expressway / NLEx Segment 7 | Transport | Roads | Highway | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Brownfield | https://www.autodeal.com.ph/articles/car-news-philippines/subic-freeport-expressway-expansion-project-now-50-complete | Resumed | https://www.autodeal.com.ph/articles/car-news-philippines/subic-freeport-expressway-expansion-project-now-50-complete | City | 14.8204 | 120.3033
Malaysia | Rapid Transit System(RTS) Link | Light Rail Transit (LRT) system | Transport | Railways | Local Passenger/Light rail | Yes | political issue | N/A | New government to review the deal |  |  |  | N/A | May | N/A | Delayed | Delay before Construction | Greenfield | https://www.nst.com.my/news/nation/2020/07/612747/malaysia-singapore-prime-ministers-officially-launch-rts-project | Resumed | https://www.nst.com.my/news/nation/2020/07/612747/malaysia-singapore-prime-ministers-officially-launch-rts-project | City | 1.4668 | 103.7635
Malaysia | Kuala Lumpur-Singapore high-speed rail | N/A | Transport | Railways | Local Passenger/Light rail | Yes | covid-19 | others | Covid-19 |  |  |  | N/A | May | N/A | Canceled | Cancel before Construction | Greenfield | https://www.straitstimes.com/singapore/politics/kl-singapore-high-speed-rail-terminated-after-singapore-and-malaysia-fail-to | N/A | N/A | City | 3.3966 | 101.4521
Mexico | 25 MW Los Humeros III Phase B geothermal unit | N/A | Energy | Electricity | Electricity generation | No | covid-19 | others | Gov't Budget Reallocation / Regulatory Changes |  |  |  | N/A | May | N/A | Canceled | Cancel before Construction | Greenfield | https://www.thinkgeoenergy.com/cfe-cancels-tender-for-development-of-los-humeros-geothermal-plant-in-puebla-mexico/ | N/A | N/A | Exact Location | 19.6845 | -97.4497
Russian Federation | Sheremetyevo Airport Terminal C Stage 2 | Sheremetyevo Airport Terminal C2 | Transport | Airports | Runway and terminal | No | covid-19 | others | Lower Demand Projection |  |  |  | N/A | July | N/A | Delayed | Delay in Construction | Brownfield | https://www.intellinews.com/index.php/moscow-s-sheremetyevo-airport-postpones-new-terminal-on-covid-19-187750/?source=russia | N/A | N/A | Exact Location | 55.9788 | 37.4118
Serbia | Kolubara B Thermal Plant | N/A | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | Due to spread of COVID-19 |  |  |  | 2019 | July | https://serbia-energy.eu/the-construction-project-of-the-kolubara-b-tpp-serbia-on-hold-for-36-years-here-is-what-the-spatial-plan-development-study-envisages/ | Delayed | Delay before Construction | Brownfield | https://serbia-energy.eu/serbia-tpp-kolubara-b-spatial-plan-public-debate-postponed/ | N/A | N/A | City | 44.4152 | 20.2182
Gabon | Transgabonaise Highway | N/A | Transport | Roads | Highway and tunnel | No | covid-19 | others | Coronavirus Pandemic |  |  |  | 2019 | July | https://cemac-eco.finance/framework-for-transgabonaise-highway-outlined-project-to-commence-soon/ | Delayed | Delay in Construction | Greenfield | https://www.worldhighways.com/wh10/news/gabon-highway-work-starting | Resumed | https://www.globalconstructionreview.com/news/gabon-begins-work-1bn-transgabonaise-motorway/ | City | 0.41597 | 9.4669
Vietnam | Duyen Hai-2 power station | Duyen Hai 2 Thermal Power Plant | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage, preemptive action, | Foreign workers not allowed to enter due to Covid-19 |  |  |  | 2017 | July | https://ppi.worldbank.org/en/snapshots/project/Duyen-Hai-2-Thermal-Power-Plant-9304 | Delayed | Delay in Construction | Greenfield | baodauthau.vn/dau-tu/covid19-tac-dong-toi-tien-do-nhieu-du-an-dien-128323.html | N/A | N/A | City | 10.3817 | 106.883
Bangladesh | Ramu-Gundum (Myanmar) project | Bangladesh-Myanmar Railway Construction Project / Railway Track from Dohazari to Cox’s Bazar via Ramu and Ramu to Gundum near Myanmar | Transport | Railways | Local Passenger/Light rail | Yes | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2016 | May | https://railway.portal.gov.bd/sites/default/files/files/railway.portal.gov.bd/tenders/5e57d52f_642d_46c5_9340_ba027c7350a5/Signed%20tender%20notice%20CPTU%20format.pdf | Delayed | Delay in Construction | Greenfield | https://www.newagebd.net/article/112937/bangladesh-myanmar-railway-project-goes-slow | N/A | N/A | City | 21.4434 | 92.0994
India | Indira Gandhi International Airport Expansion project | N/A | Transport | Airports | Runway and terminal | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2019 | August | https://www.business-standard.com/article/pti-stories/gmr-to-raise-usd-350-million-via-bonds-for-delhi-airport-119050700192_1.html | Delayed | Delay in Construction | Brownfield | https://timesofindia.indiatimes.com/city/delhi/terminal-delay-covid-19-latest-of-setbacks-in-igis-expansion-plans/articleshow/77339324.cms | N/A | N/A | Exact Location | 28.556 | 77.0999
India | 100MW Solar power project at Tamil Nadu | N/A | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | N/A | August | N/A | Delayed | Delay in Construction | Greenfield | https://energy.economictimes.indiatimes.com/news/renewable/india-may-give-reprieve-to-solar-projects-delayed-by-coronavirus-fallout/74200647 | N/A | N/A | City | 8.825 | 77.5674
Bangladesh | Khulna-Mongla railway project | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19, environmental issue | others | Delays in land acquisition, change of consultant in the middle of work, repeated failure in piling, and base grounding alongside the pandemic and rains |  |  |  | N/A | February | N/A | Delayed | Delay in Construction | Greenfield | https://www.dhakatribune.com/bangladesh/nation/2020/08/13/covid-19-persistent-rainfall-continue-to-hinder-much-delayed-khulna-mongla-railway-project | N/A | N/A | City | 22.868 | 89.5325
Ghana | Tema-Akosombo Railways | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Non-availability of labourers due to Lockdown measure |  |  |  | 2017 | August | https://www.tagmydeals.com/Deals/DealData/7352 | Delayed | Delay in Construction | Greenfield | https://www.projectstoday.com/News/Work-on-Tema-Akosombo-railway-project-70-percent-complete | Resumed | https://www.ghanaweb.com/GhanaHomePage/business/Tema-Akosombo-railway-project-progresses-despite-coronavirus-pandemic-1034311 | City | 5.7337 | 0.029206
Myanmar | Yangon Elevated Expressway | N/A | Transport | Roads | Local Passenger/Light rail | No | covid-19 | others | Tender Delayed |  |  |  | N/A | April | N/A | Delayed | Delay before Construction | Greenfield | https://thailand-construction.com/myanmars-yangon-elevated-expressway-project-delayed-for-two-months-due-to-covid-19/ | N/A | N/A | City | 16.9533 | 96.1417
Bosnia and Herzegovina | Bihac Airport | N/A | Transport | Airports | Runway and terminal | No | covid-19 | others | Gov't Budget Reallocation / Regulatory Changes |  |  |  | N/A | May | N/A | Delayed | Delay in Construction | Greenfield | http://www.sarajevotimes.com/166286-2/ | N/A | N/A | Exact Location | 44.8109 | 15.9025
Bosnia and Herzegovina | Banja Luka-Prijedor motorway PPP | N/A | Transport | Roads | Highway and tunnel | No | covid-19 | others | Government of the Republika Srpska again gave them extra time, justifying everything with the corona virus. |  |  |  | N/A | August | N/A | Delayed | Delay before Construction | Greenfield | https://tekdeeps.com/the-parcelling-plan-for-the-banja-luka-prijedor-highway-is-two-years-late/ | N/A | N/A | City | 44.7766 | 17.2007
Mexico | General Francisco Javier Mina International Airport (Tampico Airport) | N/A | Transport | Airports | Runway and terminal | No | covid-19 | others | Stopped the investment plans for airports |  |  |  | N/A | August | N/A | Delayed | Delay before Construction | Brownfield | https://mexico-now.com/covid-19-stopped-investment-in-the-tampico-international-airport/ | N/A | N/A | Exact Location | 22.2915 | -97.8648
Mongolia | Mongolia-China coal railway | Haoji Railway | Transport | Railways | Freight | Yes | covid-19 | labor shortage | Travel limit and shipping disruption |  |  |  | 2016 | September | https://www.bloomberg.com/news/articles/2016-02-23/mongolia-seeks-1-3-billion-from-china-to-complete-coal-railway | Delayed | Delay in Construction | Greenfield | http://www.sxcoal.com/news/4615926/info/en | N/A | N/A | City | 43.6609 | 105.4239
Nigeria | Second Niger bridge | N/A | Transport | Roads | Other | No | covid-19 | labor shortage | Travel limit and shipping disruption |  |  |  | 2018 | September | https://punchng.com/2nd-niger-bridge-fg-investors-talks-collapse-govt-bears-n250bn-cost/ | Delayed | Delay in Construction | Greenfield | https://www.sunnewsonline.com/2nd-niger-bridge-covid-19-disrupts-completion-date/ | N/A | N/A | Exact Location | 6.1197 | 6.7554
India | Mumbai Coastal Tunnel Work | N/A | Transport | Roads | Highway and tunnel | No | covid-19, etc | labor shortage | Travel limit and shipping disruption |  |  |  | 2018 | September | https://www.thehindu.com/news/cities/mumbai/coastal-road-contractors-finalised-at-high-rates/article25010651.ece | Delayed | Delay in Construction | Greenfield | https://timesofindia.indiatimes.com/city/mumbai/tensions-with-china-covid-hit-mumbai-coastal-tunnel-work/articleshow/77968880.cms | Resumed | https://www.hindustantimes.com/cities/mumbai-news/tunnelling-for-mumbai-s-coastal-road-set-to-begin-100-workers-to-drill-24x7-101610304343718.html | City | 18.9571 | 72.7989
Nepal | 68km Jayanagar-Bardibas railway project | Jayanagar-Janakpur-Bardibas railway | Transport | Railways | Local Passenger/Light rail | Yes | covid-19 | labor shortage, supply chain | Travel limit and shipping disruption |  |  |  | N/A | September | N/A | Delayed | Delay in Construction | Greenfield | https://timesofindia.indiatimes.com/city/patna/covid-19-pandemic-brake-on-india-nepal-rly-project-work/articleshow/77708708.cms | N/A | N/A | City | 26.987 | 85.895
India | Ahmedabad-Mumbai high-speed rail corridor | N/A | Transport | Railways | Local Passenger/Light rail | No | covid-19 | others | Tender Delayed |  |  |  | N/A | August | N/A | Delayed | Delay before Construction | Greenfield | https://thewire.in/government/ahmedabad-mumbai-bullet-train-project-may-face-five-year-delay | N/A | N/A | City | 23.0268 | 72.6008
Myanmar | Dala bridge | Yangon-Dala bridge | Transport | Roads | Bridge | No | covid-19 | labor shortage, supply chain | Non-availability of labourers due to Lockdown measure |  |  |  | 2020 | September | http://myanmarcs.focuscoregroup.com/loan-approved-for-construction-of-yangon-dala-bridge/ | Delayed | Delay in Construction | Greenfield | https://consult-myanmar.com/2020/09/18/dala-bridge-construction-suspended-over-covid-19-cases/ | N/A | N/A | Exact Location | 16.8398 | 96.2066
Nepal | Solu corridor transmission line | N/A | Energy | Electricity | Electricity transmission | No | covid-19 | supply chain | Travel limit and shipping disruption |  |  |  | N/A | September | N/A | Delayed | Delay in Construction | Greenfield | https://kathmandupost.com/money/2020/09/14/solu-corridor-transmission-line-project-deadline-extended-for-the-fourth-time | Resumed | https://myrepublica.nagariknetwork.com/news/solu-corridor-transmission-line-project-to-resume-work/ | City | 27.4449 | 86.575
Croatia | N/A | Peljesac Bridge Project | Transport | Roads | Bridge | No | covid-19 | supply chain | production delays in China factories will impact the Pelješac Bridge completion date |  |  |  | N/A | September | N/A | Delayed | Delay in Construction | Greenfield | https://dailycroatia.com/2020/08/07/peljesac-bridge-delayed-videos/ | Resumed | https://www.croatiaweek.com/peljesac-bridge-construction-going-according-to-plan/ | Exact Location | 42.9407 | 17.5432
Canada | N/A | The LNG Canada project | Energy | Natural Gas | Natural gas transmission | No | covid-19, capital issue | labor shortage | suffered a delay after the developer was forced to reduce by half the amount of staff at the construction site in Kitimat, British Columbia, including workers flying in on rotation, as a precaution against the virus. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.gasworld.com/covid-19-triggers-delays-in-lng-projects/2019106.article | N/A | N/A | Exact Location | 54.0294 | -128.6849
Australia | N/A | NorthConnex tunnel | Transport | Roads | Highway and tunnel | No | covid-19, technical issue | labor shortage | international specialists unable to enter Australia for the commissioning stage |  |  |  | 2015 |  | https://investment.infrastructure.gov.au/projects/ProjectDetails.aspx?Project_id=034643-09NSW-NP | Delayed | Delay in Operation | Greenfield | https://www.smh.com.au/national/nsw/northconnex-s-final-weeks-inside-the-race-to-open-australia-s-deepest-road-tunnel-20200927-p55zos.html | N/A | N/A | Exact Location | -33.7439 | 151.0348
Australia | N/A | Kennedy renewable energy farm | Energy | Electricity | Electricity generation and transmission | No | monetary issue | N/A | investor Federation Asset Management is negotiating to buy the company's outstanding stock |  |  |  | 2017 |  | https://www.ippjournal.com/news/kennedy-hybrid-project-reaches-financial-closure | Delayed | Delay in Operation | Greenfield | https://www.abc.net.au/news/rural/2020-03-04/renewable-profits-slashed-amid-national-transmission-failure/12021082 | N/A | N/A | Exact Location | -20.7657 | 145.0167
United Kingdom | N/A | Gibraltar Airport Road and Tunnel Project | Transport | Roads | Highway and tunnel | No | monetary issue, legal issue | N/A | problems and delays have been constant, which have included a legal battle in court |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.reachextra.com/gibraltar-airport-tunnel/ | Resumed | https://www.reachextra.com/gibraltar-airport-tunnel/ | Exact Location | 36.1537 | -5.3473
United Kingdom | N/A | 50MW Kincardine Offshore Wind Farm | Energy | Electricity | Electricity generation | No | covid-19 | supply chain | supply chain and construction setbacks caused by the COVID-19 pandemic |  |  |  | 2020 |  | https://renews.biz/61238/kincardine-floater-secures-380m-green-bond/ | Delayed | Delay in Construction | Greenfield | https://www.4coffshore.com/news/covid-19-pushes-back-kincardine-commissioning-nid19312.html | N/A | N/A | City | 57.2265 | -1.9732
Norway, Denmark, Poland | N/A | Baltic Pipe Project | Energy | Natural Gas | Other | Yes | covid-19, environmental issues | others | delayed by rains and the coronavirus |  |  |  | 2018 |  | https://www.baltic-pipe.eu/about/financial-support-eu/ | Delayed | Delay in Construction | Greenfield | https://biznesalert.com/baltic-pipe-delay-nuclear-energy-three-seas-summit/ | N/A | N/A | City | 59.0831 | 17.3332
Canada | N/A | Nation Rise Wind Farm | Energy | Electricity | Electricity generation | No | environmental issue | N/A | pose a threat to nearby bat populations |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://ottawacitizen.com/news/local-news/ontario-cancels-nearly-built-200m-wind-farm-over-threat-to-bat-populations | Resumed | https://globalnews.ca/news/6943301/ontario-court-government-eastern-wind-farm/ | City | 45.1726 | -75.1112
Canada | N/A | Woodfibre LNG project | Energy | Natural Gas | Natural gas transmission | No | covid-19, capital issue | supply chain | substantial construction expected to start this summer won't take place until after the middle of next year |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.cbc.ca/news/canada/british-columbia/covid-19-pandemic-woodfibre-lng-project-1.5510418 | N/A | N/A | City | 49.7053 | -123.1556
United Kingdom | N/A | Road Infrastructure Rehabilitation Project | Transport | Roads | Highway | No | covid-19 | supply chain | essential supplies have been held up, impacting the previously projected completion date of September 2020. |  |  |  | 2017 |  | Second Road Infrastructure Rehabilitation Project ¦ Caribbean Development Bank (caribank.org) | Delayed | Delay in Construction | Greenfield | https://antiguaobserver.com/roadworks-project-set-back-by-covid-19/ | N/A | N/A | City | 17.1276 | -61.8461
UAE, Saudi Arabia, Oman, Kuwait, Bahrain | N/A | Gulf Railway (GCC Railway) | Transport | Railways | Freight and Regional Passenger | Yes | monetary issue | N/A | But GCC financial challenges, including US$ 260 billion in loss resulting from an oil price collapse between 2014 and 2015, and the subsequent failure of the market to recover, delayed infrastructure spending on the Gulf Railway project. |  |  |  | 2009 |  | https://gulfnews.com/business/gcc-railway-project-estimated-to-cost-154b-1.1292154 | Delayed | Delay in Construction | Greenfield | https://insidearabia.com/gcc-railway-project-held-up-by-financial-problems-and-qatars-exclusion/ | Resumed | https://www.arabianbusiness.com/transport/403177-kuwait-said-to-start-work-on-111km-railway-project | City | 24.0386 | 53.5285
Singapore, Malaysia | N/A | 350km HSR project | Transport | Railways | Regional Passenger | Yes | political issue | N/A | the election of Malaysian Prime Minister Mahathir Mohamad two years later. Mahathir said he wanted to scrap the project as part of an effort to review major infrastructure projects approved by his scandal-tainted predecessor in a bid to cut the country’s debt. Construction was then suspended for two years at Malaysia’s request, with plans to commence service in 2031. The project was terminated after a final deadline on December 31, and after both governments failed to reach an agreement over changes proposed by Malaysia. |  |  |  | N/A |  | N/A | Cancelled | Cancel in construction | Greenfield | https://english.alarabiya.net/News/world/2021/01/01/Singapore-and-Malaysia-abandon-high-speed-rail-plan-after-delays | N/A | N/A | City | 1.3531 | 103.8205
Australia | N/A | West Gate Tunnel project | Transport | Roads | Highway and tunnel | No | political issue, environmental issue | N/A | Tolling giant Transurban told investors on Thursday the project won't be completed by 2023, due to an ongoing dispute over where to dump tonnes of contaminated soil. tunnelling was delayed in 2019 after soil contaminated with PFAS was discovered at the construction site. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://au.news.yahoo.com/west-gate-tunnel-project-delayed-013753665.html | N/A | N/A | Exact Location | -37.7756 | 144.937
Slovenia | N/A | Karawanks Tunnel | Transport | Others | Highway and tunnel | Yes | covid-19 | supply chain | Difficulties with the supply of materials and the housing of workers |  |  |  | 2020 |  | https://seenews.com/news/cengiz-suspends-construction-of-slovenias-karavanke-tunnel-over-coronavirus-report-692472 | Delayed | Delay in Construction | Greenfield | https://seenews.com/news/cengiz-suspends-construction-of-slovenias-karavanke-tunnel-over-coronavirus-report-692472 | Resumed | https://seenews.com/news/cengiz-starts-excavating-second-pipe-of-slovenias-karavanke-tunnel-711445 | Exact Location | 46.5204 | 14.0229
Mozambique | N/A | Total Mozambique LNG project | Energy | Natural Gas | Natural gas transmission | No | political issue | N/A | Mozambique's jihadist violence has forced the French energy firm Total to suspend work |  |  |  | 2019 |  | https://www.mzlng.total.com/en/about-mozambique-liquefied-natural-gas-project | Cancelled | Cancel in Construction | Greenfield | https://accesswdun.com/article/2021/1/967804 | N/A | N/A | Exact Location | -10.0291 | 40.523
Canada | N/A | Trans Mountain pipeline expansion project (TMX) | Energy | Natural Gas | Natural gas transmission | No | covid-19 | preemptive action | Significant health concerns have been raised |  |  |  | 2019 |  | https://nationalpost.com/news/politics/liberals-approve-12b-trans-mountain-expansion-project-offering-some-relief-to-oil-rich-provinces | Delayed | Delay in Construction | Greenfield | https://www.nationalobserver.com/2020/05/11/opinion/pipeline-projects-pandemic-and-question-journalists-fail-ask | Resumed | https://www.cbc.ca/news/politics/trans-mountain-tmx-pipeline-1.5905797 | Exact Location | 49.2885 | -122.954
Australia | N/A | Melbourne Metro Tunnel Project | Transport | Railways | Local Passenger/Light rail | No | covid-19 | supply chain | Due to the late arrival of the first of the machines from China |  |  |  | 2017 |  | https://www.inframationgroup.com/aus-nz-john-laing-joins-melbourne-metro-tunnel-ppp-jv | Delayed | Delay in Construction | Greenfield | https://www.theage.com.au/national/victoria/metro-tunnel-digging-running-seven-months-late-20201115-p56epy.html | Resumed | https://www.theage.com.au/national/victoria/commuters-warned-of-may-misery-with-replacement-buses-ready-to-roll-20190430-p51iie.html | Exact Location | -37.8144 | 144.9657
Philippines | N/A | 50-MW Bulacan solar project | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | Chinese engineers contracted by MGen for the Bulacan solar project have been unable to reach the site due to a Philippines government travel ban to and from China, Hong Kong and Macau, aimed at halting the spread of the virus. |  |  |  | 2015 |  | https://manilastandard.net/business/power-technology/343857/50-mw-bulacan-solar-project-to-open-in-q1.html | Delayed | Delay in Construction | Greenfield | https://www.pv-tech.org/coronavirus-delays-135mw-of-solar-by-philippines-utility/ | Resumed | https://businessmirror.com.ph/2020/04/29/mgen-gets-ok-to-resume-work-on-bulacan-solar-power-project/ | Exact Location | 15.0071 | 121.0297
United Kingdom (기사 내용은 failed 되었다고 말하고 있음) | N/A | Western HVDC Link project | Energy | Electricity | Electricity transmission | Yes | technical issue | N/A | Completion of the £1bn Western HVDC link, a subsea electricity cable linking Hunterston in Scotland with Deeside in North Wales, has been delayed until 2017-18 due to cable manufacturing problems. |  |  |  | N/A |  | N/A | Cancelled | Delay in Construction | Greenfield | https://www.newpower.info/2017/07/western-hvdc-link-completion-delayed-until-next-year/ | Resumed | https://www.theregister.com/2020/01/29/ofgem_national_grid_scottish_power_subsea_cable/ | City | 55.7211 | -4.8853
Denmark, Germany | N/A | Kriegers Flak Combined Grid Solution system (CGS Project) | Energy | Electricity | Electricity transmission | Yes | covid-19 | others | ongoing movement restrictions for the Swedish team members due to Corona-Pandemic |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.4coffshore.com/news/coronavirus-delays-kriegers-flak-combined-grid-solution-nid17709.html | N/A | N/A | Exact Location | 55.026 | 12.939
United Kingdom | N/A | Montserrat Submarine Fibre Optic Cable Project | ICT | ICT backbone | Submarine cable | No | covid-19 | preemptive action | The installations for the Terrestrial Fibre Cable and the Cable Landing Station delayed by COVID-19 related restrictions are ongoing and should be completed by the middle of August 2020. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.caribbeannewsglobal.com/montserrats-subsea-fibre-optic-cable-project-progresses-steadily/ | Resumed | https://www.caribbeannewsglobal.com/montserrats-subsea-fibre-optic-cable-project-progresses-steadily/ | City | 16.7909 | -62.2106
Canada | N/A | Kitimat LNG Canada project | Energy | Natural Gas | Natural gas transmission | No | covid-19 | preemptive action | In a sign of what may be to come elsewhere, Shell-backed LNG Canada, which began construction in late 2018 of the up to $31 billion facility, is cutting by half the amount of staff at its site in Kitimat, British Columbia, including workers flying in on rotation, it said Tuesday in a message posted on its website. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/031720-slowdown-in-construction-of-new-north-american-liquefaction-supply-expected-amid-outbreak | Resumed | https://www.energyvoice.com/coronavirus/290119/lng-canada-covid-19-screening/ | City | 54.0641 | -128.6373
Belarus | N/A | Belaurs Nuclear Power Plant project | Energy | Electricity | Electricity generation | No | environmental issue | N/A | The first reactor was due to launch in autumn 2018, but was delayed to mid-2019, and then again to autumn 2019, and finally, to January 2020. The timescale was later extended to the second quarter of 2020. |  |  |  | N/A |  | N/A | Delayed | Delay in Operation | Brownfield | https://www.lrt.lt/en/news-in-english/19/1163135/launch-of-belarus-nuclear-plant-near-lithuania-delayed-again | Resumed | https://www.lrt.lt/en/news-in-english/19/1163135/launch-of-belarus-nuclear-plant-near-lithuania-delayed-again | Exact Location | 54.7612 | 26.0926
Canada | N/A | Kugluktuk Hybrid Solar/Diesel Project | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | “However, unpredictable delays due to COVID-19 may be beyond our control,” Pereira said in a statement to Nunatsiaq News. |  |  |  | 2019 |  | https://www.newswire.ca/news-releases/kugluktuk-residents-to-benefit-from-a-cleaner-more-energy-efficient-power-plant-895070346.html | Delayed | Delay in Construction | Brownfield | https://nunatsiaq.com/stories/article/nunavut-power-corp-pushes-kugluktuks-new-power-plant-ahead-by-two-years/ | N/A | N/A | City | 67.828 | -115.0886
Sri Lanka | N/A | East Container Terminal (ECT) | Transport | Ports | Freight | No | political issue | N/A | overturn Sri Lanka’s tripartite agreement to develop Colombo’s East Container Terminal |  |  |  | 2019 |  | https://www.jagranjosh.com/general-knowledge/east-container-terminal-project-1611817385-1 | Canceled | Cancel before Construction | Greenfield | https://www.thehindu.com/opinion/editorial/terminal-declined-the-hindu-editorial-on-sri-lanka-reneging-on-colombo-east-container-terminal/article33762935.ece | Resumed | https://news.slpa.lk/index.php/2020/11/26/port-of-colombo-all-operations-return-to-normal/ | Exact Location | 6.9488 | 79.8413
Chile | N/A | BHP Cerro Colorado copper mine | Others | Others | Other | No | legal issue | N/A | forced to suspend operations at its Cerro Colorado copper mine in water-parched northern Chile after the country’s Supreme Court upheld local indigenous communities’ complaint about the project’s water use. |  |  |  | N/A |  | N/A | Delayed | Delay in Operation | greenfield | https://www.reuters.com/article/chile-mining-bhp/court-ruling-forces-bhp-to-suspend-operations-at-chilean-copper-mine-idUSL1N2JP1JO | N/A | N/A | Exact Location | -19.4282 | -67.1084
Chile | N/A | Enel SpA subsidiary Enel Generación Chile SA Bocamina coal-fired power plant | Energy | Electricity | Electricity generation | No | political issue | N/A | has stopped operations at unit 1 of its Bocamina coal-fired power plant in Chile, three years before the scheduled date |  |  |  | N/A |  | N/A | Canceled | Cancel in Operation | greenfield | https://www.spglobal.com/marketintelligence/en/news-insights/latest-news-headlines/enel-disconnects-chile-coal-fired-unit-3-years-early-61958518 | N/A | N/A | Exact Location | -37.0227 | -73.1657
Romania | N/A | Cernavodă Nuclear Power Plant(C 3&4) | Energy | Electricity | Electricity generation | No | monetary issue | N/A | development plans of C 3&4 with CGN would be dropped |  |  |  | 2014 |  | https://www.nsenergybusiness.com/projects/cernavoda-nuclear-power-plant-expansion/ | Canceled | Cancel before Construction | brownfield | https://balkaninsight.com/2020/05/27/romania-cancels-deal-with-china-to-build-nuclear-reactors/ | N/A | N/A | Exact Location | 44.3183 | 28.059
Chile | N/A | Chacao Channel Bridge | Transport | Roads | Local Passenger/Light rail | No | political issue | N/A | South Korea-based Hyundai Engineering & Construction Co. and the government of Chile have apparently resolved a dispute that temporarily halted construction of the $740-million Chacao Channel Bridge in December. |  |  |  | N/A |  | N/A | Delayed | Delay in construction | greenfield | https://www.enr.com/articles/48715-chilean-bridge-dispute-close-to-resolution | Resumed | https://www.enr.com/articles/48715-chilean-bridge-dispute-close-to-resolution | Exact Location | -41.7959 | -73.5213
Denmark, Germany | N/A | Fehmarn Belt Fixed Link | Transport | Roads | Regional Passenger | Yes | covid-19 | others | Development was deferred by a half year as a result of the COVID-19 pandemic. |  |  |  | 2016 |  | https://www.vanoord.com/en/projects/fehmarn-belt-fixed-link-dredging-and-reclamation-works/ | Delayed | Delay in construction | greenfield | https://www.medicircle.in/medicircle-in-denmark-denmark-approves-start-of-work-for-7-billion-underwater-tunnel-to-germany | Resumed | https://www.medicircle.in/medicircle-in-denmark-denmark-approves-start-of-work-for-7-billion-underwater-tunnel-to-germany | Exact Location | 54.5921 | 11.2976
Cyprus | N/A | Paphos-Polis highway project / A7 motorway | Transport | Roads | Local Passenger/Light rail | No | political issue | N/A | As he understood it, construction of the road would be delayed by a few months. |  |  |  | N/A |  | N/A | Delayed | Delay in construction | brownfield | https://cyprus-mail.com/2020/05/13/polis-mayor-warns-of-dynamic-measures-is-road-to-paphos-scrapped/ | N/A | N/A | City | 34.7729 | 32.4301
Chile | N/A | Teck Resources Quebrada Blanca phase 2 project | Others | Coal / Mine | Other | No | covid-19 | supply chain | This prompted Codelco to not only halt the construction of all new projects and expansions with these being the main operations in mining where the workforce is required to travel, but also to reduce its workforce at its Chuquicamata operations to a minimum at least from late June to at least 2-half July, impacting both the mine and the smelter. |  |  |  | 2019 |  | https://www.teck.com/operations/chile/projects/quebrada-blanca-phase-2/ | Delayed | Delay in construction | brownfield | https://ihsmarkit.com/research-analysis/chile-report-july-2020--sulphuric-acid-market-and-covid19.html | N/A | N/A | City | -20.2305 | -70.1374
Chile | N/A | Tango FLNG project | Energy | Natural Gas | Natural gas transmission | No | covid-19 | others | Argentinian energy company YPF has sent a force majeure notice to Belgium shipowner Exmar, saying it is unable to pay for the charter of the Tango FLNG unit due to the effect of the coronavirus pandemic. |  |  |  | 2018 |  | http://www.exmar.be/sites/default/files/media/document_center/reports_and_downloads/press_releases/announcement_exmar_ypf.pdf | Delayed | Delay in construction | greenfield | https://www.oedigital.com/news/479692-exmar-slams-unlawful-tango-flng-force-majeure-by-ypf | N/A | N/A | Exact Location | -33.8735 | -58.423
Canada | N/A | Site C Project | Energy | Electricity | Electricity generation and transmission | No | covid-19 | supply chain | Construction delays and rising costs on British Columbia's Site C dam project are being blamed on the impact of the pandemic, but it's prompted the provincial government to appoint an adviser to look over the operation. |  |  |  | 2014 |  | https://www.bchydro.com/news/press_centre/news_releases/2016/site-c-fact-sheet.html | Delayed | Delay in construction | greenfield | https://www.jwnenergy.com/article/2020/8/3/bc-hydro-says-pandemic-hits-site-c-project-expect-/ | N/A | N/A | Exact Location | 56.1947 | -120.9142
Bulgaria | N/A | Balkan Stream natural gas pipeline | Energy | Natural gas | Natural gas transmission | No | covid-19 | labor shortage | Lockdowns due to the coronavirus delayed construction |  |  |  | 2019 |  | https://globuc.com/news/russia-and-bulgaria-begin-construction-of-balkan-stream-gas-pipeline/ | Delayed | Delay in Construction | greenfield | https://pgjonline.com/news/2020/06-june/bulgaria-still-aims-to-complete-turkstream-pipeline-extension-by-year-end-pm | N/A | N/A | City | 43.2984 | 27.3605
Italy | N/A | Milan Metro Line 4 | Transport | Railways | Local Passenger/Light rail | No | covid-19 | labor shortage | Implementation of Covid-19 pandemic restrictions |  |  |  | 2014 |  | https://www.infrapppworld.com/news/megaproject-382-financial-close-reached-for-milan-metro-line-4 | Delayed | Delay in Construction | greenfield | https://www.enr.com/articles/49127-work-restarts-on-18b-covid-19-closed-milan-subway-project | Resumed | https://www.enr.com/articles/49127-work-restarts-on-18b-covid-19-closed-milan-subway-project | City | 45.4752 | 9.197
Italy, Austria | N/A | Brenner Base Tunnel | Transport | Roads | Highway and tunnel | Yes | covid-19 | labor shortage | Implementation of Covid-19 pandemic restrictions |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | greenfield | https://www.tunneltalk.com/International-25Mar2020-Coronavirus-impacts-projects-around-the-world.php | N/A | N/A | City | 47.2821 | 11.3664
India | N/A | 100MW Tidong hydropower project | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | Due to Covid-19 outbreak |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | brownfield | https://www.hydroreview.com/hydro-industry-news/statkraft-stalls-hydro-and-wind-projects-due-to-covid-19/#gref | N/A | N/A | City | 31.6644 | 78.384
Chile | N/A | 52MW Los Lagos hydropower project | Energy | Electricity | Electricity generation | No | covid-19 | preemptive action | Due to Covid-19 outbreak |  |  |  | N/A |  | N/A | Delayed | Delay in construction | greenfield | https://www.hydroreview.com/hydro-industry-news/statkraft-stalls-hydro-and-wind-projects-due-to-covid-19/#gref | N/A | N/A | City | -40.3354 | -72.9543
Russia Federation | N/A | Nord Stream 2 | Energy | Natural Gas | Natural gas transmission | Yes | political issue | N/A | Due to threat of sanctions from US |  |  |  | 2017 |  | https://www.gazprom.com/projects/nord-stream2/ | Delayed | Delay in Construction | greenfield | https://www.oedigital.com/news/484551-report-nord-stream-2-set-to-resume-pipelaying-works-in-danish-waters | Resumed | https://www.oedigital.com/news/484551-report-nord-stream-2-set-to-resume-pipelaying-works-in-danish-waters | Exact Location | 59.6661 | 28.2815
Bangladesh | N/A | Padma Bridge Rail Link Project | Transport | Railways | Regional Passenger | No | technical issue | N/A | "So, it appears that the deadline for construction of the railway viaduct at the Mawa-Bhanga section would be delayed and the cost would be hiked," reads the document. |  |  |  | 2018 |  | https://www.thedailystar.net/frontpage/news/padma-rail-link-poject-time-cost-may-draw-out-further-2042073 | Delayed | Delay in construction | Greenfield | https://www.thedailystar.net/frontpage/news/padma-rail-link-poject-time-cost-may-draw-out-further-2042073 | N/A | N/A | Exact Location | 23.4705 | 90.2641
Mexico | N/A | Juchitán wind farm (Eólica del Sur) | Energy | Electricity | Electricity generation | No | legal issue | N/A | The Supreme Court ruled yesterday that a wind farm project in Oaxaca must be halted because the process to approve it violated the rights of the local indigenous community. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://mexiconewsdaily.com/news/court-orders-halt-to-juchitan-wind-farm/ | Resumed | https://www.business-humanrights.org/en/latest-news/mexico-largest-windfarm-in-the-region-opened-despite-concerns-that-the-consultation-of-local-indigenous-communities-did-not-comply-with-international-law/ | Exact Location | 16.4878 | -95.0369
Brazil | N/A | Belo Monte Dam | Energy | Electricity | Electricity generation | No | legal issue | N/A | The court ordered further construction halted until Norte Energia met the commitments it made in 2011 to provide adequate housing for those displaced by the dam |  |  |  | 2011 |  | https://news.mongabay.com/2017/09/belo-monte-dam-installation-license-suspended-housing-inadequacy-cited/ | Delayed | Delay in Construction | Greenfield | https://news.mongabay.com/2017/09/belo-monte-dam-installation-license-suspended-housing-inadequacy-cited/ | Resumed | https://www.nsenergybusiness.com/projects/belo-monte-hydropower-project-brazil/ | Exact Location | -3.1281 | -51.779
Canada | N/A | Petronas Pacific Northwest LNG Project | Energy | Natural Gas | Natural gas transmission | No | environmental issue | N/A | by the prolonged depressed prices and shifts in the energy industry have led us to this decision |  |  |  | 2015 |  | https://www.theedgemarkets.com/article/petronas-reach-conditional-fid-canadian-lng-project-next-month | Cancelled | Cancel before Construction | Greenfield | https://www.bbc.com/news/world-us-canada-40719926 | N/A | N/A | Exact Location | 49.54439809835141, -123.1153065791589 | -123.1153
Argentina | N/A | Kirchner-Cepernic Hydro Complex | Energy | Electricity | Electricity generation | No | legal issue | N/A | the Supreme Court of Justice of the Nation (CSJN) suspended the construction |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://dialogochino.net/en/climate-energy/8356-argentina-suspends-patagonia-dams/ | N/A | N/A | City | -50.233 | -70.9523
Australia | N/A | Wheatstone Offshore Gas Project | Energy | Natural Gas | Natural gas transmission | No | etc. | N/A | U.S. oil major Chevron has announced that the first exports from Australia’s Wheatstone offshore gas project will be delayed from later this year to the middle of 2017. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.maritime-executive.com/article/australias-wheatstone-offshore-gas-project-delayed | N/A | N/A | City | -20.4568 | 115.5237
Bulgaria | N/A | 174.2MW Gorna Arda hydropower complex | Energy | Electricity | Electricity generation | No | political issue | N/A | Plans to build the 174.2MW Gorna Arda hydropower complex in Bulgaria have been put on hold by Austria’s EVN, with the company suggesting that changes in the energy policy environment in the country mean that project development is currently not possible. |  |  |  | 2010 |  | https://dgkv.com/?p=news&lang=en&id=648 | Delayed | Delay before Construction | Greenfield | https://www.waterpowermagazine.com/news/newsevn-calls-halt-to-gorna-arda-plans-bulgaria-5753943 | N/A | N/A | City | 41.4474 | 24.6065
United States | N/A | US Mountain Valley Pipeline | Energy | Oil / Gas Pipeline | Other | No | political issue | N/A | The developer of Mountain Valley Pipeline on Tuesday delayed the in-service target for the 303-mile, 2 Bcf/d natural gas pipeline project to late 2020 Faced with litigation from environmental groups challenging its ESA authorizations from the US Fish and Wildlife Service, MVP had previously voluntarily suspended some work. The project's prior voluntary suspension of forward construction and inability to work in streams and wetlands prevented MVP from fully completing portions of the route |  |  |  | 2017 |  | https://www.mountainvalleypipeline.info | Delayed | Delay in Construction | Greenfield | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/102219-us-mountain-valley-pipeline-delays-startup-to-late-2020-cost-may-now-reach-55-billion | Resumed | https://apnews.com/article/business-mountains-archive-27a72f0b4a6a47ede6dedb2cb5388317 | City | 38.5086 | -80.9968
Canada | N/A | Enbridge Line 3 replacement project | Energy | Oil / Gas Pipeline | Other | Yes | legal issue | N/A | a state and federal permitting timeline that would wrap up later than expected |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Brownfield | https://www.duluthnewstribune.com/business/4582918-line-3-delay-setback-enbridge-canadian-oil-industry | N/A | N/A | City | 45.8752 | -94.9574
Canada | N/A | North Stormont wind farm | Energy | Electricity | Electricity generation | No | legal issue | N/A | Ontario's environment minister is cancelling a wind farm near Ottawa over concerns that it may negatively impact bat populations |  |  |  | 2016 |  | https://www.cornwallnewswatch.com/2020/05/14/court-quashes-cancellation-of-north-stormont-wind-farm/ | Cancelled | Cancel in Construction | Greenfield | https://www.cbc.ca/news/canada/ottawa/bat-concerns-province-cancel-wind-farm-1.5390885 | N/A | N/A | City | 45.1713 | -75.0831
Canada | N/A | 695-Keeyask hydropower plant | Energy | Electricity | Electricity generation | No | monetary issue | N/A | announced a significant increase in its control budget and a revised commissioning date for the 695-MW Keeyask Generating Station |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.hydroreview.com/business-finance/increased-cost-delayed-commissioning-date-announced-for-695-keeyask-hydropower-plant-in-manitoba/ | Resumed | https://www.spglobal.com/marketintelligence/en/news-insights/latest-news-headlines/manitoba-hydro-to-resume-construction-of-695-mw-hydro-project-58783985 | Exact Location | 56.3648 | -95.2349
Canada | N/A | White Pines(60 MW facility with 29 turbines) | Energy | Electricity | Electricity generation | No | political issue | N/A | The bill terminated the 2010 contract between the province’s Independent Electricity System Operator (IESO) and wpd |  |  |  | N/A |  | N/A | Cancelled | Cancel in Construction | Greenfield | https://www.nationalobserver.com/2019/10/29/news/white-pines-demolition-mourned-ford-dismantles-green-energy-ontario | N/A | N/A | City | 44.0079 | -77.3069
Australia | N/A | Carmichael coal mine | Others | Coal / Mine | Other | No | monetary issue, environental issue | N/A | The proposed $16.5 billion project has been delayed for years over environmental and financing issues |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.financialexpress.com/world-news/big-setback-for-adani-enterprises-australia-project-this-huge-fightback-starts-go-home-adani-calls-made/886369/ | Resumed | https://www.brisbanetimes.com.au/politics/queensland/adani-on-track-for-first-carmichael-mine-coal-exports-in-2021-20200716-p55cnh.html | Exact Location | -22.1333 | 146.45
Canada | N/A | Valley Line LRT Southeast | Transport | Railways | Local Passenger/Light rail | No | etc. | N/A | The line was initially expected to open this December, but hit an early roadblock when a car-sized concrete slab in the North Saskatchewan River was found during the Tawatinâ Bridge construction |  |  |  | 2016 |  | https://www.on-sitemag.com/construction/financial-close-reached-on-edmontons-1-8b-transit-expansion/1003953252/ | Delayed | Delay in Construction | Greenfield | https://edmontonjournal.com/news/local-news/trending-late-six-month-delay-anticipated-for-1-8-b-valley-line-southeast-lrt | Resumed | https://edmontonjournal.com/news/local-news/trending-late-six-month-delay-anticipated-for-1-8-b-valley-line-southeast-lrt | Exact Location | 53.5431 | -113.4951
Canada | N/A | Pacific NorthWest LNG(PNW LNG) | Energy | Oil / Gas Pipeline | Natural gas transmission | No | monetary issue | N/A | Pacific NorthWest LNG no longer financially viable, |  |  |  | 2015 |  | https://www.ctvnews.ca/business/a-timeline-of-b-c-s-cancelled-pacific-northwest-lng-project-1.3518469 | Cancelled | Cancel in Construction | Greenfield | https://financialpost.com/commodities/energy/a-tragedy-for-canada-petronas-cancels-36b-lng-project-as-b-c-jacks-up-demands | N/A | N/A | Exact Location | 54.2005 | -130.2886
Canada | N/A | Walterdale Bridge | Transport | Roads | Bridge | No | capital issue | N/A | during the spring of 2015 the opening was pushed back because the bridge’s 42 steel beams, which were made in South Korea, arrived months later than expected. |  |  |  | N/A |  | N/A | Delayed | Cancel in Construction | Brownfield | https://canada.constructconnect.com/joc/news/infrastructure/2018/09/edmontons-walterdale-bridge-still-mired-controversy | Resumed | https://globalnews.ca/news/7602891/edmonton-walterdale-bridge-cost/ | Exact Location | 53.5287 | -113.5016
Canada | N/A | Walterdale Bridge | Transport | Roads | Bridge | No | environmental issue | N/A | The bridge was then scheduled to open in late 2016, but it was pushed back again to mid-2017 because of weather-sensitive work, including asphalt paving, which couldn’t be done until after winter. |  |  |  | N/A |  | N/A | Delayed | Cancel in Construction | Brownfield | https://canada.constructconnect.com/joc/news/infrastructure/2018/09/edmontons-walterdale-bridge-still-mired-controversy | Resumed | https://globalnews.ca/news/7602891/edmonton-walterdale-bridge-cost/ | Exact Location | 53.5287 | -113.5016
Canada | N/A | North Van sewage treatment plant | Water and sewerage | Treatment plant | Portable water and sewerage treatment | No | legal issue | N/A | the company failed to meet certain administrative requirements |  |  |  | 2019 |  | https://www.nsnews.com/local-news/metro-approves-tertiary-treatment-for-north-vancouver-sewage-plant-3107472 | Delayed | Delay in Construction | Greenfield | https://www.nsnews.com/local-news/north-van-sewage-treatment-plant-slapped-with-stop-work-order-3097734 | N/A | N/A | Exact Location | 49.3168 | -123.1086
Bahrain | N/A | Bahrain LNG terminal | Energy | Natural Gas | Natural gas transmission | No | N/A | N/A | Teekay, which owns a share in the terminal, did not mention the reason for the delay. |  |  |  | 2017 |  | https://www.gtreview.com/news/mena/bahrain-lng-reaches-financial-close/ | Delayed | Delay in Construction | Greenfield | https://www.zawya.com/mena/en/business/story/Bahrain_LNG_terminal_to_start_operations_by_yearend__Teekay-TR20191114nL4N27U15DX1/ | Resumed | https://www.reuters.com/article/bahrain-lng-imports-idUSL4N27U15D | Exact Location | 26.195 | 50.751
Kenya | N/A | 310-MW Lake Turkana wind farm | Energy | Electricity | Electricity generation and transmission | No | monetary issue | N/A | been lagging behind schedule due to various issues, including demands for compensation from landowners. |  |  |  | 2014 |  | https://www.power-technology.com/projects/lake-turkana-wind-power-project-loyangalani/ | Delayed | Delay in Construction | Greenfield | https://renewablesnow.com/news/transmission-link-delays-launch-of-kenyas-310-mw-wind-farm-report-571467/ | Resumed | https://renewablesnow.com/news/kenyas-310-mw-lake-turkana-wind-farm-delivers-1st-power-to-the-grid-627998/ | Exact Location | 2.4905 | 36.7933
Canada | N/A | Samuel De Champlain Bridge Corridor Project | Transport | Roads | Bridge | No | political issue | N/A | Two labour strikes halted work on the site for several weeks, and new weight restrictions on the old Champlain Bridge meant trucks couldn’t haul the heavy materials needed to build the bridge. Instead, SSL used barges pulled on a winch through the river’s strong current. Making matters worse, one of the tugboats moving the barges capsized and sank to the bottom of the river. |  |  |  | 2015 |  | https://www.infrastructure.gc.ca/nbsl-npsl/agreement-entente-eng.html | Delayed | Delay in Construction | Brownfield | https://montrealgazette.com/news/local-news/champlain-corridor-to-be-complete-by-summer | N/A | N/A | Exact Location | 45.4686 | -73.5047
Vietnam | N/A | Ninh Thuận 2 Nuclear Power Plant | Energy | Electricity | Electricity generation | No | technical issue | N/A | Vietnam’s National Assembly voted on Tuesday to abandon plans to build two multi-billion-dollar nuclear power plants with Russia and Japan, after officials cited lower demand forecasts, rising costs and safety concerns. |  |  |  | 2010 |  | https://www.world-nuclear-news.org/NN-Russia_to_build_nuclear_plant_in_Vietnam-0111104.html | Cancelled | Cancel before Construction | Greenfield | https://www.reuters.com/article/us-vietnam-politics-nuclearpower-idUSKBN13H0VO | N/A | N/A | Exact Location | 11.4123 | 108.974
United States | N/A | Dakota Pipeline Project | Energy | Oil / Gas Pipeline | Other | No | legal issue | N/A | the U.S. Army Corps of Engineers said it would deny the company an easement it needs for the $3.8 billion project |  |  |  | 2014 |  | https://www.gem.wiki/Energy_Transfer_Crude_Oil_Pipeline_(ETCOP)#:~:text=In%20October%202014%2C%20Phillips%2066,Partners%2C%20for%20US%242%20billion. | Delayed | Delay in Construction | Greenfield | https://www.wsj.com/articles/obama-administration-moves-to-deny-easement-for-dakota-pipeline-1480890468 | N/A | N/A | City | 33.7314 | -90.6419
United States | N/A | Dakota Pipeline Project | Energy | Oil / Gas Pipeline | Other | No | legal issue, environmental issue | N/A | The decision by U.S. District Court for the District of Columbia followed the cancellation of another high-profile U.S. pipeline project |  |  |  | 2014 |  | https://www.gem.wiki/Energy_Transfer_Crude_Oil_Pipeline_(ETCOP)#:~:text=In%20October%202014%2C%20Phillips%2066,Partners%2C%20for%20US%242%20billion. | Delayed | Cancel in Construction | Greenfield | https://www.reuters.com/article/us-usa-pipeline-energy-transfer-idUSKBN2471TQ | N/A | N/A | City | 33.7314 | -90.6419
Australia | N/A | Sydney CBD light rail | Transport | Railways | Freight and Regional Passenger | No | technical issue | N/A | Noonan put the latest delay down to Ausgrid’s “failure” to perform essential works to move overhead electricity wires in Kensington and Kingsford underground. |  |  |  | 2015 |  | https://www.railjournal.com/regions/australia-nz/sydney-cbd-light-rail-reaches-financial-close/#:~:text=SYDNEY's%20CBD%20and%20South%20East,financial%20close%20on%20the%20%24A | Delayed | Delay in Construction | Greenfield | https://www.theguardian.com/australia-news/2018/oct/04/sydneys-troubled-21bn-light-rail-project-delayed-again | N/A | N/A | City | -33.8758 | 151.2062
Finland | N/A | Olkiluoto 3 | Energy | Electricity | Electricity generation | No | legal issue | N/A | due to system tests taking longer than expected and long delivery times for spare parts |  |  |  | 2005 |  | https://www.tvo.fi/en/index/news/pressreleasesstockexchangereleases/2005/hnNElbth6.html | Delayed | Delay in Construction | Greenfield | https://www.world-nuclear-news.org/Articles/System-tests-further-delay-Finnish-EPR-start-up | N/A | N/A | Exact Location | 61.2369 | 21.4408
Finland | N/A | Tallinn tunnel project | Transport | Roads | Highway and tunnel | Yes | political issue | N/A | political decision delaying the project |  |  |  | 2018 |  | https://newsnowfinland.fi/economy-business/new-china-deal-keeps-tallinn-tunnel-project-on-track-but-its-still-dogged-by-critics | Delayed | Delay in Construction | Greenfield | https://www.railjournal.com/passenger/high-speed/finnish-regional-council-delays-finland-estonia-undersea-rail-tunnel/ | Resumed | https://yle.fi/uutiset/osasto/news/helsinki-tallinn_tunnel_firm_to_set_up_research_centre_in_metals_mine/11799073 | City | 59.9375 | 24.8396
India | N/A | Adani Power 1,600MW Paraspani thermal power project | Energy | Electricity | Electricity generation | No | etc. | N/A | the PP (Project proponent) did not provide the information regarding the water availability... accordingly, the proposal was deferred |  |  |  | N/A |  | N/A | Delayed | Delay before Construction | Greenfield | https://economictimes.indiatimes.com/industry/energy/power/green-panel-defers-nod-to-adani-power-1600-mw-project-in-jharkhand/articleshow/51424549.cms?from=mdr | Resumed | https://scroll.in/article/917532/in-final-days-of-modi-government-adani-project-in-jharkhand-becomes-india-s-first-power-sector-sez | City | 24.8301 | 87.1305
Malaysia | East Coast Rail Link project | MRL East Coast Rail Line project | Transport | Railways | Regional Passenger | No | monetary issue | N/A | Malaysia has put the brakes on a massive China-backed rail project, citing excessive costs. |  |  |  | 2016 |  | https://en.wikipedia.org/wiki/MRL_East_Coast_Rail_Link | Delayed | Delay in Construction | Greenfield | https://money.cnn.com/2018/07/05/news/economy/malaysia-china-rail-project-suspended/index.html | N/A | N/A | City | 2.9999 | 101.396
Vietnam | N/A | Vam Cong Bridge | Transport | Roads | Bridge | No | political issue | N/A | Its general director Tran Van Thi said repair work at a cracked girder at Vam Cong Bridge has been delayed because the South Korean contractor “did not take drastic enough measures” and “was not active enough". |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://e.vnexpress.net/news/news/s-korean-contractor-slammed-for-delay-in-opening-major-vietnam-bridge-3819251.html | Resumed | http://www.koreaherald.com/view.php?ud=20190524000509 | Exact Location | 10.3177 | 105.5037
Russia Federation | N/A | Nord Stream 2 | Energy | Oil / Gas Pipeline | Natural gas transmission | Yes | political issue | N/A | US sanctions have interrupted construction of Russia's divisive gas pipeline to Germany, Nord Stream 2. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Brownfield | https://euobserver.com/foreign/146996 | Resumed | https://www.derstandard.at/story/2000122346403/bau-von-gas-pipeline-nord-stream-2-geht-wieder-los | City | 59.6659 | 28.2819
Kuwait | N/A | Al-Zour North 2 independent water and power project (IWPP) | Energy, Water and Sewerage | Electricity, Treatment plant | Electricity generation, Sewerage treatment plant | No | legal issue, technical issue | N/A | Kuwait has cancelled the tender for the planned Al-Zour North 2 independent water and power project (IWPP), some 14 months after bids were submitted. |  |  |  | N/A |  | N/A | Cancelled | Cancel before Construction | Brownfield | https://www.meed.com/kuwait-cancels-al-zour-north-2-iwpp-tender/ | N/A | N/A | Exact Location | 28.7214 | 48.3682
Kazakhstan | N/A | Balkhash Thermal Power Plant | Energy | Electricity | Electricity generation | No | monetary issue | N/A | Samsung Engineering has put a big coal power plant project in Kazakhstan on hold due to finance-related issues. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | http://www.koreatimes.co.kr/www/news/tech/2015/09/133_187428.html | N/A | N/A | City | 45.207 | 73.9297
Kazakhstan | N/A | Balkhash Thermal Power Plant | Energy | Electricity | Electricity generation | No | legal issue | N/A | South Korea’s Samsung C&T Corp. and Samsung Engineering Co. have decided to terminate a 2.8 trillion won ($2.50 billion) thermal power plant project in Kazakhstan due to delayed financing arrangements from the local government, the companies said in regulatory filings on Thursday. |  |  |  | N/A |  | N/A | Cancelled | Cancel in Construction | Greenfield | https://pulsenews.co.kr/view.php?year=2016&no=623932 | N/A | N/A | City | 45.207 | 73.9297
Canada | N/A | Walterdale Bridge Replacement | Transport | Roads | Bridge | No | environmental issue | N/A | A complex bridge design, working in the river and bad weather meant that work proceeded more slowly this construction season than the contractor expected, he said. Difficulties with steel shipments were resolved but the delay affected the project’s schedule. |  |  |  | 2015 |  | https://edmontonjournal.com/business/local-business/walterdale-bridge-delayed-again-wont-open-until-mid-2017 | Delayed | Delay in Construction | Brownfield | https://edmontonjournal.com/business/local-business/walterdale-bridge-delayed-again-wont-open-until-mid-2017 | Resumed | https://edmontonjournal.com/news/local-news/a-lot-of-money-industry-eyes-late-fines-as-grand-opening-booked-for-walterdale-bridge | Exact Location | 53.5296 | -113.5012
India | N/A | Zojila Tunnel project | Transport | Roads | Highway and tunnel | No | monetary issue | N/A | But 18 months later, the state project has ground to a halt. The contractor, Infrastructure Leasing and Financial Services, defaulted in September 2018, accused of wrongdoing and leaving behind about $13bn in debt. |  |  |  | 2018 |  | https://en.wikipedia.org/wiki/Zoji-la_Tunnel | Cancelled | Cancel before Construction | Greenfield | https://www.ft.com/content/1cb65eaa-1c4e-11ea-97df-cc63de1d73f4 | Resumed | https://en.wikipedia.org/wiki/Zoji-la_Tunnel | Exact Location | 34.2532 | 75.4268
Denmark | N/A | Vesterhav Syd wind farm | Energy | Electricity | Electricity generation | No | environmental issue | N/A | This February, the Energy Board of Appeal cancelled and withdrew the part of Vesterhav Syd’s construction licence that concerns the environmental impact assessment (EIA). |  |  |  | 2018 |  | https://renewablesnow.com/news/construction-of-vattenfalls-danish-offshore-wind-farms-pushed-to-2023-648529/ | Delayed | Delay before Construction | Greenfield | https://renewablesnow.com/news/construction-of-vattenfalls-danish-offshore-wind-farms-pushed-to-2023-648529/ | Resumed | https://group.vattenfall.com/press-and-media/newsroom/2020/the-danish-energy-agency-grant-permits-for-vesterhav-syd-and-nord | Exact Location | 56.0335 | 8.0266
Denmark | N/A | Nord wind farm | Energy | Electricity | Electricity generation | No | legal issue | N/A | This February, the Energy Board of Appeal cancelled and withdrew the part of Vesterhav Syd’s construction licence that concerns the environmental impact assessment (EIA). |  |  |  | 2018 |  | https://renewablesnow.com/news/construction-of-vattenfalls-danish-offshore-wind-farms-pushed-to-2023-648529/ | Delayed | Delay before Construction | Greenfield | https://renewablesnow.com/news/construction-of-vattenfalls-danish-offshore-wind-farms-pushed-to-2023-648529/ | N/A | N/A | City | 56.1498 | 8.162
Australia | N/A | Brisbane Legacy Way tunnel | Transport | Roads | Highway and tunnel | No | etc. | N/A | Mr Quirk stopped short of blaming the slowdown on unions // civil work had not been completed, as well as delays caused by safety issues |  |  |  | 2010 |  | https://www.tunneltalk.com/TransApex-Sep10-Brisbane-Northern-Link-award.php | Delayed | Delay in Operation | Greenfield | https://www.abc.net.au/news/2015-10-23/opening-legacy-way-delayed-slow-workers-graham-quirk-brisbane/6880396 | N/A | N/A | City | -27.4812 | 152.9809
United States | N/A | Keystone XL Pipeline | Energy | Oil / Gas Pipeline | Other | Yes | legal issue, environmental issue, political issue | N/A | Keystone XL has been killed and revived under two presidents 10 years after it first was proposed. Now the battleground over its future is in the courts and on the ground where it would be constructed. In early November, U.S. District Court Judge Brian Morris in Great Falls halted the project, ruling it couldn’t proceed without additional study of oil spill mitigation and the pipeline’s effects on climate change and Native American cultural resources. January 20, 2021 United States President Joe Biden revoked the permit for the pipeline on his first day in office. |  |  |  | 2017-03-01 |  | https://www.forbes.com/sites/ellenrwald/2020/12/08/12-years-later-and-we-are-still-debating-the-keystone-xl-pipeline/?sh=17ab617c3bf9 | Delayed | Delay before Construction | Greenfield | https://www.greatfallstribune.com/story/news/2018/11/28/montana-keystone-xl-pipeline-oil-taxes-protest-risk/1893505002/ | Resumed | https://www.ktvq.com/news/montana-news/tc-energy-says-keystone-xl-pipeline-construction-to-resume | City | 52.669 | -111.317
Ireland | N/A | Dunkettle interchange upgrade | Transport | Roads | Highway | No | political issue | N/A | The criticism follows confirmation that Transport Infrastructure Ireland (TII) is to tender for the construction stage of the Cork project as it could not agree on the costs with Sisk, the company that has carried out preparatory work on the Dunkettle interchange upgrade to date. |  |  |  | 2017-05-01 |  | https://www.irishexaminer.com/news/arid-30944273.html | Delayed | Delay before Construction | Brownfield | https://www.irishexaminer.com/news/arid-30944273.html | N/A | N/A | City | 53.3502 | -6.2705
Uganda | Nyagak III Hydro Power | Nyagak III Hydroelectric Power Station | Energy | Electricity | Electricity generation | No | monetary issue | N/A | German bank Kfw has withhold its funds for the construction of uganda’s nyagak power project due to incomplete financial closure from project developers. |  |  |  | 2019-03-01 |  | https://www.afrik21.africa/en/uganda-to-relaunch-6-6-mw-nyagak-hydroelectric-project/ | Delayed | Delay before Construction | Greenfield | https://www.gambetanews.com/germany-withhold-funds-for-ugandas-nyagak-power-project/ | Resumed | https://constructionreviewonline.com/news/uganda/uganda-to-commence-construction-of-nyagak-mini-hydro-power-dam/ | Exact Location | 2.4281 | 30.9733
Denmark, Germany | N/A | Kriegers Flak Grid Solution | Energy | Electricity | Electricity transmission | Yes | capital issue | N/A | the delay is primarily due to the German labour market. |  |  |  | 2018 |  | https://www.4coffshore.com/news/kriegers-flak-grid-solution-delayed-nid8619.html | Delayed | Delay in Construction | Greenfield | https://www.4coffshore.com/news/kriegers-flak-grid-solution-delayed-nid8619.html | Resumed | https://www.windtech-international.com/projects-and-contracts/construction-of-kriegers-flak-offshore-wind-farm-has-started | Exact Location | 55.026 | 12.939
Germany | N/A | 203MW Trianel Windpark Borkum II Project | Energy | Electricity | Electricity generation | No | monetary issue, environmental issue | N/A | its self-administered insolvency procedure — which has dominated much of 2019 — has caused massive delays in the construction schedule //Frequent bad weather in autumn and winter compounded the issue |  |  |  | 2019 |  | https://www.powerworldanalysis.com/senvion-completes-supply-contract-203mw-trianel-windpark-borkum-ii/ | Delayed | Delay in Construction | Greenfield | https://www.windpowermonthly.com/article/1667843/senvion-troubles-delay-trianel-completion | N/A | N/A | Exact Location | 54.042 | 6.4667
Greece | N/A | Skouries mine | Others | Coal / Mine | Other | No | legal issue, political issue | N/A | Pending permits for Skouries, covering the construction of a smelter on site, have been delayed because of differences between Eldorado and the ministry’s technical experts regarding testing methods applied to comply with environmental regulations. |  |  |  | 2012 |  | https://www.eldoradogold.com/assets/operations-and-projects/europe/projects/skouries-greece/default.aspx | Delayed | Delay in Construction | Greenfield | https://biv.com/article/2017/11/eldorado-halts-investment-greeces-skouries-project | Resumed | https://www.mining.com/greece-grants-eldorado-gold-permits-for-olympia-mine-and-skouries-project/ | Exact Location | 40.6218 | 23.1916
Hungary | N/A | M4 motorway project | Transport | Roads | Highway | Yes | political issue, monetary issue | N/A | the European Commission had withdrawn support from the project thereby prompting the government of Hungary to cease further construction// Hungarian government had known from the start that it could not fund the motorway’s construction using Hungarian public funds alone, and that the government had hoped European Union funds would cover bulk of the costs |  |  |  | 2018 |  | https://www.worldhighways.com/wh8/news/eu-loan-hungarys-m4-budapest-romanian-border | Cancelled | Cancel in Construction | Greenfield | https://budapestbeacon.com/hungary-cancels-m4-motorway-project-after-ec-calls-foul/ | Resumed | https://www.worldhighways.com/wh8/news/construction-start-hungarys-revamped-m4-project-2016 | City | 47.5352 | 19.0361
Vietnam | N/A | Nghi Son 2 Thermal Power Plant | Energy | Electricity | Electricity generation | No | monetary issue | N/A | there has been a delay in the construction due to the contract schedule of the ordering organization and the Vietnamese government, but it has finally been able to kick off construction after receiving the advancement payment for the project. |  |  |  | 2018-04-01 |  | https://www.nsenergybusiness.com/projects/nghi-son-2-thermal-power-plant-thanh-hoa/ | Delayed | Delay in Construction | Greenfield | https://pulsenews.co.kr/view.php?year=2018&no=469625 | Resumed | https://pulsenews.co.kr/view.php?year=2018&no=469625 | City | 19.8006 | 105.7886
Greece | N/A | E65 Central Greece Motorway | Transport | Roads | Highway | No | etc. | N/A | the projects were poorly planned and significantly delayed |  |  |  | 2018 |  | https://ec.europa.eu/commission/presscorner/detail/en/ip_21_144 | Delayed | Delay in Construction | Greenfield | https://www.keeptalkinggreece.com/2018/03/21/greece-motorways-eu-auditors/ | Resumed | https://news.gtp.gr/2021/01/19/commission-approves-works-central-greece-e65-highway/ | City | 38.9009 | 22.4367
Lithuania, Sweden | N/A | 700 MW NordBalt power cable | Energy | Electricity | Electricity generation and transmission | Yes | technical issue | N/A | “has previously communicated that the line will temporarily be shut down due to cable joint repair. We ... (cannot) comment on any contractual terms, |  |  |  | 2010 |  | https://www.reuters.com/article/idUSWEA820020101217?edition-redirect=uk | Delayed | Delay in Operation | Greenfield | https://www.wirenet.org/news-categories/item/171-submarine-power-cable-shut-down-for-repairs-in-response-to-multiple-failures | Resumed | https://www.globaltransmission.info/archive.php?id=22419 | City | 55.8042 | 21.1963
Greece | N/A | Elefsina-Korinthos-Patras-Pyrgos-Tsakona Motorway | Transport | Roads | Highway | No | etc. | N/A | the projects were poorly planned and significantly delayed |  |  |  | 2008-05-01 |  | https://www.eib.org/en/projects/pipelines/all/20070091 | Delayed | Delay in Construction | Divestiture | https://www.keeptalkinggreece.com/2018/03/21/greece-motorways-eu-auditors/ | N/A | N/A | City | 38.0474 | 23.5408
Finland, Russian Federation | N/A | Hanhikivi 1power plant | Energy | Electricity | Electricity generation | No | political issue | N/A | Rosatom reportedly attributed the delay to concerns from Finland’s safety regulators, who have been hesitant to green light the project due to potential safety threats. |  |  |  | 2013-12-01 |  | https://www.fennovoima.fi/en/news/fennovoima-and-rusatom-overseas-signed-plant-supply-contract | Delayed | Delay in Construction | Greenfield | https://www.helsinkitimes.fi/finland/finland-news/domestic/16064-setback-for-nuclear-industry-as-hanhikivi-power-plant-is-delayed-by-a-further-four-years.html | N/A | N/A | City | 64.466 | 24.2625
Russian Federation | N/A | Kaliningrad Wastewater Treatment Plant | Water and sewerage | Treatment plant | Portable water and sewerage treatment | No | technical issue | N/A | the plant was still unfinished, and the construction froze when the general contractor went bust |  |  |  | 2007-12-01 |  | https://www.ymparisto.fi/en-US/Waters/Kaliningrad_Wastewater_Treatment_Plant_o(43467) | Delayed | Delay in Construction | Greenfield | https://www.nib.int/who_we_are/news_and_media/articles/2104/kaliningrad_inaugurates_long-expected_wastewater_treatment_plant | N/A | N/A | Exact Location | 54.6939 | 20.3183
United States | N/A | Freeport LNG Texas export terminal | Energy | Natural Gas | Natural gas transmission | No | etc. | N/A | Freeport LNG, a privately held U.S. liquefied natural gas company, said on Thursday it pushed back the projected start date for its $13 billion export terminal under construction in Texas by about nine months to around Sept. 1, 2019. |  |  |  | 2015 |  | https://www.nsenergybusiness.com/projects/freeport-lng-export-terminal-quintana-island-texas/ | Delayed | Delay in Construction | Greenfield | https://www.reuters.com/article/us-freeport-lng-outlook/freeport-lng-delays-start-of-texas-export-terminal-to-september-2019-idUSKBN1HQ2ET | Resumed | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/081919-freeport-lng-begins-liquefaction-production-at-texas-export-facility-operator | City | 28.9802 | -95.3084
Ireland | N/A | Mayo Renewable Power - Killala Plant | Energy | Electricity | Electricity generation | No | monetary issue | N/A | WORK ON A power plant at Killala, Co Mayo, has been halted due to a lack of funding. |  |  |  | 2015 |  | https://electricenergyonline.com/news.php?ID=533892 | Delayed | Delay in Construction | Greenfield | https://www.thejournal.ie/mayo-power-plant-halt-2891808-Jul2016/ | N/A | N/A | City | 54.2132 | -9.2207
United Kingdom | N/A | Isle of Man Ferry terminal | Transport | Ports | Runway and terminal | No | legal issue | N/A | A new £38m ferry terminal connecting Liverpool and the Isle of Man will not be completed until July 2021, the Manx government has said. |  |  |  | 2019 |  | https://www.bbc.com/news/world-europe-isle-of-man-49018913 | Delayed | Delay in Construction | Greenfield | https://mannintv.com/2019/11/20/38m-manx-ferry-terminal-project-delayed-until-july-2021-bbc-news/ | Resumed | https://www.business-live.co.uk/ports-logistics/build-38m-isle-man-ferry-17582284 | Exact Location | 53.4129 | -3.0008
United States | N/A | MOX fuel fabrication plant project | Energy | Electricity | Electricity generation | No | legal issue | N/A | NRC-regulated construction activities at the facility ceased in October 2018, when the National Nuclear Security Administration (NNSA) - a semi-autonomous agency of the US Department of Energy (DOE) - issued a contract termination notice to the consortium |  |  |  | 1999 |  | https://www.linkedin.com/company/shaw-areva-mox-services-llc | Cancelled | Cancel in Construction | Greenfield | https://www.world-nuclear-news.org/Articles/NRC-terminates-US-MOX-plant-authorisation | N/A | N/A | City | 33.6271 | -81.7188
Norway | N/A | Follo Line Project | Transport | Railways | Freight and Regional Passenger | No | monetary issue | N/A | Condotte are in debt to several of their subcontractors and this has led to a full stop in the construction work, |  |  |  | 2015 |  | https://www.banenor.no/en/startpage1/News/bane-nor-has-terminated-two-epc-contracts/ | Cancelled | Cancel in Construction | Greenfield | https://www.banenor.no/en/startpage1/News/bane-nor-has-terminated-two-epc-contracts/ | Resumed | https://www.railjournal.com/financial/norway-set-for-record-rail-investment-in-2021-budget/ | City | 59.9226 | 10.7553
Russian Federation | N/A | Sakhalin-2 LNG plant expansion | Energy | Natural Gas | Natural gas transmission | No | political issue | N/A | the lack of gas resources and international sanctions |  |  |  | 1994 |  | https://2b1stconsulting.com/gazprom-approved-shell-sakhalin-2-lng-expansion-roadmap/ | Delayed | Delay before Construction | Brownfield | https://www.reuters.com/article/russia-gazprom-lng/russias-sakhalin-2-lng-plants-expansion-put-on-hold-sources-idUSL8N27H1T8 | N/A | N/A | Exact Location | 52.87 | 143.77
United Arab Emirates | N/A | Barakah Nuclear Energy Plant | Energy | Electricity | Electricity generation | No | legal issue | N/A | FANR was not ready to give Nawah its operating license and wanted to postpone this |  |  |  | 2011 |  | https://www.thenationalnews.com/uae/uae-s-first-nuclear-power-plant-delayed-until-late-2019-or-2020-1.734445 | Delayed | Delay in Operation | Greenfield | https://www.thenationalnews.com/uae/uae-s-first-nuclear-power-plant-delayed-until-late-2019-or-2020-1.734445 | N/A | N/A | Exact Location | 23.9678 | 52.2317
Russian Federation | N/A | South Stream Gas Pipeline | Energy | Oil / Gas Pipeline | Other | Yes | monetary issue, political issue | N/A | The decision to cancel South Stream came at a time of increased diplomatic tension with the EU ... But there were also economic reasons. |  |  |  | 2012 |  | https://www.gem.wiki/South_Stream_Gas_Pipeline#Project_Details | Cancelled | Cancel in Construction | Greenfield | https://mondediplo.com/2015/06/07South-Stream | N/A | N/A | City | 44.9194 | 37.3195
Georgia | N/A | Nenskra hydropower plant | Energy | Electricity | Electricity generation | No | political issue, environmental issue | N/A | The second project, the Nenskra hydroelectric power station, is only at the stage of preparation for construction, but it may not even start due to the protests |  |  |  | 2017 |  | https://www.aiib.org/en/projects/proposed/2017/_download/georgia_nenskra_hydropower/nenskra_hydropower_plant.pdf | Cancelled | Cancel in Construction | Greenfield | https://energycentral.com/news/georgia-suspends-construction-hydropower-plants-across-country | N/A | N/A | City | 43.0279 | 42.4606
United Kingdom | N/A | 340MW Thanet Extension offshore wind project | Energy | Electricity | Electricity generation | No | environmental issue | N/A | The UK government has delayed a consent decision on Vattenfall’s planed 340MW Thanet Extension offshore wind project off southern England, asking for more details over a clutch of outstanding issues from seabed leasing to fish impacts before saying yes or no. |  |  |  | N/A |  | N/A | Delayed | Delay before Construction | Brownfield | https://www.rechargenews.com/wind/uk-delays-consent-for-vattenfalls-thanet-extension-offshore-wind/2-1-711727 | N/A | N/A | Exact Location | 51.4272 | 1.6029
Singapore | N/A | Bukit Brown road project | Transport | Roads | Highway | No | monetary issue, etc. | N/A | The controversial Bukit Brown road will not be completed by next month as projected. It is the second delay since the project was announced in 2011. |  |  |  | 2013 |  | https://www.straitstimes.com/singapore/lta-confirms-second-delay-in-bukit-brown-road-project-new-completion-deadline-by-early | Delayed | Delay in Construction | Greenfield | https://www.straitstimes.com/singapore/lta-confirms-second-delay-in-bukit-brown-road-project-new-completion-deadline-by-early | Resumed | https://www.torque.com.sg/news/lornie-highway-opens/ | City | 1.365 | 103.8687
Nigeria | N/A | Trans-Saharan Gas Pipeline Project (TSGP) | Energy | Oil / Gas Pipeline | Other | No | political issue, etc. | N/A | The investors are aware that Nigeria is currently facing the challenge of meeting its gas obligation to neighbouring African countries through the West Africa Gas Pipeline Company, due to insecurity in the Niger Delta. |  |  |  | 2009 |  | https://www.esi-africa.com/industry-sectors/business-and-markets/nigeria-trans-saharan-gas-pipeline-project-remains-a-dream/ | Delayed | Delay before Construction | Greenfield | https://www.esi-africa.com/industry-sectors/business-and-markets/nigeria-trans-saharan-gas-pipeline-project-remains-a-dream/ | N/A | N/A | City | 4.9755 | 8.3383
Malaysia | N/A | East Coast Rail Link (ECRL) project | Transport | Railways | Regional Passenger | No | monetary issue, political issue | N/A | Malaysian Prime Minister Mahathir Mohamad said on Tuesday that the Chinese-funded $20 billion East Coast Rail Link (ECRL) project and a natural gas pipeline project in Sabah will be canceled for now, according to media reports. |  |  |  | N/A |  | N/A | Cancelled | Cancel before Construction | Brownfield | https://www.reuters.com/article/us-china-malaysia/malaysias-mahathir-cancels-china-backed-rail-pipeline-projects-idUSKCN1L60DQ | Resumed | https://www.railway-technology.com/projects/east-coast-rail-link-ecrl-project/ | City | 2.9997 | 101.4024
New Zealand | N/A | Transmission Gully motorway | Transport | Roads | Highway | No | environmental issue | N/A | Progress has been slower than anticipated due to numerous weather and seismic events, including the need for resources to be diverted for the response to the 2016 Kaikoura earthquake. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.stuff.co.nz/motoring/117777481/transmission-gully-motorway-construction-considerably-behind-schedule | N/A | N/A | Exact Location | -41.1107 | 174.9181
Fiji | N/A | Kinoya Sewerage Treatment Plant | Water and sewerage | Treatment plant | Sewerage treatment plant | No | monetary issue | N/A | The contract had shifted from 2009 to 2010 because there was an eight months delay of payment to the contractor. |  |  |  | N/A |  | N/A | Delayed | Delay before Construction | Management contract and lease | https://fijisun.com.fj/2018/02/01/pac-highlights-delay-in-construction-of-treatment-plant/ | N/A | N/A | Exact Location | -18.109 | 178.4812
United States | N/A | Constitution Pipeline Project | Energy | Oil / Gas Pipeline | Natural gas transmission | No | environmental issue | N/A | because its developer, the Williams Companies, is unable to complete tree cutting by a March 31 federal deadline that is designed to protect migratory birds, |  |  |  | N/A |  | N/A | Delayed | Delay before Construction | Greenfield | https://stateimpact.npr.org/pennsylvania/2016/03/11/williams-delays-construction-of-constitution-pipeline/ | N/A | N/A | City | 40.8811 | -77.0451
United States | N/A | Constitution Pipeline Project | Energy | Oil / Gas Pipeline | Natural gas transmission | No | environmental issue | N/A | Oklahoma energy giant Williams Cos. has canceled plans for the controversial Constitution pipeline, an interstate natural gas pipeline that would have crossed through New York's Catskill Mountains. |  |  |  | N/A |  | N/A | Cancelled | Cancel before Construction | Greenfield | https://www.eenews.net/stories/1062432063 | N/A | N/A | City | 40.8811 | -77.0451
Albania | N/A | Power Plant on the Langarica River | Energy | Electricity | Electricity generation | No | environmental issue | N/A | Licenses for the construction and use of 30 power plants throughout Albania were cancelled by the country’s government |  |  |  | 2012 |  | http://www.ensohydro.at/en/portfolio/detail/lengarica/ | Cancelled | Cancel before Construction | Greenfield | https://balkangreenenergynews.com/government-cancels-contracts-for-30-hydro-plants/ | N/A | N/A | Exact Location | 40.2599 | 20.4628
Honduras | N/A | Agua Zarca hydro project | Energy | Electricity | Electricity generation | No | political issue, environmental issue | N/A | After the murder of Berta Caceres and other violent incidents in the beginning of 2016, the project's funding was suspended |  |  |  | 2011 |  | https://www.banktrack.org/project/agua_zarca_dam#brief_history | Delayed | Delay in Construction | Greenfield | https://www.banktrack.org/project/agua_zarca_dam | N/A | N/A | Exact Location | 15.0677 | -88.0665
Philippines | N/A | Laguna Lake Rehabilitation Project | Water and sewerage | Water Utility | Channel dredging and terminal | No | political issue | N/A | because it was a project of his predecessor Arroyo whom he and his Yellow cult demonized, Aquino abruptly ordered the project stopped in November 2010 |  |  |  | N/A |  | N/A | Cancelled | Cancel before Construction | Greenfield | https://www.manilatimes.net/2018/07/23/opinion/columnists/topanalysis/flooded-filipinos-pay-p1-2b-for-flood-control-project-that-aquino-stopped/422409/ | N/A | N/A | City | 14.4162 | 121.191
Ireland, Scotland | N/A | Scotland-Ireland gas pipeline phase2 | Others | Natural Gas | Natural gas transmission | Yes | monetary issue | N/A | Contractor SICIM/Roadbridge JV has had to undertake additional works on river crossings which has led to a delay of a year to the opening of the 50km tunnel which will connect Ireland and Scotland. The cost of phase two of the project, between Cluden and Brighouse Bay in Scotland, was expected to be £41.2M but has now risen to £62.2M. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.newcivilengineer.com/latest/next-phase-of-scotland-ireland-gas-pipeline-21m-over-budget-02-08-2018/ | N/A | N/A | City | 54.8651 | -4.0789
Cambodia | N/A | Chhay Areng hydropower dam | Energy | Electricity | Electricity distribution | No | political issue, environmental issue | N/A | “Now I beg you to stop talking about it.” Hun Sen’s comments came a day after Spanish activist Alex Gonzalez-Davidson, who had campaigned against the Chinese-backed Chhay Areng hydropower dam in Koh Kong province, was deported following the government’s refusal to renew his visa. |  |  |  | N/A |  | N/A | Delayed | Delay before Construction | Greenfield | https://thediplomat.com/2015/02/cambodia-suspends-china-dam-project-to-silence-opposition/ | N/A | N/A | City | 11.548 | 103.4427
Spain | N/A | Castor Natural Gas Submarine Storage project | Energy | Natural Gas | Natural gas transmission | No | environmental issue | N/A | The plant has never again been in operation since it provisionally closed down in 2013, after the facility was blamed for causing hundreds of earthquakes measuring up to 4.1 on the Richter scale, with tremors going on for weeks. |  |  |  | N/A |  | N/A | Cancelled | Cancel in Operation | Greenfield | https://www.catalannews.com/business/item/spanish-government-to-dismantle-controversial-gas-plant | N/A | N/A | City | 39.988 | -0.052355
Fiji | N/A | Suva Arterial Road Upgrading Project 2 (SARUP 2) | Transport | Roads | Highway | No | etc. | N/A | The Fiji Roads Authority (FRA) has announced that it has had to take the regrettable action to terminate the contract for the delivery of the Suva Arterial Road Upgrading Project 2 (SARUP 2). |  |  |  | 2015 |  | http://documents1.worldbank.org/curated/en/844151559191998730/text/Disclosable-Version-of-the-ISR-Fiji-Transport-Infrastructure-Investment-Project-P150028-Sequence-No-09.txt | Cancelled | Cancel in Construction | Brownfield | https://fijisun.com.fj/2019/11/18/fiji-roads-authority-terminates-sarup-2-contract-with-guizhou-road-and-bridge-company/ | N/A | N/A | City | -18.1173 | 178.4546
Saudi Arabia | N/A | Haramain High Speed rail system | Transport | Railways | Freight and Regional Passenger | No | technical issue, political issue | N/A | the Medina-Mecca rail link is plagued by delays, political tensions and technical headaches. |  |  |  | 2011 |  | https://www.irishtimes.com/business/spanish-high-speed-rail-fiasco-in-saudi-arabia-1.2094125 | Delayed | Delay in Constrution | Greenfield | https://www.irishtimes.com/business/spanish-high-speed-rail-fiasco-in-saudi-arabia-1.2094125 | Resumed | https://www.arabnews.com/node/1825356/saudi-arabia | Exact Location | 22.4216 | 39.1914
Bhutan | N/A | Thimphu-Wangdue Tunnel Project | Transport | Roads | Highway and tunnel | No | monetary issue | N/A | The cost of building a tunnel is astronomically higher as compared to roads |  |  |  | 2011 |  | https://www.businessbhutan.bt/2017/12/21/budget-constraints-stall-thimphu-wangdue-tunnel-project/ | Delayed | Delay in Construction | Brownfield | https://www.businessbhutan.bt/2017/12/21/budget-constraints-stall-thimphu-wangdue-tunnel-project/ | N/A | N/A | Exact Location | 27.4801 | 89.8962
Australia | N/A | Gorgon LNG plant | Energy | Natural Gas | Natural gas transmission | No | technical issue | N/A | the project was repeatedly delayed, with the company blaming technical issues. |  |  |  | 2007 |  | https://web.archive.org/web/20110706101026/http://anthonyalbanese.com.au/file.php?file=%2Fnews%2FZJJDWKOLIUWJNVUAWHIGLRJJ%2Findex.html | Delayed | Delay in Operation | Greenfield | https://www.theguardian.com/australia-news/2019/aug/08/gorgon-lng-plant-begins-long-delayed-carbon-capture-and-storage-project | Resumed | https://www.theguardian.com/australia-news/2019/aug/08/gorgon-lng-plant-begins-long-delayed-carbon-capture-and-storage-project | Exact Location | -20.7909 | 115.4509
United Kingdom | N/A | Hinkley C Point Nuclear Plant | Energy | Electricity | Electricity generation | No | covid-19 | labor shortage | We are still facing the full force of the pandemic |  |  |  | 2016 |  | https://www.gov.uk/government/news/government-confirms-hinkley-point-c-project-following-new-agreement-in-principle-with-edf | Delayed | Delay in Construction | Greenfield | https://www.bloomberg.com/news/articles/2021-01-27/edf-sees-delay-and-rising-bill-in-british-nuclear-plant-project | N/A | N/A | Exact Location | 51.2077 | -3.1277
Panama | N/A | Panama Canal expansion project | Transport | Others | Other | No | capital issue | N/A | ue to a dispute between the administrator and the building consortium over costs |  |  |  | 2008 |  | https://archive.is/20120525182120/http://www.ordons.com/americas/central-america-and-caribbean/162-financing-deal-for-panama-canal-expansion-signed.html | Delayed | Delay in Construction | Brownfield | https://www.maritime-executive.com/article/acp-new-panama-canal-locks-to-be-completed-by-june | N/A | N/A | City | 9.124 | -79.732
Taiwan, China | N/A | Taoyuan Airport Terminal 3 | Transport | Airports | Runway and terminal | No | technical issue | N/A | The complexity of the design is proving to be an obstacle to completing the project on schedule. |  |  |  | 2020.05 |  | https://www.taiwannews.com.tw/en/news/3798581 | Delayed | Delay in Construction | Brownfield | https://www.taiwannews.com.tw/en/news/3404806 | Resumed | https://www.taiwannews.com.tw/en/news/3404806 | Exact Location | 25.0804 | 121.2371
United Arab Emirates | N/A | Barakah Nuclear Plant Unit1 | Energy | Electricity | Electricity generation | No | technical issue | N/A | make time for regulatory approvals and complete safety checks. |  |  |  | 2012 |  | https://www.power-technology.com/projects/barakah-nuclear-power-plant-abu-dhabi/ | Delayed | Delay in Operation | Greenfield | https://www.neimagazine.com/news/newsmore-delays-for-uaes-barakah-project-6233083 | Resumed | https://www.enec.gov.ae/barakah-plant/interactive-timeline/ | Exact Location | 23.9703 | 52.236
Norway | N/A | Martin Linge Project | Energy | Oil / Gas Pipeline | Other | No | capital issue | N/A | The incident which occurred at the Samsung Heavy Industries (SHI) Geoje yard in South Korea on May 1 has caused delays |  |  |  | 2012 |  | https://www.nsenergybusiness.com/projects/martin-linge-oil-and-gas-field-north-sea/ | Delayed | Delay in Construction | Greenfield | https://www.offshore-energy.biz/shi-crane-collapse-delays-totals-construction-projects/ | N/A | N/A | Exact Location | 60.3382 | 2.1116
Uruguay | N/A | Punta del Tigre combined-cycle power plant | Energy | Electricity | Electricity generation | No | etc. | N/A | The delay is due to labour conflicts that Hyundai HDEC considers outside its responsibility |  |  |  | 2012 |  | http://www.engdaily.com/news/articleView.html?idxno=1155 | Delayed | Delay in Construction | Greenfield | https://www.powerengineeringint.com/world-regions/asia/concern-over-delay-at-uruguay-s-punta-tigre/ | N/A | N/A | Exact Location | -34.7494 | -56.5389
Israel | N/A | Israel Railways electrification project | Transport | Railways | Local Passenger/Light rail | No | technical issue, monetary issue, etc | N/A | The first attempt was so unsuccessful and amateurish that in 2008, seven years later, the Ministry of Finance decided to cancel the tenders and start the entire project over again. Israel Railways is planning to spend only NIS 158 million of a total NIS 4.185 billion budget this year on the sub-project of preparing the electrification infrastructure. In other words, in 2019, which was to have a peak year in the railway track electrification project, only 3.7% of the project will be carried out. Semi, the spanish comapny which held the electrification infrastructure tender, lacked local representation as a foreign company working in Israel for the first time. It was given a lot of tasks comapred to their inproficiency regarding the local and small amount of budget. |  |  |  | 2019 |  | https://en.globes.co.il/en/article-israels-electric-trains-running-nine-years-late-1001280126 | Delayed | Delay in Construction | Brownfield | https://en.globes.co.il/en/article-israels-electric-trains-running-nine-years-late-1001280126 | N/A | N/A | City | 31.7886 | 35.203
United Arab Emirates | N/A | Barakah Nuclear Power Plant | Energy | Electricity | Electricity generation | No | technical issue, etc | N/A | The delays were caused by the need to rip and replace counterfeit cables and other components installed in the plant. |  |  |  | 2013 |  | https://energypost.eu/south-koreas-nuclear-ambitions-face-safety-quality-issues/ | Delayed | Delay in Construction | Greenfield | https://energypost.eu/south-koreas-nuclear-ambitions-face-safety-quality-issues/ | Resumed | https://world-nuclear-news.org/Articles/First-UAE-nuclear-reactor-reaches-full-power | Exact Location | 23.9703 | 52.2374
Estonia | N/A | Saaremaa offshore wind project | Energy | Electricity | Electricity generation | No | political issue | N/A | In April 2019, the Estonian government announced it will not issue a building permit to the developer of the project due to national security concerns. |  |  |  | 2015 |  | https://www.msp-platform.eu/events/development-saaremaa-offshore-wind-farm-estonia | Delayed | Delay before Construction | Greenfield | https://www.offshore-energy.biz/van-oord-joins-estonian-offshore-wind-project/ | Resumed | https://www.vanoord.com/en/updates/van-oord-shareholder-saare-wind-energy/ | Exact Location | 58.1139 | 21.8933
Turkmenistan, Uzbekistan, Kazakhstan, China | N/A | The Central Asia-China Gas Pipeline Network: Line D | Energy | Oil / Gas Pipeline | Other | Yes | political issue | N/A | that construction of Line D — the most significant chunk of the Central Asia-China gas network — would be indefinitely suspended wasn’t necessarily a surprise |  |  |  | 2007 |  | https://www.cnpc.com.cn/en/FlowofnaturalgasfromCentralAsia/FlowofnaturalgasfromCentralAsia2.shtml | Cancelled | Cancel in Construction | Greenfield | https://thediplomat.com/2017/03/the-central-asia-china-gas-pipeline-network-line-dead/ | N/A | N/A | City | 39.6547 | 62.7832
United States | N/A | Kentucky Wired | ICT | ICT backbone | Land-based cables | No | monetary issue | N/A | These delays have pushed backed the project’s expected completion date to October 2020. |  |  |  | 2015 |  | https://www.fhwa.dot.gov/ipd/project_profiles/ky_kentuckywired.aspx | Delayed | Delay in Construction | Greenfield | https://www.courier-journal.com/story/news/politics/2018/10/11/lawmakers-hammer-botched-kentuckywired-broadband-project/1606954002/ | Resumed | http://www.floydct.com/news/official-progress-slow-but-moving-forward-on-kentucky-wired/article_c01b7a6c-5a12-11e8-a5f5-ab59f23afa6a.html | City | 38.1043 | -84.5122
Finland | N/A | Hanhikivi nuclear power plant | Energy | Electricity | Electricity generation | No | legal issue, technical issue | N/A | The start-up date of a Russian-built Hanhikivi nuclear power plant in Finland has again been delayed over safety concerns |  |  |  | 2010 |  | https://www.reuters.com/article/idUKLDE6600ED?edition-redirect=uk | Delayed | Delay before Construction | Greenfield | https://bellona.org/news/nuclear-issues/2019-01-russian-built-reactor-in-finland-again-delayed | N/A | N/A | Exact Location | 65.7901 | 23.7552
United States | N/A | Cameron LNG | Energy | Natural Gas | Natural gas transmission | No | technical issue | N/A | Cameron LNG, a liquefied natural gas (LNG) facility in Louisiana operated be Sempra Energy has declared force majeure due to technical problems at the export terminal |  |  |  | 2014 |  | https://www.nsenergybusiness.com/projects/cameron-lng-project-louisiana/ | Delayed | Delay in Construction | Greenfield | https://www.reuters.com/article/us-usa-lng-forcemajeure/cameron-lng-declares-force-majeure-at-louisiana-export-terminal-traders-idUSKCN1VY16X | N/A | N/A | Exact Location | 30.0768 | -93.3508
Panama | N/A | Barro Blanco hydroelectric power plant | Energy | Electricity | Electricity generation | No | etc. | N/A | In early November 2016, Panama withdrew the Barro Blanco hydroelectric power plant project from the Clean Development Mechanism (CDM) – the first time a host country has withdrawn a CDM registration due to human rights concerns. Specifically, the project failed to respect the rights of the indigenous Ngäbe people. |  |  |  | 2016 |  | https://www.banktrack.org/project/barro_blanco_dam_project | Cancelled | Cancel in Construction | Greenfield | https://www.ciel.org/panama-withdraws-problematic-barro-blanco-dam-project-cdm-registry/ | N/A | N/A | Exact Location | 8.2143 | -81.5942
Qatar | N/A | Barzan Gas Project | Energy | Oil / Gas Pipeline | Other | No | technical issue | N/A | The start-up of Qatar’s Barzan gas project has reportedly been delayed due to a leak in a gas pipeline. |  |  |  | 2011 |  | https://ijglobal.com/articles/75302/barzan-gas-project-qatar | Delayed | Delay in Operation | Greenfield | https://www.offshore-energy.biz/report-gas-leak-delays-barzan-project-start-up/ | Resumed | https://www.mees.com/2019/6/28/news-in-brief/qatar-long-delayed-barzan-gas-approaches-start-up/557b1fe0-99b2-11e9-973d-c1404d36619e | City | 25.8961 | 51.5272
Singapore | N/A | Johor Bahru-Singapore Rapid Transit System (RTS) Link | Transport | Railways | Freight | Yes | etc. | N/A | The suspension of the Johor Bahru-Singapore Rapid Transit System (RTS) Link project has been extended to Apr 30, 2020, said Transport Minister Khaw Boon Wan on Monday (Nov 4). |  |  |  | N/A |  | N/A | Delayed | Delay before Construction | Greenfield | https://www.channelnewsasia.com/news/singapore/singapore-jb-malaysia-rts-rail-link-agreement-12062794 | Resumed | https://www.channelnewsasia.com/news/singapore/malaysia-johor-bahru-singapore-rts-signing-july-30-12934908 | Exact Location | 1.4665 | 103.7636
United States | N/A | Plains & Eastern Clean Line | Energy | Electricity | Electricity transmission | No | capital issue | N/A | The U.S. Department of Energy on Friday withdrew from a 2016 agreement to partner with a private developer on a more than 700-mile transmission line that would have delivered wind power from blustery Oklahoma to Tennessee and beyond. |  |  |  | N/A |  | N/A | Cancelled | Cancel before Construction | Greenfield | https://www.reuters.com/article/us-usa-energy-clean-line/u-s-withdraws-from-wind-energy-power-line-project-idUSKBN1GZ3A2 | N/A | N/A | City | 35.5674 | -97.5466
United States | N/A | V.C. Summer nuclear power plant | Energy | Electricity | Electricity generation | No | monetary issue | N/A | South Carolina Electric & Gas Company, principal subsidiary of SCANA Corporation, and South Carolina Public Service Authority (Santee Cooper) announced on July 31 that they are halting construction of two new nuclear reactors at the V.C. Summer nuclear power plant. |  |  |  | N/A |  | N/A | Cancelled | Cancel in Construction | Greenfield | https://www.eia.gov/todayinenergy/detail.php?id=32472 | N/A | N/A | Exact Location | 34.2986 | -81.3162
United States | N/A | Permian Highway Pipeline | Energy | Natural Gas | Natural gas transmission | Yes | legal issue | N/A | The Permian Highway Pipeline, proposed to stretch 430 miles from Waha, Texas to the Gulf Coast, has been delayed due to the “slower than anticipated pace of regulatory approvals.” |  |  |  | 2018 |  | https://braungresham.com/condemnation/active-pipeline-companies-texas/permian-highway-pipeline/ | Delayed | Delay in Construction | Greenfield | https://www.sanmarcosrecord.com/news/permian-highway-pipeline-delayed | N/A | N/A | Exact Location | 32.7257 | -102.6719
Panama | N/A | 224-MW Bocas del Toro project (Changuinola II hydroelectric project) | Energy | Electricity | Electricity generation | No | political issue | N/A | Panama said on Tuesday it will cancel a contract given to Brazil’s Odebrecht |  |  |  | 2014 |  | https://www.reuters.com/article/us-panama-corruption/panama-to-cancel-odebrecht-contract-amid-corruption-scandal-idUSKBN14H072 | Cancelled | Cancel before Construction | Greenfield | https://www.reuters.com/article/us-panama-corruption/panama-to-cancel-odebrecht-contract-amid-corruption-scandal-idUSKBN14H072 | N/A | N/A | City | 9.405 | -82.2657
Romania | N/A | Ploiesti – Brasov (A3) highway | Transport | Roads | Highway | No | etc. | N/A | The government of Romania has abandoned a plan to procure a €1.4bn toll motorway over the Carpathian mountains through a public–private partnership (PPP) with a Turkish–Chinese consortium. |  |  |  | 2018 |  | https://www.romaniajournal.ro/business/contract-for-ploiesti-brasov-highway-to-be-made-by-turkish-chinese-consortium/ | Cancelled | Cancel before Construction | Greenfield | https://www.globalconstructionreview.com/news/romania-abandons-14bn-carpathian-motorway-ppp/ | N/A | N/A | City | 44.9378 | 26.0265
France | N/A | Notre-Dame-des-Landes airport | Others | Airports | Other | No | environmental issue, etc | N/A | The French government abandoned plans for a new 580 million euro ($710 million) airport in western France on Wednesday. But opponents said it was too costly, environmentally unfriendly and that there was another under-utilised airport 110 km to the north near Rennes in Brittany. |  |  |  | 2008 |  | https://www.ouest-france.fr/pays-de-la-loire/notre-dame-des-landes-44130/notre-dame-des-landes-ce-qu-il-faut-retenir-de-l-annonce-d-edouard-philippe-5505933 | Cancelled | Delay before Construction | Brownfield | https://www.reuters.com/article/us-france-airport/france-abandons-plan-for-new-airport-squatters-ordered-out-idUSKBN1F61LQ | N/A | N/A | Exact Location | 47.3817 | -1.7089
Russian Federation, Ukraine, Belarus, Poland, Hungary, Slovakia, Czech Republic, Germany | N/A | Druzhba pipeline | Energy | Oil / Gas Pipeline | Other | Yes | technical issue, political issue | N/A | The serious damage this is causing Russia as an oil exporter, in both economic and image terms, may indicate that the crisis is the result of machinations by some of the smaller Russian private oil companies. On the other hand, rising tensions between Russia and Belarus, and the Kremlin’s use of energy to implement its foreign policy goals, means we cannot completely rule out the possibility that this is a politically motivated action undertaken by Moscow. |  |  |  | N/A |  | N/A | Delayed | Delay in Operation | Greenfield | https://www.osw.waw.pl/en/publikacje/analyses/2019-05-08/dirty-oil-greatest-crisis-history-druzhba-pipeline | Resumed | https://112.international/finance/450-000-tons-of-contaminated-oil-returned-to-russia-belneftekhim-40557.html | City | 51.9242 | 4.475
New Zealand | N/A | Waterview Tunnel | Transport | Roads | Highway and tunnel | No | technical issue | N/A | The tunnel, between Point Chevalier and Mount Roskill, was due to be completed in April but that was pushed back after a sprinkler system was found to be faulty. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.rnz.co.nz/news/national/334290/new-waterview-tunnel-attracts-noise-concerns | Resumed | https://www.rnz.co.nz/news/national/334290/new-waterview-tunnel-attracts-noise-concerns | Exact Location | -36.8974 | 174.7098
United Kingdom | N/A | Heathrow Airport Expansion project | Transport | Airports | Runway and terminal | No | monetary issue, political issue, environmental issue | N/A | The delay came after Britain’s aviation regulator, the Civil Aviation Authority, said the airport could not increase its spending on early construction costs to ensure that the runway was built by the end of 2026, as it wanted. |  |  |  | N/A |  | N/A | Delayed | Delay before Construction | Brownfield | https://www.reuters.com/article/us-britain-heathrow/heathrows-new-runway-delayed-until-at-least-2028-idUSKBN1YO0TM | N/A | N/A | Exact Location | 51.4709 | -0.45474
Chile | N/A | Quebrada Blanca Phase 2 (QB2) expansion project | Energy | Coal / Mine | Other | No | covid-19 | labor shortage | workforce was reduced to 500 people in March, following demobilisation activities |  |  |  | 2019 |  | https://www.jbic.go.jp/en/information/press/press-2019/0531-012214.html | Delayed | Delay in Construction | Greenfield | https://www.miningweekly.com/article/teck-slashes-guidance-covid-delays-chile-expansion-by-up-to-6-months-2020-07-23/rep_id:3650 | N/A | N/A
France | N/A | Strasbourg West Bypass A355 2 | Transport | Roads | Highway | No | environmental issue | N/A | The French Government has stopped the construction works for the western Strasbourg bypass due to environmental issues. |  |  |  | 2014 |  | Vinci achieves US$435 million financial close of road PPP in... ¦ Infrastructure Finance & Investment (infrapppworld.com) | Delayed | Delay in Construction | Greenfield | https://www.worldhighways.com/wh1/news/strasbourg-bypass-surveys-halted-over-environmental-concerns | N/A | N/A | Exact Location | 48.5757 | 7.7528
Ireland | N/A | N25 New Ross Road Bypass PPP Project | Transport | Roads | Bridge, Highway | No | capital issue | N/A | Delivery of Ireland’s longest bridge has been delayed by several weeks due to crumbling concrete which was detected at one of the supporting piers for the structure, The Irish Times has learned. |  |  |  | 2016 |  | Republic of Ireland’s N25 New Ross Bypass achieves financial close ¦ World Highways | Delayed | Delay in Construction | Brownfield | https://www.irishtimes.com/news/ireland/irish-news/crumbling-concrete-delays-finish-of-ireland-s-longest-bridge-1.4029146 | Resumed | https://www.munster-express.ie/business/opening-date-announced-for-n25-new-ross-bypass/ | Exact Location | 52.3565 | -6.9939
United Kingdom | N/A | Aberdeen Western Peripheral Route | Transport | Roads | Highway | No | legal issue, technical issue | N/A | Scottish Economy Secretary Keith Brown has confirmed at least another six months delay in the opening of the over-running Aberdeen Western Peripheral Route. |  |  |  | 2014 |  | Financial close for Aberdeen Western Peripheral Route PPP ¦ Infrastructure Finance & Investment (infrapppworld.com) | Delayed | Delay in Construction | Greenfield | https://www.scotsman.com/news/transport/aberdeen-bypass-opening-delayed-again-until-least-december-230987 | N/A | N/A | Exact Location | 57.1378 | -2.247
United Kingdom | N/A | Nottingham Express Transit | Transport | Railways | Local Passenger/Light rail | No | technical issue | N/A | NET phase 2, the Nottingham tram extension adding two new lines to the city’s light rail network, opened today (25 August) after eight months of delays. |  |  |  | 2011 |  | Nottingham Express Transit - developed two new tram lines (fulcruminfrastructuremanagement.co.uk) | Delayed | Delay in Construction | Greenfield | https://www.railtechnologymagazine.com/Rail-News/nottingham-tram-extension-opens-after-eight-month-delay | Resumed | https://www.railwaygazette.com/nottingham-express-transit-phase-2-opens/41277.article | City | 53.0022 | -1.1963
Spain | N/A | Barcelona Metro - Line 9 | Transport | Railways | Local Passenger/Light rail | N | etc. | N/A | From 2011 to 2014 the construction of this work was delayed |  |  |  | 2010 |  | Barcelona Metro Linea 9 Stretch II - Tagmydeals | Delayed | Delay in Construction | Greenfield | https://pemb.cat/en/strategic-projects/construction_line_9_of_the_metro/2/ | Resumed | https://pemb.cat/en/strategic-projects/construction_line_9_of_the_metro/2/ | City | 41.3608 | 2.1255
United Kingdom | N/A | M25 Motorway Widening | Transport | Roads | Highway | No | etc. | N/A | The delay occurred because the Highways Agency was testing whether using the hard shoulder at peak times could negate the need for motorway widening. |  |  |  | 2009 |  | https://bankwatch.org/public-private-partnerships/case-studies/m25-widening-uk | Delayed | Delay before Construction | Brownfield | https://www.bbc.com/news/uk-england-london-11791804 | Resumed | https://www.newcivilengineer.com/archive/transport-minister-marks-official-start-of-m25-widening-08-07-2009/ | Exact Location | 51.6854 | -0.1487
Italy | N/A | Rome Fiumicino Airport / Leonardo da Vinci International Airport | Transport | Airports | Runway and terminal | No | Political issue | N/A | The financial holding indirectly running Rome’s two airports has postponed approval of its 2013 budget and of a multibillion-euro investment plan because of uncertainty over tariffs that need to be approved by the government. |  |  |  | 1999 |  | https://www.eib.org/de/press/all/1999-104-eur-155-mio-to-aeroporti-di-roma-to-upgrade-romes-airport | Delayed | Delay in Operation | Brownfield | https://www.reuters.com/article/uk-airports-rome-idUKLNE8BC00520121213 | Resumed | https://www.wantedinrome.com/news/romes-fiumicino-rated-best-airport-in-europe-for-fourth-year-in-a-row.html | Exact Location | 41.8004 | 12.2448
Ireland | N/A | M50 Motorway: Dublin bypass | Transport | Roads | Highway | No | Legal issue, environmental issue | N/A | CONSTRUCTION work on the last remaining section of Dublin's M50 motorway near Carrickmines Castle could be further delayed after conservationists yesterday lodged an appeal with the Supreme Court. |  |  |  | 1993 |  | https://www.eib.org/en/projects/pipelines/all/20050315 | Delayed | Delay in Construction | Greenfield | https://www.independent.ie/irish-news/supreme-court-appeal-may-further-delay-completion-of-m50-motorway-25890963.html | N/A | N/A | Exact Location | 53.4265 | -6.2498
Ireland | N/A | M7 - M8 Motorways: Casteltown - Portlaoise - Cullahill | Transport | Roads | Highway | No | etc. | N/A | The section between Nenagh and Limerick was originally due to open last year, but the project was delayed because of subsidence on a stretch of road through Annaholty bog. |  |  |  | 2007 |  | https://www.eib.org/en/projects/pipelines/all/20050563 | Delayed | Delay in Operation | Greenfield | https://www.rte.ie/news/2010/0928/136080-m7/ | Resumed | https://www.independent.ie/regionals/kerryman/news/motorway-section-opens-27399392.html | Exact Location | 52.9382 | -7.6122
Uganda | N/A | Bujagali Hydroelectric | Energy | Electricity | Electricity Generation | No | political issue | N/A | Construction was initially scheduled to begin in January 2003, but was delayed after vocal protests by environmentalists and residents of the area. |  |  |  | 2005 |  | https://www.eib.org/en/projects/pipelines/all/20050357 | Delayed | Delay before Construction | Greenfield | https://www.power-technology.com/projects/bujagali/ | N/A | N/A | Exact Location | 0.49858 | 33.1375
Greece | N/A | Thessaloniki Submerged Tunnel | Transport | Roads | Highway | No | etc. | N/A | The reasons for the delay in the programme are many. Initially, delays arose from the finalisation of environmental and technical studies on behalf of the tender authorities and there were extended negotiations to finalise project and finance documentation for each concession scheme after preferred bidder stage. Furthermore in several cases the final tender award process was impacted due to legal challenges from losing bidders following announcement of preferred tenderer. |  |  |  | 2007 |  | https://ijglobal.com/articles/111819/tunnel-visions | Delayed | Delay before Construction | Greenfield | https://ijglobal.com/articles/111819/tunnel-visions | Resumed | https://ijglobal.com/articles/111819/tunnel-visions | City | 40.6401 | 22.9368
Spain | N/A | Malaga Light Rightway Network | Transport | Railways | Local Passenger/Light rail | No | etc. | N/A | The delay has been caused by the Mobility Department of Málaga City Hall, who issued a report on the traffic problems which will be caused by the metro construction to the city centre with a terminus at La Alameda, saying that a total of 25 street diversions will be needed. |  |  |  | 2003 |  | https://www.emta.com/spip.php?article434 | Delayed | Delay in Construction | Greenfield | http://www.typicallyspanish.com/news-spain/malaga/The_delay_in_taking_the_M_laga_Metro_to_the_city_centre_will_result_in_a_multimillion_overspend.shtml | N/A | N/A | City | 36.7194 | -4.42
Spain | N/A | Autopista Radial 2 / R-2 | Transport | Roads | Highway | No | monetary issue | N/A | There are two main reasons why these toll roads are in this situation. Firstly, the cost of the land on which the motorways were built was higher than originally anticipated and, secondly, there has been a sharp drop in traffic as a result of the economic crisis. The R‐2 motorway management company is owned by Abertis, ACS, Acciona and Globalvía (which, itself, is jointly owned by FCC and Bankia), has become insolvent as a result of the government’s delay in paying out funds that it had earmarked several years previously with the aim of alleviating the plight of the toll roads. |  |  |  | 2000 |  | https://www.eib.org/attachments/general/events/ecofin0710_1_a1.pdf | Delayed | Delay in Operation | Greenfield | https://www.europarl.europa.eu/doceo/document/E-7-2013-010698_EN.html?redirect | N/A | N/A | City | 40.524 | -3.3892
Bolivia | N/A | Bolivia electric vehicle battery plant | Energy | Electricity | Electricity generation | No | monetary issue | N/A | Bolivia’s government has cancelled a joint venture project with Germany’s privately owned ACI Systems Alemania (ACISA), which was seeking to develop a massive lithium project in the country’s southern highlands. |  |  |  | 2018 |  | https://www.reuters.com/article/us-bolivia-lithium-china-idUSKCN1PV2F7 | Cancelled | Cancel in Construction | Greenfield | https://www.dw.com/en/bolivia-scraps-joint-lithium-project-with-german-company/a-51100873 | N/A | N/A | Exact Location | -19.979 | -67.4982
United Arab Emirates | N/A | Abu Dhabi international airport Midfield Terminal | Transport | Airports | Runway and terminal | No | etc. | N/A | The opening of Abu Dhabi Airports' $2.94 billion Midfield Terminal has been pushed back by two years, regional newspapers reported on Monday, in the latest setback for a project seen as crucial to the emirate's wider expansion into tourism. |  |  |  | 2012 |  | https://www.adac.ae/english/mtp/MTP/latest-news/2012-06-27-ADAC-Signs-AED-10-8-Billion-Contract-with-TAV-CCC-Arabtec-Joint-Venture-for-the-Construction-of-the-Midfield-Terminal-Building | Delayed | Delay in Construction | Brownfield | https://www.zawya.com/mena/en/story/Abu_Dhabis_new_airport_terminal_opening_delayed_to_2019-TR20170306nL5N1GJ3M9X2/ | Resumed | https://simpleflying.com/abu-dhabi-airport-new-terminal/ | Exact Location | 24.4419 | 54.65
United Kingdom | N/A | Rampion Wind Farm | Energy | Electricity | Electricity generation | No | technical issue | N/A | A billion-pound wind farm has been closed for more than two weeks after a technical fault brought it to a standstill. Rampion Wind Farm |  |  |  | 2014 |  | https://www.rampionoffshore.com/about/history/ | Delayed | Delay in Operation | Greenfield | https://www.wind-watch.org/news/2019/11/12/1bn-rampion-wind-farm-will-be-shut-for-weeks-due-to-fault/ | N/A | N/A | Exact Location | 50.7843 | 0.05796
Romania | N/A | Rovinari Coal Mine expansion | Others | Coal / Mine | Other | No | legal issue | N/A | A Bucharest court blocked the expansion of Rosia, the largest coal mine in Romania located in Gorj county, following a legal challenge to the mine’s environmental permit lodged by Bankwatch Romania. |  |  |  | 2008 |  | https://web.archive.org/web/20080610165936/http://www.cnlo.ro/index.html | Cancelled | Delay before Construction | Brownfield | https://bankwatch.org/press_release/expansion-of-largest-coal-mine-in-romania-stopped-following-bankwatch-court-case | N/A | N/A | Exact Location | 45.4439 | 23.4094
Portugal | N/A | Fridão hydropower dam on the Tâmega river | Energy | Electricity | Electricity generation | No | environmental issue | N/A | the Portuguese government called off controversial plans for the Fridão hydropower dam on the Tâmega river |  |  |  | 2018 |  | https://www.hydropower-dams.com/news/eib-financing-sought-for-tamega-river-complex-in-portugal/ | Cancelled | Delay before Construction | Greenfield | https://meta.eeb.org/2019/09/24/threat-to-portugals-tamega-river-continues-despite-hydropower-reprieve/ | N/A | N/A | City | 41.3127 | -8.0346
Germany | N/A | Willy Brandt Berlin Brandenburg International Airport | Transport | Airports | Runway and terminal | No | monetary issue, etc. | N/A | The Willy Brandt Berlin Brandenburg International Airport was supposed to open in 2012, but it has been delayed repeatedly and is now set to open in 2017. |  |  |  | 2016 |  | https://www.berlin-airport.de/en/press/press-releases/2016/2016-08-03-funding/index.php | Delayed | Delay in Construction | Greenfield | https://www.npr.org/sections/parallels/2015/08/04/429047195/berlins-new-airport-still-in-a-holding-pattern | Resumed | https://www.berliner-kurier.de/berlin/ber-luftfahrtbehoerde-erlaubt-inbetriebnahme-am-31-oktober-li.108821 | Exact Location | 52.3649 | 13.5097
Colombia | N/A | Caribbean FLNG project | Energy | Natural Gas | Electricity transmission | No | capital issue | N/A | Exmar said that Pacific Rubiales attributed the delay to “unfavorable energy market conditions,” |  |  |  | 2012 |  | https://www.oedigital.com/news/453506-caribbean-flng-delayed | Delayed | Delay in Construction | Greenfield | https://www.oedigital.com/news/453506-caribbean-flng-delayed | Resumed | https://www.offshore-energy.biz/exmar-takes-delivery-of-caribbean-flng-unit/ | City | 9.5251 | -75.5832
India | N/A | Shinkula tunnel | Transport | Roads | Highway and tunnel | No | technical issue | N/A | the water ingress from Seri nullah, a rivulet, that runs above tunnel posed a major geological challenge for engineers |  |  |  | 2016 |  | https://aquaterra.in/trips/darcha-padum-shingo-la-trek-nepal/ | Delayed | Delay in Construction | Greenfield | https://www.hindustantimes.com/chandigarh/jai-ram-keen-on-completion-of-16-703ft-shinkula-tunnel/story-Hk9IfEmT0t4ekVsee0viTK.html | Resumed | https://www.aninews.in/news/national/general-news/centre-speeds-up-construction-work-of-shinku-la-tunnel20200919051206/ | City | 32.9162 | 77.1166
India | N/A | Ratle hydropower project | Energy | Electricity | Electricity generation | No | political issue | N/A | push the World Bank to break the pause and pressure India for resolution of dispute on Kishanganga project |  |  |  | 2017 |  | https://timesofindia.indiatimes.com/india/india-permitted-to-construct-kishanganga-ratle-projects-world-bank/articleshow/59874464.cms | Delayed | Delay in Construction | Greenfield | https://www.thenews.com.pk/print/421530-wb-pause-gives-india-free-rein-to-complete-ratle-project | Resumed | https://www.business-standard.com/article/current-affairs/j-k-s-ratle-hydroelectric-power-corporation-to-develop-850-mw-project-121031800067_1.html | Exact Location | 33.1771 | 75.8082
India | N/A | The Kishanganga Hydro Electric Project (KHEP) | Energy | Electricity | Electricity generation | No | political issue | N/A | rising tensions in Kashmir for the last few months |  |  |  | 2013 |  | https://www.livemint.com/Industry/HgF7hMUl7BWheRxl8CuR4J/India-to-start-Kishanganga-hydropower-project-construction.html | Delayed | Delay in Operation | Greenfield | https://www.thethirdpole.net/en/regional-cooperation/kishanganga-project-opening-delayed-by-kashmir-tensions/ | Resumed | http://www.nhpcindia.com/Default.aspx?id=186&lg=eng&CatId=1&ProjectId=32 | Exact Location | 34.6494 | 74.7508
Pakistan | N/A | Dasu hydropower project | Energy | Electricity | Electricity generation | No | capital issue | N/A | project execution authorities have so far failed to resolve issues pertaining to the cost of land, security of the site and channelling of funds |  |  |  | 2014 |  | https://tribune.com.pk/story/938342/work-delayed-as-issues-remain-unresolved | Delayed | Delay before Construction | Greenfield | https://tribune.com.pk/story/938342/work-delayed-as-issues-remain-unresolved | N/A | N/A | Exact Location | 35.3173 | 73.1933
India | N/A | Chennai Metro rail | Transport | Railways | Local Passenger/Light rail | No | legal issue | N/A | A Russian contractor, Mosmetrostroy, carrying out tunneling operations over an 18-km length underground, had disappeared without a word to Chennai Metro Rail Limited (CMRL) |  |  |  | 2011 |  | https://economictimes.indiatimes.com/industry/transportation/railways/trouble-with-russian-contractor-court-battle-why-chennai-metro-rail-is-caught-in-a-controversy/articleshow/48496857.cms?from=mdr | Delayed | Delay in Construction | Greenfield | https://economictimes.indiatimes.com/industry/transportation/railways/trouble-with-russian-contractor-court-battle-why-chennai-metro-rail-is-caught-in-a-controversy/articleshow/48496857.cms?from=mdr | N/A | N/A | City | 13.0281 | 80.2014
Ghana | N/A | Ghanaian Kpone power plant | Energy | Electricity | Electricity generation | No | environmental issue | N/A | due to fuel contamination. |  |  |  | 2015 |  | https://www.ghanaweb.com/GhanaHomePage/business/Kpone-IPP-will-be-cost-efficient-Cenpower-boss-344713 | Delayed | Delay in Construction | Greenfield | https://cn.reuters.com/article/ozabs-uk-group-five-kpone-idAFKCN1NB12B-OZABS | N/A | N/A | Exact Location | 5.6739 | 0.0375
Myanmar | N/A | Myanmar-China Crude Oil Pipeline | Energy | Oil / Gas Pipeline | Natural gas transmission | Yes | legal issue | N/A | Opposition among the public and non-government organisations |  |  |  | 2015 |  | https://www.mmtimes.com/business/25558-myanmar-china-crude-oil-pipeline-to-commence-next-month.html | Delayed | Delay in Operation | Greenfield | https://www.mmtimes.com/business/25558-myanmar-china-crude-oil-pipeline-to-commence-next-month.html | N/A | N/A | City | 19.129 | 93.7894
Myanmar | N/A | Myitsone Dam | Energy | Electricity | Electricity generation | No | political issue, environmental issue | N/A | Myanmar’s dilemma in choosing between environmental protection and safeguarding the great Irrawaddy River, and its political and economic dependence on Beijing. |  |  |  | 2009 |  | https://www.irrawaddy.com/opinion/analysis/myitsone-dam-flashback.html | Delayed | Delay in Construction | Greenfield | https://thediplomat.com/2019/03/myanmars-myitsone-dam-dilemma/ | Resumed | https://www.irrawaddy.com/opinion/analysis/myitsone-dam-flashback.html | Exact Location | 25.6897 | 97.5178
Myanmar | N/A | Mizoram-Myanmar Kaladan project | Transport | Roads | Highway | Yes | environmental issue | N/A | the long rainy season as the primary cause which has hindered completion of work in time |  |  |  | 2018 |  | https://www.maritimegateway.com/mizoram-myanmar-kaladan-road-project/ | Delayed | Delay in Construction | Greenfield | https://www.firstpost.com/india/slow-progress-mars-mizoram-myanmar-kaladan-project-as-india-misses-deadline-for-road-third-time-in-a-row-5817371.html | N/A | N/A | City | 22.4355 | 92.7595
Nepal | N/A | Dhalkebar substation | Energy | Electricity | Electricity generation and transmission | No | legal issue | N/A | Chinese contractor — Central China Power Grid International Economic and Trade Co Ltd — has been intentionally delaying work |  |  |  | 2018 |  | http://documents1.worldbank.org/curated/en/491661545407029602/pdf/Disclosable-Restructuring-Paper-Nepal-India-Electricity-Transmission-and-Trade-Project-P115767.pdf | Delayed | Delay in Construction | Greenfield | https://thehimalayantimes.com/business/contractor-halts-work-dhalkebar-substation | Resumed | https://en.setopati.com/social/128209 | Exact Location | 26.9488 | 85.95
Rwanda | N/A | Lake Kivu Methane gas project | Energy | Natural Gas | Natural gas transmission | No | legal issue | N/A | disputes between a private investor |  |  |  | 2009 |  | https://www.theeastafrican.co.ke/tea/news/east-africa/dispute-delays-rwanda-power-project-by-3-years--1333878 | Delayed | Delay in Construction | Greenfield | https://www.theeastafrican.co.ke/tea/news/east-africa/dispute-delays-rwanda-power-project-by-3-years--1333878 | Resumed | https://time.com/4338310/rwanda-kivuwatt-methane-lake-kivu/ | Exact Location | -2.0219 | 29.1867
India | N/A | 100-MW Uhl Stage III project | Energy | Electricity | Electricity generation | No | technical issue | N/A | delayed as the construction of the head race tunnel was tedious and also they had just one edit tunnel for the job. The tunnel was filled with slush that further delayed the work |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://www.tribuneindia.com/news/archive/himachal/uhl-iii-project-to-be-functional-by-dec-827320 | N/A | N/A | City | 31.7097 | 76.9344
Albania | N/A | hydropower project (HPP) Kalivaç | Energy | Electricity | Electricity generation | No | capital issue | N/A | the Italian Becchetti Group and Deutsche Bank, however, the constructions have only been completed to 30 %, leaving the river yet unimpaired. |  |  |  | 1997 |  | https://www.ecoalbania.org/en/2017/05/30/hydropower-project-kalivac-revisited-vjosa-at-risk/ | Cancelled | Cancel in Construction | Greenfield | https://www.ecoalbania.org/en/2017/05/30/hydropower-project-kalivac-revisited-vjosa-at-risk/ | N/A | N/A | City | 40.41 | 19.8112
Nigeria | N/A | Lagos-Ibadan railway project | Transport | Railways | Local Passenger/Light rail | No | technical issue | N/A | The contractor has identified over 1,400 buildings to be demolished in communities along the projects right of way right inside Abeokuta in Ogun State. |  |  |  | 2011 |  | https://www.railway-technology.com/projects/abuja-kaduna-rail-line/ | Delayed | Delay in Construction | Brownfield | https://guardian.ng/features/fg-explains-delay-on-lagos-ibadan-railway-project/ | Resumed | https://www.africanews.com/2020/12/09/nigeria-commences-lagos-ibadan-railway-operations/ | Exact Location | 6.9215 | 3.2448
Pakistan | N/A | Tarbela Dam 4th Extension Hydropower Project | Energy | Electricity | Electricity generation | No | monetary issue | N/A | the delay in completion of the project had triggered a delay in the reduction in the overall production cost of energy |  |  |  | 2016 |  | https://tribune.com.pk/story/982406/boosting-power-tarbela-4-extension-to-be-completed-in-june-2017-says-wapda-chief | Delayed | Delay in Construction | Brownfield | https://archive.pakistantoday.com.pk/2016/11/06/delay-in-tarbela-4th-extension-may-cost-ruling-pml-n-money-wise-poll-wise/ | Resumed | https://www.worldbank.org/en/news/factsheet/2020/02/25/tarbela-fourth-hydropower-extension-project-t4hp | Exact Location | 34.0877 | 72.699
Malaysia | N/A | SMART WTE Plant | Municipal Solid Waste | Treatment / Disposal | Incineration / Waste to Energy | No | technical issue | N/A | due to technical issues with the road access at the landfill area. |  |  |  | 2014 |  | http://www.crbenv.com/smart-wte-plant.php | Delayed | Delay in Construction | Greenfield | https://themalaysianreserve.com/2019/09/12/6-more-months-delay-for-cypark-wte/ | N/A | N/A | Exact Location | 2.6633 | 101.8176
Philippines | N/A | La Union power station | Energy | Electricity, Coal | Electricity generation | No | legal issue | N/A | There were delays in 2017 in securing regulatory approval | In December 2016 it was reported (1) that various NGOS involved in environmental protection and climate change, including religious organizations, formed a coalition in a bid to block the proposed coal-fired power plant in Barangay Carisquis, Luna, La Union. |  |  | 2016 |  | https://manilastandard.net/business/206424/coal-plant-rising-in-la-union.html | Delayed | Delay in Construction | Greenfield | https://ejatlas.org/conflict/coal-fired-power-plant-cfpp-in-luna-la-union-philippines | Resumed | https://www.change.org/p/president-rodrigo-duterte-save-the-surfing-capital-of-the-north-from-destruction-save-la-union-province-no-to-coal-fired-power-plant | Exact Location | 16.8534 | 120.3723
Tanzania | N/A | Bagamoyo port project | Transport | Ports | Freight | No | etc. | N/A | Tanzanian President Dr. John Pombe Magufuli had indefinitely suspended plans to construct what would have been East Africa’s largest deep-water port in Bagamoyo, Tanzania, after disagreeing with Chinese investors on the terms of the highly ambitious infrastructure project |  |  |  | 2018 |  | https://constructionreviewonline.com/project-timelines/bagamoyo-port-project-timeline-and-all-you-need-to-know/ | Delayed | Delay in Construction | Greenfield | https://www.orfonline.org/expert-speak/tough-conditions-and-unfavorable-demands-does-china-risk-losing-tanzanias-bagamoyo-port-project-56891/ | N/A | N/A | Exact Location | -6.4329 | 38.9038
Brazil | Sao Manoel Hydro Power Plant | São Manoel hydropower plant | Energy | Electricity | Electricity generation | No | political issue | N/A | Construction of a power plant on the Teles Pires river in Brazil was paralyzed by protesting members of the Munduruku tribe, a leader of the movement told Reuters on Monday, adding to tensions over land conflicts in South America's largest country. |  |  |  | 2014 |  | https://ppi.worldbank.org/en/snapshots/project/sao-manoel-hydro-power-plant-8368 | Delayed | Delay in Construction | Greenfield | https://www.voanews.com/americas/brazil-power-plant-construction-paralyzed-indigenous-protesters | Resumed | https://news.mongabay.com/2018/04/ngos-denounce-tapajos-basin-intimidation-violence-brazil-inaction/ | Exact Location | -9.1628 | -57.0514
Morocco | N/A | New Port of Safi | Transport | Ports | Freight | No | technical issue | N/A | A governmental decree of August 22 has postponed the deadline for the end of construction work on Safi’s new harbor. |  |  |  | 2013 |  | https://www.moroccoworldnews.com/2019/08/281164/morocco-safi-harbor-construction-deadline-year/ | Delayed | Delay in Construction | Greenfield | https://www.moroccoworldnews.com/2019/08/281164/morocco-safi-harbor-construction-deadline-year/ | N/A | N/A | Exact Location | 32.1814 | -9.2648
Kenya | N/A | Kinangop Wind Park | Energy | Electricity | Electricity generation | No | legal issue | N/A | Two years of militant opposition has spurred the cancellation of Kenya's 60.8 MW Kinangop wind project, leaving an agreement to install 38 GE 1.6MW turbines stranded. |  |  |  | 2011 |  | https://www.evwind.es/2013/12/03/kenyas-wind-farm-gets-funding/38713 | Cancelled | Cancel in Construction | Greenfield | https://www.reuters.com/article/kenya-electricity-idUSL8N1620QG | N/A | N/A | Exact Location | -0.82812 | 36.5554
Ghana | N/A | Aboano power station | Energy | Coal / Mine | Electricity generation | No | legal issue | N/A | The project, which was initially scheduled to commence in August 2016 has been postponed to April 2017. |  |  |  | 2016 |  | https://www.ghanabusinessnews.com/2016/10/10/ghana-is-not-building-a-coal-plant-minister/ | Cancelled | Cancel before Construction | Greenfield | https://www.ghanabusinessnews.com/2016/10/10/ghana-is-not-building-a-coal-plant-minister/ | N/A | N/A | Exact Location | 5.4886 | -0.99559
Morocco | Ouarzazate Solar Phase I | Noor Ouarzazate I Solar Complex Project | Energy | Electricity | Electricity generation | No | N/A | N/A | Morocco postponed without explanation the inauguration of Noor-1, a solar power plant due to open Sunday in Ouarzazate, part of what will eventually be the world's largest solar power production facility. |  |  |  | 2016 |  | -https://www.meed.com/exclusive-acwa-power-reaches-financial-close-on-morocco-solar-project/ | Delayed | Delay in Operation | Greenfield | https://www.middleeasteye.net/news/morocco-inexplicably-postpones-opening-worlds-largest-solar-plant | Resumed | https://www.international-climate-initiative.com/en/news/article/official_ceremony_for_the_opening_of_the_noor_i_solar_complex_in_morocco | Exact Location | 31.051 | -6.8708
Kenya | N/A | Nairobi-Mombasa expressway project | Transport | Roads | Highway | No | monetary issue | N/A | Transport Cabinet Secretary James Macharia revealed the report and said the suspension is due to the country’s debt concerns. |  |  |  | 2016 |  | https://www.roadtraffic-technology.com/projects/nairobi-mombasa-highway-expansion-project/ | Delayed | Delay before Construction | Brownfield | https://www.sigmaplantfinder.com/blog/us-3bn-nairobi-mombasa-expressway-project-in-kenya-suspended/ | N/A | N/A | Exact Location | -2.4178 | 37.9608
Tanzania | Aggreko Ubungo and Tegeta Temporary Power Station | Ubungo power plant | Energy | Electricity | Electricity generation | No | monetary issue | N/A | We also need the funds to enable us to meet some of the costs |  |  |  | N/A |  | N/A | Delayed | Delay in Operation | Greenfield | https://www.esi-africa.com/regional-news/east-africa/tanzania-songas-halts-suspensions-ubungo-plant/ | N/A | N/A | Exact Location | -6.7935 | 39.2084
Sri lanka | N/A | $1.5bn Chinese-backed port city project in Colombo | Transport | Ports | Other | No | political issue | N/A | Beijing: The Sri Lankan government has ordered the suspension of a $1.5bn Chinese-backed port city project in Colombo claiming that the project lacks the necessary approvals. |  |  |  | 2014 |  | https://web.archive.org/web/20140119024155/http://www.colombopage.com/archive_12A/Jul30_1343633133CH.php | Delayed | Delay in Operation | Greenfield | https://splash247.com/sri-lanka-suspends-chinese-port-project-in-colombo// | N/A | N/A | City | 6.9407 | 79.8382
Myanmar | N/A | Myitsone Dam project | Energy | Electricity | Electricity generation | No | political issue | N/A | In September 2011, now six years ago, Myanmar’s then-president Thein Sein surprised his countryfolk and international observers by suspending the construction of the Myitsone Dam project in northern Myanmar, the largest of seven dam projects to be built on the Irrawaddy River. |  |  |  | N/A |  | N/A | Delayed | Delay in Construction | Greenfield | https://theconversation.com/dams-on-myanmars-irrawaddy-river-could-fuel-more-conflicts-in-the-country-84386 | N/A | N/A | City | 25.3987 | 97.3841
China, Mongolia | N/A | Egiin Gol Hydropower project | Energy | Electricity | Electricity generation | Yes | environmental issue | N/A | But in the spring, Chinese authorities intervened to suspend the dam project until due diligence is carried out on transboundary impacts |  |  |  | 2015 |  | https://chinadialogue.net/en/pollution/9040-silk-road-project-suspended-over-threats-to-lake-baikal/ | Delayed | Delay before Construction | Greenfield | https://chinadialogue.net/en/pollution/9040-silk-road-project-suspended-over-threats-to-lake-baikal// | N/A | N/A | City | 50.4426 | 100.1593
Peru | Peru Lima Metro Line 2 Project | Lima Metro Line 2 | Transport | Railways | Local Passenger/Light rail | No | technical issue, etc. | N/A | The government failed to meet the deadline for the expropriation of properties that would provide the required land for the execution of the project—requiering the concession-winning contractor to request an arbitration from the World Bank’s International Centre for Settlement of Investment Disputes. |  |  |  | 2015/2016 |  | https://projects.worldbank.org/en/projects-operations/project-detail/P145610 | Delayed | Delay in Operation | Greenfield | https://perureports.com/lima-metro-line-2-delays-postpone-opening-date/5498/ | N/A | N/A | City | -11.8491 | -77.0482
Afghanistan | N/A | Pashdan Dam | Energy | Electricity | Electricity generation | No | etc. | N/A | The construction of the dam was stopped three years ago due to some certain reasons which so far have not been clarified by the Ministry of Energy and Water. However, officials of the ministry recently said that insecurity was one of the main reasons for a pause in the construction work of the project. |  |  |  | 2018 |  | https://tolonews.com/business/work-resumes-construction-herat’s-pashdan-dam | Delayed | Cancel in Construction | Greenfield | https://tolonews.com/business/work-resumes-construction-herat’s-pashdan-dam | Resumed | https://tolonews.com/business/work-resumes-construction-herat%E2%80%99s-pashdan-dam | City | 34.3536 | 62.204
Iran, Pakistan | N/A | Iran-pakistan gas pipeline project | Energy | Oil / Gas Pipeline | Natural gas transmission | Yes | political issue | N/A | Plans to complete a pipeline delivering Iranian gas to Pakistan stalled after Pakistan's energy ministry said last week that it could not continue with the project as long as Tehran was subject to US sanctions |  |  |  | 1995 |  | https://www.dw.com/en/iran-gas-pipeline-deal-with-pakistan-hampered-by-us-sanctions/a-48802450 | Delayed | Delay in Construction | Greenfield | https://www.dw.com/en/iran-gas-pipeline-deal-with-pakistan-hampered-by-us-sanctions/a-48802450 | N/A | N/A | City | 27.4723 | 52.6147
Kenya | N/A | JKIA Greenfield terminal project | Transport | Airports | Runway and terminal | No | etc. | N/A | President Uhuru Kenyatta launch the greenfield terminal project in 2013 by but the contract was terminated in 2016. |  |  |  | 2013 |  | https://www.enr.com/articles/46961-kenya-feuds-with-chinese-contractor-over-cancelled-terminal-job | Cancelled | Cancel in Construction | Greenfield | https://www.enr.com/articles/46961-kenya-feuds-with-chinese-contractor-over-cancelled-terminal-job | N/A | N/A | Exact Location | -1.3219 | 36.9266
Bulgaria | N/A | Gorna Arda Hydro Power Plant | Energy | Electricity | Electricity generation | No | political issue | N/A | Further implementation of Gorna Arda hydro power project is not realizable in the current environment due to changed energy policy conditions in Bulgaria |  |  |  | 2010 |  | https://en.wikipedia.org/wiki/Gorna_Arda_Hydro_Power_Plant | Delayed | Delay before Construction | Greenfield | https://balkangreenenergynews.com/evn-suspends-construction-hydropower-plants-bulgaria/ | N/A | N/A | City | 41.4489 | 24.6068
India, Pakistan | N/A | Ratle hydro projects | Energy | Electricity | Electricity generation and transmission | Yes | political issue | N/A | Pakistan’s two parliamentary committees in rare joint resolution asked India to immediately suspend work on two hydropower projects in Jammu and Kashmir and agree on the constitution of an arbitration court to resolve the water dispute. |  |  |  | 2017 |  | https://timesofindia.indiatimes.com/india/india-permitted-to-construct-kishanganga-ratle-projects-world-bank/articleshow/59874464.cms | Delayed | Delay in Construction | Greenfield | https://www.livemint.com/Politics/uWCEoP5KmzKrtsduAbU9QO/Pakistan-asks-India-to-suspend-work-on-hydro-projects-in-Ja.html | Resumed | https://www.timesnownews.com/india/article/pakistan-india-ratle-hydroelectric-project-indus-water-treaty-agreement-chenab-shahpur-kandi-dam-project-ujh-multipurpose-project-jammu-and-kashmir/310636 | Exact Location | 33.1771
Note on D1: 있음 -Stella Kim
Note on N1: 있음 -Stella Kim
Note on T1: 있는데 이름 status -Stella Kim
Note on V1: 있는데 이름 PPI Type -Stella Kim
Note on W92: 구글에서 '저장된 페이지' 로 들어가서 보면 로그인 없이 볼 수 있습니당 -Jaehee Yoo
Note on H142: The decision was motivated by the impact of the coronavirus disease pandemic on the normal development of activities worldwide, the same reason the ministry gave when it postponed the round in April.
Note on H144: The decision was motivated by the impact of the coronavirus disease pandemic on the normal development of activities worldwide, the same reason the ministry gave when it postponed the round in April.
Note on H152: The decision was motivated by the impact of the coronavirus disease pandemic on the normal development of activities worldwide, the same reason the ministry gave when it postponed the round in April.
Note on B155: Kempegowda Airport 프로젝트와 같은 프로젝트인것 같습니다. -Jae Hyun Kim
Note on W155: 빨간 음영은 유료 전환이거나 접속이 안되는 url입니다. -Jae Hyun Kim
Note on W195: Unvalid 이유 : Take a Free Trial to unlock article. 기존기사 https://ijglobal.com/articles/149170/bosnia-and-herzegovina-road-ppp-fc-delaye 대체 기사(2020.12.16) : https://tekdeeps.com/the-parcelling-plan-for-the-banja-luka-prijedor-highway-is-two-years-late/
Note on W199: Unvalid 이유 : page not found 기존 기사 링크 https://www.universalpersonality.com/tensions-with-china-covid-hit-mumbai-coastal-tunnel-work-mumbai-news-times-of-india/
Note on H294: safety issue면 environmental issue가 맞나요?
Note on E311: Natural gas VS oil gas pipeline -강민정